## Information
Client Line 1: | Province of KwaZulu-Natal
Client Line 2: | Department of Transport
Contract No | ZNB01216/00000/00/PMC/INF/21/T
Contract Description | PROVISION OF ROUTINE AND SAFETY MAINTENANCE ON VARIOUS ROADS WITHIN THE IMPENDLE ZONE - VULINDLELA AREA OFFICE
TRUE
Summary Pages:
A | 39
Contract Duration | 24 | Months
Roads | Start Chainage | End Chainage | Total Distance
0
0
Road Type | P | P | 0
Road Width |  | D
L
Distance to Quarry |  | km
Summary Pages:
A | 50
E | 51
F | 54
Summary | 55
Show Pricing in BoQ

## C1.2
250000
Province of KwaZulu-Natal |  |  | Contract No. ZNB01216/00000/00/PMC/INF/21/T
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C1.2
PROVISION OF ROUTINE AND SAFETY MAINTENANCE ON VARIOUS ROADS WITHIN THE IMPENDLE ZONE - VULINDLELA AREA OFFICE
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C1.2 | GENERAL REQUIREMENTS AND PAYMENT
C1.2.2 | Programming and Reporting
C1.2.2.1 | Submission of a Scheme 1 Programme | Lump Sum | 1
C1.2.2.5 | Reviewing and updating a Scheme 1 Programme | month | 24
C1.2.2.6 | Preparation and submission of all information and reports specified in the Contract Documentation | month | 24
P.S.C1.2.4 | Stakeholder Liaison
P.S.C1.2.4.1 | Provision of a Community Liaison Officer (CLO) | Prov Sum | 1 | 250000 | 250000
| (b) Handling costs and profit in respect of subitem P.S.C1.2.4.1(a) above | % | 250000
P.S.C1.2.4.2 | Compensation for Project Liaison Committee:
| (a) Provisional sum for Project Liaison Committee | Prov Sum | 1 | 100000 | 100000
| (b) Handling costs and profit in respect of subitem P.S.C1.2.4.2(a) above | % | 100000
C1.2.5 | Safety
C1.2.5.1 | Health and safety plan | Lump Sum | 1
C1.2.5.2 | Implementation of health and safety plan | month | 24
C1.2.8 | Dayworks
C1.2.8.1 | Personnel
(a) | Unskilled labourer | hour | 24
(b) | Semi-skilled labourer | hour | 24
(c) | Skilled labourer | hour | 24
(d) | Gang leader | hour | 24
(e) | Foreman | hour | 24
(f) | Skilled Artisan | hour | 24
C1.2.8.2 | Construction Equipment (specify size and/or model number)
(a) | Motor grader | hour | 24
(b) | Vibratory roller | hour | 24
(c) | Pneumatic roller | hour | 24
(d) | Front end loader backhoe | hour | 24
(e) | Excavator | hour | 24
(f) | Compressor | hour | 24
C1.2 | TOTAL CARRIED FORWARD
Province of KwaZulu-Natal |  |  | Contract No. ZNB01216/00000/00/PMC/INF/21/T
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C1.2
PROVISION OF ROUTINE AND SAFETY MAINTENANCE ON VARIOUS ROADS WITHIN THE IMPENDLE ZONE - VULINDLELA AREA OFFICE
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
TOTAL BROUGHT FORWARD
C1.2.8.3 | Vehicles (specify size)
(a) | Light delivery vehicle | km | 100
(b) | Flatbed truck | km | 100
(c) | Dump Truck | km | 100
C1.2.8.4 | Materials
(a) | Procurement of materials | Prov Sum | 1 | 100000 | 100000
(b) | Contractor's handling costs, profit and all other charges in respect of item C1.2.8.4(a) | % | 100000
C1.2 | TOTAL CARRIED FORWARD TO SUMMARY PAGE C50

## C1.3
0
Province of KwaZulu-Natal |  |  | Contract No. ZNB01216/00000/00/PMC/INF/21/T |  |  | 0
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C1.3
PROVISION OF ROUTINE AND SAFETY MAINTENANCE ON VARIOUS ROADS WITHIN THE IMPENDLE ZONE - VULINDLELA AREA OFFICE
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C1.3 | CONTRACTOR'S SITE ESTABLISHMENT AND GENERAL OBLIGATIONS
C1.3.1 | The Contractor's general obligations
C1.3.1.1 | Fixed obligations | Lump Sum | 1
C1.3.1.3 | Time-related obligations | month | 24
C1.3.2 | Contract sign boards | m2 | 12
Note: The combined total tendered for subitems C1.3.1.1 and C1.3.1.3 shall not exceed 15% of the Tender Sum (excluding contingencies, CPA and VAT).
C1.3 | TOTAL CARRIED FORWARD TO SUMMARY (Page C50)

## C1.5
0
Province of KwaZulu-Natal |  |  | Contract No. ZNB01216/00000/00/PMC/INF/21/T
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C1.5
PROVISION OF ROUTINE AND SAFETY MAINTENANCE ON VARIOUS ROADS WITHIN THE IMPENDLE ZONE - VULINDLELA AREA OFFICE
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C1.5 | ACCOMMODATION OF TRAFFIC
C1.5.2 | Accommodation of vehicular traffic | month | 24
C1.5.7 | Temporary traffic control facilities
C1.5.7.1 | Delineators including mounting bases and ballast:
(a) | Single sided, reversible left or right (1000mm x 250mm) | No | 500
(b) | Double sided, reversible left or right (1000 mm x 250mm) | No | 500
C1.5.7.2 | Traffic cones, minimum height 750 mm | No | 400
C1.5.7.3 | Flagmen | man-shift | 3000
C1.5.7.4 | Traffic controllers | man-shift | 600
C1.5.7.7 | Traffic calming devices:
(b) | Rumble strips as per SD0314/A | m | 20
(c) | Speed Control Humps as per SD0314/A | m | 20
C1.5.7.8 | Traffic control stations | month | 16
P.S.C 1.5.13 | (a) Blading by road grader of: > 6m
| (i) Machine trimming: Normal Blading - 3% | km | 600
| (ii) Machine trimming: Dry Road Blading using Watercart - chamber 3% | km | 300
(b) Blading by road grader of: < 6m
| (i) Machine trimming: Normal Blading - Without using Watercart - 3% | km | 300
| (ii) Machine trimming: Dry Road Blading using Watercart- chamber 3% | km | 150
C1.5 | TOTAL CARRIED FORWARD TO SUMMARY (Page C50)

## C1.6
0
Province of KwaZulu-Natal |  |  | Contract No. ZNB01216/00000/00/PMC/INF/21/T
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C1.6
PROVISION OF ROUTINE AND SAFETY MAINTENANCE ON VARIOUS ROADS WITHIN THE IMPENDLE ZONE - VULINDLELA AREA OFFICE
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C1.6 | CLEARING AND GRUBBING
C1.6.1 | Clearing
C1.6.1.1 | Clearing with machines and some hand labour where necessary | ha | 0.2
C1.6.1.2 | Clearing with hand labour only when labour enhanced work is specified | ha | 0.2
C1.6.2 | Grubbing
C1.6.2.1 | Grubbing with machines and some hand labour where necessary | ha | 0.2
C1.6.2.2 | Grubbing with hand labour only when labour enhanced work is specified or it is not practical to use a machine | ha | 0.2
P.S.C 1.6.11 | Removal and grubbing of trees and tree stumps:
(c) Cutting of smaller trees.
| (i) Felling and Removal of trees : 200m to 400mm | No | 1000
| (ii) Felling and Removal of trees : 401m to 600mm | No | 100
| (iii) Felling and Removal of trees : 601m to 800mm | No | 100
| (iv) Felling and Removal of trees : 801m to 1000mm | No | 100
| (v) Chemical treatment of tree stumps with chemical | No | 1000
C1.6 | TOTAL CARRIED FORWARD TO SUMMARY (Page C50)

## C1.7
0
Province of KwaZulu-Natal |  |  | Contract No. ZNB01216/00000/00/PMC/INF/21/T
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C1.7
PROVISION OF ROUTINE AND SAFETY MAINTENANCE ON VARIOUS ROADS WITHIN THE IMPENDLE ZONE - VULINDLELA AREA OFFICE
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C1.7 | LOADING AND HAULING
C1.7.1 | Loading
C1.7.1.1 | Loading from stockpile using machines and some hand labour where necessary | m3 | 2625
C1.7.1.2 | Loading from heaps or windrows using machines and/some hand labour where necessary | m3 | 1050
C1.7.1.3 | Loading by hand only from stockpile or heaps when labour ehancement work is specified or is not possible to use machines | m3 | 262.5
C1.7.2 | Hauling
C1.7.2.1 | Hauling material for use in the Works and off-loading it on the site of the Works:
(a) | Soil, gravel, crushed stone and pavement layer material | m3 - km | 10000
(b) | Boulders and hard material | m3 - km | 10000
C1.7.2.2 | Hauling material to spoil and off-loading it at a designated spoil or stockpile are:
(a) | Cleared and grubbed material (organic matter and all other unsuitable or waste material) | m3 - km | 10000
(b) | Soil and gravel material | m3 - km | 10000
(c) | Boulders, hard material and concrete | m3 - km | 2625
C1.7 | TOTAL CARRIED FORWARD TO SUMMARY (Page C50)

## C3.2
0
Province of KwaZulu-Natal |  |  | Contract No. ZNB01216/00000/00/PMC/INF/21/T
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C3.2
PROVISION OF ROUTINE AND SAFETY MAINTENANCE ON VARIOUS ROADS WITHIN THE IMPENDLE ZONE - VULINDLELA AREA OFFICE
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C3.2 | CULVERTS
C3.2.1 | Excavation for culvert structures:
C3.2.1.1 | Excavating in all material situated within the following depth ranges below the surface level:
(a) | 0m to 1.5m | m3 | 600
(b) | Exceeding 1.5m and up to 3.0m | m3 | 550
C3.2.1.2 | Excavating soft material 0 m to 1,5 m below the surface level using labour enhanced construction methods, or instructed by hand under Clause A3.2.7.2d): | m3 | 60
C3.2.1.4 | Extra over sub-item C3.2.1.1 for excavation in hard or boulder material, irrespective of depth | m3 | 9
C3.2.2 | Backfilling:
C3.2.2.1 | Using the excavated material | m3 | 875
C3.2.2.2 | Using imported selected material:
(a) | From commercial sources (G6) | m3 | 95
C3.2.3 | Concrete pipe culverts:
C3.2.3.3 | On Class C bedding Class 100D
| 2) 600 mm Diameter | m | 500
| 3) 900 mm Diameter | m | 75
C3.2.3.5 | Provision of skew ends of pipe culvert (Class 100D)
| 2) 600 mm Diameter | No | 0.6
| 3) 900 mm Diameter | No | 0.6
C3.2.7 | Cast in situ concrete and formwork:
C3.2.7.5 | In inlet and outlet structures including kerbs, chutes and downpipes, skewed ends, catchpits, manholes, thrust and anchor blocks, excluding formwork but including Class U2 surfacing finish (30MPa) | m3 | 95
C3.2.7.6 | Formwork of concrete under items C3.2.7.3 to 5 above (F1 finish ) | m2 | 515
C3.2 | TOTAL CARRIED FORWARD
Province of KwaZulu-Natal |  |  | Contract No. ZNB01216/00000/00/PMC/INF/21/T
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C3.2
PROVISION OF ROUTINE AND SAFETY MAINTENANCE ON VARIOUS ROADS WITHIN THE IMPENDLE ZONE - VULINDLELA AREA OFFICE
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
TOTAL BROUGHT FORWARD
C3.2.10 | Reinforcement:
C3.2.10.3 | Welded steel fabric (Ref 193) | kg | 980
C3.2.13 | Removing and re-laying existing culverts:
C3.2.13.1 | Removing and stacking existing culverts for re-use (600mm concrete pipes) | m | 5
C3.2.16 | Brickwork (Engineering bricks):
C3.2.16.2 | 230 mm thick | m² | 580
C3.2.24 | Compaction of bedding for inlets, outlets, manholes and catchpits:
C3.2.24.1 | Preparation and compaction of in situ bedding material to 90 % of MDD (150mm Deep) | m³ | 62.6846
C3.2 | TOTAL CARRIED FORWARD TO SUMMARY (Page C50)

## C3.3
0
Province of KwaZulu-Natal |  |  | Contract No. ZNB01216/00000/00/PMC/INF/21/T
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C3.3
PROVISION OF ROUTINE AND SAFETY MAINTENANCE ON VARIOUS ROADS WITHIN THE IMPENDLE ZONE - VULINDLELA AREA OFFICE
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C3.3 | CONCRETE KERBING AND CHANNELING, ASPHALT BERMS, CHUTES, DOWNPIPES, AS WELL AS CONCRETE, STONE PITCHED AND GABION LININGS FOR OPEN DRAINS
C3.3.1 | Concrete kerbing:
C3.3.1.1 | Prefabricated kerbing
(a) | SABS 927 figure 7, as shown on drawing no. SD 0309/B | m | 100
(b) | SABS 927 figure 8, as shown on drawing no. SD 0309/B | m | 100
C3.3.2 | Concrete kerbing-channeling combination:
C3.3.2.1 | Prefabricated kerbing-channeling
(a) | Precast kerb (Fig. 6) and 1000m wide channel 7 as per SD0701/A | m | 100
(b) | Precast kerb (Fig. 6) and 500m wide channel 7 as per SD0701/A | m | 100
C3.3.3 | Extra over items C3.3.1 and C3.3.2 for concrete kerbing or concrete kerbing and channeling on curves
C3.3.3.1 | On curves of radii more than or equal to 5,0 m but less than 20 m | m | 40
C3.3.3.2 | On curves with radii more than or equal to 1,0 m but less than 5,0 m | m | 20
C3.3 | TOTAL CARRIED FORWARD TO SUMMARY (Page C50)

## C4.1
0
Province of KwaZulu-Natal |  |  | Contract No. ZNB01216/00000/00/PMC/INF/21/T
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C4.1
PROVISION OF ROUTINE AND SAFETY MAINTENANCE ON VARIOUS ROADS WITHIN THE IMPENDLE ZONE - VULINDLELA AREA OFFICE
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C4.1 | BORROW MATERIALS
C4.1.4 | Removing of the overburden
C4.1.4.1 | In borrow pits | m3 | 100
C4.1.5 | Excavating of materials in the borrow pits and quarries, material obtained from
C4.1.5.1 | Soft excavation | m3 | 1000
C4.1.5.2 | Boulder excavation class A | m3 | 1000
C4.1.5.4 | Hard excavation (other than by blasting) | m3 | 1000
C4.1.15.1 | Shaping and finishing the borrow pit and quarry areas, and the stockpile sites:
(a) | Borrow pits | ha | 0.8
C4.1 | TOTAL CARRIED FORWARD TO SUMMARY (Page C50)

## C4.4
0
Province of KwaZulu-Natal |  |  | Contract No. ZNB01216/00000/00/PMC/INF/21/T
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C4.4
PROVISION OF ROUTINE AND SAFETY MAINTENANCE ON VARIOUS ROADS WITHIN THE IMPENDLE ZONE - VULINDLELA AREA OFFICE
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C4.4 | COMMERCIAL MATERIALS
C4.4.2 | Commercial materials identified by the Contractor from commercial, private or other non-commercial suppliers
C4.4.2.1 | Pavement layer material:
(q) | Natural or crushed gravel material for the wearing course of an unsealed road | m3 | 10050
C4.4 | TOTAL CARRIED FORWARD TO SUMMARY (Page C50)

## C5.1
0
Province of KwaZulu-Natal |  |  | Contract No. ZNB01216/00000/00/PMC/INF/21/T
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C5.1
PROVISION OF ROUTINE AND SAFETY MAINTENANCE ON VARIOUS ROADS WITHIN THE IMPENDLE ZONE - VULINDLELA AREA OFFICE
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C5.1 | ROADBED
C5.1.1 | Roadbed construction and compaction
C5.1.1.2 | Compaction of in-situ material to 93% of MDD | m3 | 11700
C5.1 | TOTAL CARRIED FORWARD TO SUMMARY (Page C50)

## C5.3
0
Province of KwaZulu-Natal |  |  | Contract No. ZNB01216/00000/00/PMC/INF/21/T
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C5.3
PROVISION OF ROUTINE AND SAFETY MAINTENANCE ON VARIOUS ROADS WITHIN THE IMPENDLE ZONE - VULINDLELA AREA OFFICE
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C5.3 | ROAD PAVEMENT LAYERS
C5.3.2 | Construction of pavement layers
C5.3.2.1 | Construction of layers using conventional construction methods:
(g) | Gravel wearing course layer (150mm) compacted to 95% of MDD | m3 | 10050
C5.3 | TOTAL CARRIED FORWARD TO SUMMARY (Page C50)

## C6.1
0
Province of KwaZulu-Natal |  |  | Contract No. ZNB01216/00000/00/PMC/INF/21/T
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C6.1
PROVISION OF ROUTINE AND SAFETY MAINTENANCE ON VARIOUS ROADS WITHIN THE IMPENDLE ZONE - VULINDLELA AREA OFFICE
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C6.1 | PAVER LAID CONCRETE LAYERS
C6.1.1 | Construction of trial section (Complete: including texturing and curing)
C6.1.1.2 | Labour enhanced construction (200mm thick) | m2 | 150
C6.1.2 | Construction of jointed concrete pavement (JCP) (Excluding texturing and curing)
C6.1.2.1 | JCP without dowels:
(b) | Labour enhanced construction (200mm thick) | m2 | 3750
C6.1.2.2 | JCP with dowels:
(b) | Labour enhanced construction (200mm thick) | m2 | 750
C6.1.2.3 | Additional concrete placed to thicken up the slab at joints as specified in the Contract Documentation | m3 | 75
C6.1.4 | Texturing and curing the concrete pavement
C6.1.4.1 | Burlap-dragged and grooved texture:
(b) | Labour enhanced construction | m2 | 4500
C6.1.4.2 | Burlap-dragged and broom finish only | m2 | 150
C6.1.4.3 | Curing:
(b) | Labour enhanced construction | m2 | 4500
C6.1.5 | Variation in the rate of application of the curing compound | ℓ | 160
C6.1.6 | Joints
C6.1.6.1 | Expansion joints complete (excluding dowels) | m | 675
C6.1 | TOTAL CARRIED FORWARD TO SUMMARY (Page C50)
Province of KwaZulu-Natal |  |  | Contract No. ZNB01216/00000/00/PMC/INF/21/T
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C6.1
PROVISION OF ROUTINE AND SAFETY MAINTENANCE ON VARIOUS ROADS WITHIN THE IMPENDLE ZONE - VULINDLELA AREA OFFICE
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
TOTAL BROUGHT FORWARD
C6.1.6.2 | Longitudinal hinge joints:
(a) | Sealed hinge joints (indicate type and reference to drawings) | m | 225
C6.1.6.3 | Sealed transverse contraction joints sawn in two separate operations (widths as shown on the drawings) | m | 300
C6.1.7 | Steel reinforcement in concrete pavements
C6.1.7.1 | Mild steel bars | t | 1
C6.1.7.2 | High tensile steel bars | t | 1
C6.1.7.3 | Welded steel fabric | kg | 225
C6.1.8 | Drilling of testing of cores
C6.1.8.1 | 100 mm cores drilled from pavement for testing of compressive strength | No | 15
C6.1 | TOTAL CARRIED FORWARD TO SUMMARY (Page C50)

## C8.5
0
Province of KwaZulu-Natal |  |  | Contract No. ZNB01216/00000/00/PMC/INF/21/T
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C8.5
PROVISION OF ROUTINE AND SAFETY MAINTENANCE ON VARIOUS ROADS WITHIN THE IMPENDLE ZONE - VULINDLELA AREA OFFICE
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C8.5 | STANDARD CRACK SEALING
C8.5.1.1 | Cleaning cracks
(a) | Cleaning cracks with cold compressed air | m | 4000
C8.5.1.3 | Priming (invert bitumen emulsion) | ℓ | 80
C8.5.1.4 | Sealing the cracks
(a) | Sealing using (Class C-E1 modified binder crack sealant) | ℓ | 160
C8.5 | TOTAL CARRIED FORWARD TO SUMMARY (Page C50)

## C8.8
0
Province of KwaZulu-Natal |  |  | Contract No. ZNB01216/00000/00/PMC/INF/21/T
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C8.8
PROVISION OF ROUTINE AND SAFETY MAINTENANCE ON VARIOUS ROADS WITHIN THE IMPENDLE ZONE - VULINDLELA AREA OFFICE
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C8.8 | PATCHING AND EDGE BREAK REPAIR
C8.8.1 | Saw cutting pavement layers for patching
C8.8.1.1 | Asphalt or bituminous surfacing to an average depth
(a) | Not exceeding 50 mm | m | 26460
(b) | Exceeding 50 mm but not exceeding 100 mm | m | 9450
(c) | Exceeding 100 mm | m | 1890
C8.8.1.2 | Cemented pavement layers to an average depth
(a) | Not exceeding 100 mm | m | 945
(b) | Exceeding 100 mm but not exceeding 200 mm | m | 2646
(c) | Exceeding 200 mm | m | 189
C8.8.1.3 | Granular layers to an average depth
(a) | Not exceeding 100 mm | m | 189
(b) | Not exceeding 200 mm | m | 2646
(c) | Excedding 200 mm | m | 945
C8.8.2 | Excavation in existing pavements for patching (non-milling)
C8.8.2.1 | Asphalt layers
(a) | Not exceeding 10 m2, including for edge repairs wider than 250 mm | m3 | 324
(b) | Exceeding 10 m2 but not exceeding 50 m2, including for edge repairs wider than 250 mm | m3 | 594
(c) | Exceeding 50 m2 up to 100 m2, including for edge repairs wider than 250 mm | m3 | 108
(d) | Exceeding 100 m2 | m3 | 54
C8.8.2.2 | Cemented layers
(a) | Not exceeding 10 m2, including for edge repairs wider than 250 mm | m3 | 205
(b) | Exceeding 10 m2 but not exceeding 50 m2, including for edge repairs wider than 250 mm | m3 | 142
(c) | Exceeding 50 m2 up to 100 m2, including for edge repairs wider than 250 mm | m3 | 41
(d) | Exceeding 100 m2 | m3 | 21
C8.8.2.3 | Other layers (Granular)
(a) | Not exceeding 10 m2, including for edge repairs wider than 250 mm | m3 | 270
(b) | Exceeding 10 m2 but not exceeding 50 m2, including for edge repairs wider than 250 mm | m3 | 162
C8.8 | TOTAL CARRIED FORWARD TO SUMMARY (Page C50)
Province of KwaZulu-Natal |  |  | Contract No. ZNB01216/00000/00/PMC/INF/21/T
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C8.8
PROVISION OF ROUTINE AND SAFETY MAINTENANCE ON VARIOUS ROADS WITHIN THE IMPENDLE ZONE - VULINDLELA AREA OFFICE
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
TOTAL BROUGHT FORWARD
(c) | Exceeding 50 m2 up to 100 m2, including for edge repairs wider than 250 mm | m3 | 81
(d) | Exceeding 100 m2 | m3 | 30
C8.8.3 | Compacting the floor of excavations for patching (98% MOD AASHTO) | m2 | 27000
C8.8.4 | Backfilling of excavations for patching with:
C8.8.4.1 | Chemically stabilised pavement materials (G2 Stabilised with 2% Cement compacted to 98% MOD AASHTO) for a patch with a surface area:
(a) | Not exceeding 10 m2, including for edge repairs wider than 250 mm | m3 | 205
(b) | Exceeding 10 m2 but not exceeding 50 m2, including for edge repairs wider than 250 mm | m3 | 142
(c) | Exceeding 50 m2 up to 100 m2, including for edge repairs wider than 250 mm | m3 | 41
(d) | Exceeding 100 m2 | m3 | 21
C8.8.4.3 | Asphalt for a patch with a surface area (Continuously graded medium asphalt with a 50/70 Pen Grade binder with a maximum aggregate size of 14mm and compacted to a density of 97% RICE):
(a) | Not exceeding 10 m2, including for edge repairs wider than 250 mm | t | 777.6
(b) | Exceeding 10 m2 but not exceeding 50 m2, including for edge repairs wider than 250 mm | t | 1425.6
(c) | Exceeding 50 m2 up to 100 m2, including for edge repairs wider than 250 mm | t | 259.2
(d) | Exceeding 100 m2 | t | 129.6
C8.8.4.4 | Granular base material (G2 compacted to 85% Bulk Relative Density) for a patch with a surface area:
(a) | Not exceeding 10 m2, including for edge repairs wider than 250 mm | t | 526.5
(b) | Exceeding 10 m2 but not exceeding 50 m2, including for edge repairs wider than 250 mm | t | 315.9
(c) | Exceeding 50 m2 up to 100 m2, including for edge repairs wider than 250 mm | t | 157.95
(d) | Exceeding 100 m2 | t | 58.5
C8.8 | TOTAL CARRIED FORWARD TO SUMMARY (Page C50)

## C9.1
0
Province of KwaZulu-Natal |  |  | Contract No. ZNB01216/00000/00/PMC/INF/21/T
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C9.1
PROVISION OF ROUTINE AND SAFETY MAINTENANCE ON VARIOUS ROADS WITHIN THE IMPENDLE ZONE - VULINDLELA AREA OFFICE
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C9.1 | ASPHALT LAYERS
C9.1.1 | Asphalt mix designs
C9.1.3 | Application of bond coat
C9.1.3.2 | Applied in restricted ares using a portable pressure sprayer | ℓ | 14850
C9.1.3.3 | Applied by hand using brushes on all exposed transverse and longitudinal construction joints | ℓ | 742.5
C9.1 | TOTAL CARRIED FORWARD TO SUMMARY (Page C50)

## C11.6
0
Province of KwaZulu-Natal |  |  | Contract No. ZNB01216/00000/00/PMC/INF/21/T
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C11.6
PROVISION OF ROUTINE AND SAFETY MAINTENANCE ON VARIOUS ROADS WITHIN THE IMPENDLE ZONE - VULINDLELA AREA OFFICE
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C11.6 | ROAD SIGNS
C11.6.1 | Road signboards with painted or coloured semi-matt background. Symbols, lettering and borders in semi- matt black or in Class I retro-reflective material, where the sign board is constructed from:
C11.6.1.8 | Regulatory signs, temporary
(a) | 600 mm diameter (signboard material - Steel Plate 1.4mm thick, background - Class I and symbol retro-reflective class III) | No | 50
C11.6.1.9 | Warning signs, permanent
(a) | 600 mm diameter (signboard material - Steel Plate 1.4mm thick, background - Class I and symbol retro-reflective class III) | No
C11.6.1.10 | Warning signs, temporary
(a) | 600 mm diameter (signboard material - Steel Plate 1.4mm thick, background - Class I and symbol retro-reflective class III) | No | 25
C11.6.3 | Road sign supports (overhead road sign structures excluded):
C11.6.5 | Excavation and backfilling for road sign supports (not applicable to kilometre posts)
C11.6.5.2 | Excavating soft or intermediate material and backfilling using labour enhanced construction methods | m³ | 15
C11.6.5.4 | Extra over item C11.6.5.1 for hard material excavation | m³ | 5
C11.6 | TOTAL CARRIED FORWARD TO SUMMARY (Page C50)

## C11.9
0
Province of KwaZulu-Natal |  |  | Contract No. ZNB01216/00000/00/PMC/INF/21/T
Department of Transport
CHAPTER 11 |  |  |  |  | CHAPTER C11.9
PROVISION OF ROUTINE AND SAFETY MAINTENANCE ON VARIOUS ROADS WITHIN THE IMPENDLE ZONE - VULINDLELA AREA OFFICE
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C11.9 | FINISHING THE ROAD AND ROAD RESERVE AND TREATING OLD ROADS
C11.9.1 | Finishing the road and road reserve:
C11.9.1.2 | Single carriageway road | km | 100
C11.9 | TOTAL CARRIED FORWARD TO SUMMARY (Page C50)

## A1
| Page C50 |  | 0
Province of KwaZulu-Natal |  |  |  | Contract No. ZNB01216/00000/00/PMC/INF/21/T
Department of Transport
SCHEDULE A: ROADWORKS
SUMMARY OF SECTIONS
PROVISION OF ROUTINE AND SAFETY MAINTENANCE ON VARIOUS ROADS WITHIN THE IMPENDLE ZONE - VULINDLELA AREA OFFICE
CHAPTER | DESCRIPTION | FROM PAGE | AMOUNT
C1.2 | GENERAL REQUIREMENTS AND PAYMENT | 30 |  |  | 2
C1.3 | CONTRACTOR'S SITE ESTABLISHMENT AND GENERAL OBLIGATIONS | 31 |  |  | 1 | 57
C1.5 | ACCOMMODATION OF TRAFFIC | 32 |  |  | 1
C1.6 | CLEARING AND GRUBBING | 33 |  |  | 1
C1.7 | LOADING AND HAULING | 34 |  |  | 1
C3.2 | CULVERTS | 36 |  |  | 2
C3.3 | CONCRETE KERBING AND CHANNELING, ASPHALT BERMS, CHUTES, DOWNPIPES, AS WELL AS CONCRETE, STONE PITCHED AND GABION LININGS FOR OPEN DRAINS | 37 |  |  | 1
C4.1 | BORROW MATERIALS | 38 |  |  | 1
C4.4 | COMMERCIAL MATERIALS | 39 |  |  | 1
C5.1 | ROADBED | 40 |  |  | 1
C5.3 | ROAD PAVEMENT LAYERS | 41 |  |  | 1
C6.1 | PAVER LAID CONCRETE LAYERS | 43 |  |  | 2
C8.5 | STANDARD CRACK SEALING | 44 |  |  | 1
C8.8 | PATCHING AND EDGE BREAK REPAIR | 46 |  |  | 2
C9.1 | ASPHALT LAYERS | 47 |  |  | 1
C11.6 | ROAD SIGNS | 48 |  |  | 1
C11.9 | FINISHING THE ROAD AND ROAD RESERVE AND TREATING OLD ROADS | 49 |  |  | 1
1
TOTAL CARRIED FORWARD TO SUMMARY (Page C55)
50

## Chapter E
900000
Province of KwaZulu-Natal |  |  | Contract No. ZNB01216/00000/00/PMC/INF/21/T
Department of Transport
SCHEDULE E: EXPANDED PUBLIC WORKS PROGRAMME (EPWP) |  |  |  |  | CHAPTER E
PROVISION OF ROUTINE AND SAFETY MAINTENANCE ON VARIOUS ROADS WITHIN THE IMPENDLE ZONE - VULINDLELA AREA OFFICE
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
E | EXPANDED PUBLIC WORKS PROGRAMME (EPWP)
E6.01 | Provision of training venue facility, including the cost of transport the learners to and from this facility | Lump Sum | 1
E6.02 | Training of learners employed by the contractor or by the Targeted Enterprise subcontractors:
(a) | Generic Skills:
(a.i) | Training costs | Prov Sum | 500000 | 1 | 500000
(a.ii) | Handling costs and profit in respect of subitem E6.02(a)(i) above. | % | 500000
(b) | Entrepreneurial skills:
(b.i) | Training costs | Prov Sum | 500000 | 1 | 500000
(b.ii) | Handling costs and profit in respect of subitem E6.02(b)(i) above. | % | 500000
(c) | Construction skills:
(c.i) | Training costs | Prov Sum | 500000 | 1 | 500000
(c.ii) | Handling costs and profit in respect of subitem E6.02(c)(i) above. | % | 500000
(d) | Transportation and accommodation costs of selected learners only, while receiving off-site training:
(d.i) | Transportation and accommodation costs | Prov Sum | 100000 | 1 | 100000
(d.ii) | Handling costs and profit in respect of subitem E6.02(d)(i) above. | % | 100000
E6.03 | Payments associated with the NYS programme:
(a) | Employment of NYS workers | Prov Sum | 500000 | 1 | 500000
(b) | Provision of tools and apparel for the NYS workers | Prov Sum | 50000 | 1 | 50000
(c) | Handling cost and profit in respect of subitem E6.03(a) and (b) above | % | 550000
(d) | Training of NYS workers:
(d.i) | Provision of training for NYS workers | Prov Sum | 900000 | 1 | 900000
(d.ii) | Handling costs and profit in respect of subitem subitem E6.03(d)(i) above | % | 900000
(e) | Liaison with the Employer’s project manager and the training service provider:
(e.i) | Liaison conducted by the construction manager | hr | 60
(e.ii) | Liaison conducted by senior site foreman | hr | 60
(f) | EPWP Branding (refer to spec)
| (i) Prime cost sum for EPWP branding | PC Sum | 50000 | 1 | 50000
| (ii) Handling costs and profit in respect of sub item F5.03(f)(i)above | % | 50000
E | TOTAL CARRIED FORWARD TO SUMMARY

## E1
Province of KwaZulu-Natal |  |  |  | Contract No. ZNB01216/00000/00/PMC/INF/21/T
Department of Transport
SCHEDULE E: EXPANDED PUBLIC WORKS PROGRAMME (EPWP)
SUMMARY OF SECTIONS
PROVISION OF ROUTINE AND SAFETY MAINTENANCE ON VARIOUS ROADS WITHIN THE IMPENDLE ZONE - VULINDLELA AREA OFFICE
CHAPTER | DESCRIPTION | FROM PAGE | AMOUNT
E | EXPANDED PUBLIC WORKS PROGRAMME (EPWP) | C51
TOTAL CARRIED FORWARD TO SUMMARY (Page C55) |  |  |  |  | 57

## Chapter F
22288184.536
Province of KwaZulu-Natal |  |  | Contract No. ZNB01216/00000/00/PMC/INF/21/T
Department of Transport
SCHEDULE F: SMALL CONTRACTOR DEVELOPMENT |  |  |  |  | CHAPTER F
PROVISION OF ROUTINE AND SAFETY MAINTENANCE ON VARIOUS ROADS WITHIN THE IMPENDLE ZONE - VULINDLELA AREA OFFICE
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
F | SMALL CONTRACTOR DEVELOPMENT
F10.1 | Procurement of Targeted Enterprises:
(a) | Management and execution of Targeted Enterprise procurement process:
(a.i) | Procurement process for the appointment of CIDB contractor grading designation 1 Targeted Enterprise subcontractor (100 copies of the tender document required for each individual tender) | No | 7
(a.ii) | Procurement process for the appointment of CIDB contractor grading designation 2 Targeted Enterprise subcontractor (80 copies of the tender document required for each individual tender) | No | 5
(a.iii) | Procurement process for the appointment of CIDB contractor grading designation 3 Targeted Enterprise subcontractor (60 copies of the tender document required for each individual tender) | No | 5
(a.iv) | Procurement process for the appointment of CIDB contractor grading designation 4 Targeted Enterprise subcontractor (50 copies of the tender document required for each individual tender) | No | 1
F10.2 | Construction Works for Targeted Enterprise subcontractors:
(a) | Payments associated with the construction Works carried out by Targeted Enterprise subcontractors | Prov Sum | 22288184.536 | 1 | 22288184.536
(b) | Handling costs and profit in respect of subitem F10.02(a) | % | 22288184.536
(c) | Supply of materials and small construction equipment to assist Targeted Enterprise subcontractors | Prov Sum | 1173062.344 | 1 | 1173062.344
(d) | Handling costs and profit in respect of subitem F10.02(c) | % | 1173062.344
(e) | Management of the Targeted Enterprise subcontractors | Month | 24
F | TOTAL CARRIED FORWARD
Province of KwaZulu-Natal |  |  | Contract No. ZNB01216/00000/00/PMC/INF/21/T
Department of Transport
SCHEDULE F: SMALL CONTRACTOR DEVELOPMENT |  |  |  |  | CHAPTER F
PROVISION OF ROUTINE AND SAFETY MAINTENANCE ON VARIOUS ROADS WITHIN THE IMPENDLE ZONE - VULINDLELA AREA OFFICE
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
TOTAL BROUGHT FORWARD
(a) | Generic Skills
(a.i) | Training costs | Prov Sum | 150000 | 1 | 150000
(a.ii) | Handling costs and profit in respect of subitem F10.03(a)(i) | % | 150000
(b) | Entrepreneurial skills:
(b.i) | Training costs | Prov Sum | 200000 | 1 | 200000
(b.ii) | Handling costs and profit in respect of subitem F10.03(b)(i) | % | 200000
(c) | Construction skills:
(c.i) | Training costs | Prov Sum | 300000 | 1 | 300000
(c.ii) | Handling costs and profit in respect of subitem F10.03(c)(i) | % | 300000
(d) | Transportation and accommodation costs of selected learners only, while receiving off-site training:
(d.i) | Transportation and accommodation costs | Prov Sum | 295000 | 1 | 295000
(d.ii) | Handling costs and profit in respect of subitem F10.03(d)(i) | % | 295000
F | TOTAL CARRIED FORWARD TO SUMMARY

## F1
Province of KwaZulu-Natal |  |  |  | Contract No. ZNB01216/00000/00/PMC/INF/21/T
Department of Transport
SCHEDULE F: SMALL CONTRACTOR DEVELOPMENT
SUMMARY OF SECTIONS
PROVISION OF ROUTINE AND SAFETY MAINTENANCE ON VARIOUS ROADS WITHIN THE IMPENDLE ZONE - VULINDLELA AREA OFFICE
CHAPTER | DESCRIPTION | FROM PAGE | AMOUNT
F | SMALL CONTRACTOR DEVELOPMENT | C54
TOTAL CARRIED FORWARD TO SUMMARY (Page C55)

## Summary1
Province of KwaZulu-Natal |  |  |  | Contract No. ZNB01216/00000/00/PMC/INF/21/T
Department of Transport
C2.3 SUMMARY OF BILL OF QUANTITIES
PROVISION OF ROUTINE AND SAFETY MAINTENANCE ON VARIOUS ROADS WITHIN THE IMPENDLE ZONE - VULINDLELA AREA OFFICE
| DESCRIPTION | FROM PAGE | AMOUNT
TOTAL SCHEDULE A : ROADWORKS |  | C50
TOTAL SCHEDULE E: EXPANDED PUBLIC WORKS PROGRAMME |  | C52
TOTAL SCHEDULE F: CONTRACT PARTICIPATION GOALS |  | C54
Subtotal 1
CONTINGENCIES (10% of Subtotal 1)
Subtotal 2
CONTRACT PRICE ADJUSTMENT AND RISE & FALL (10% of Subtotal 2)
Subtotal 3
VAT (15% of Subtotal 3)
TOTAL CARRIED FORWARD TO FORM OF OFFER
Signed on behalf of the Tenderer: ……………………………………………………. (Signature) Date: ………………………………………………….. Tenderer’s Name: ………………………………………………………………. (Company Name)
DISCLAIMER
Kindly note that the responsibility lies with Tenderer to check the tender document and the tender addenda (if issued) to verify that all the information is correct and all changes have been incorporated as no claims will be entertained in this regard afterwards. Accordingly, we confirm that the hard copies of the original tender document and the tender addenda are to be regarded to contain the correct items and quantities.