## Information
Client Line 1: | Province of KwaZulu-Natal
Client Line 2: | Department of Transport
Contract No | ZNB01544/00000/00/HOD/INF/22/T
Contract Description | THE CONSTRUCTION OF THE WHITE MFOLOZI RIVER BRIDGE NO.3600 AND GRAVEL LINK ROAD D2047 FROM KM 7.318 TO KM 14.300 IN THE ZULULAND DISTRICT UNDER EMPANGENI REGION

## C1.2
Province of KwaZulu-Natal |  |  | Contract No. ZNB01544/00000/00/HOD/INF/22/T
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C1.2
THE CONSTRUCTION OF THE WHITE MFOLOZI RIVER BRIDGE NO.3600 AND GRAVEL LINK ROAD D2047 FROM KM 7.318 TO KM 14.300 IN THE ZULULAND DISTRICT UNDER EMPANGENI REGION
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C1.2 | GENERAL REQUIREMENTS AND PAYMENT
C1.2.1 | Environmental Management
C1.2.1.1 | Monitoring of compliance with and reporting on the EMP | month | 20
C1.2.1.2 | Dedicated environmental officer | month | 20
C1.2.2 | Programming and Reporting
C1.2.2.6 | Preparation and submission of all information and reports specified in the Contract Documentation | month | 20
C1.2.4 | Stakeholder liaison | month | 20
C1.2.5 | Safety
C1.2.5.1 | Health and safety plan | Lump Sum | 1
C1.2.5.2 | Implementation of health and safety plan | month | 20
C1.2.8 | Dayworks
C1.2.8.1 | Personnel
(a) | Unskilled labourer | hour | 750
(b) | Semi-skilled labourer | hour | 190
(c) | Skilled labourer | hour | 140
(d) | Gang leader | hour | 140
(e) | Foreman | hour | 150
C1.2.8.2 | Construction Equipment
(a) | Motor grader (112 kW) | hour | 70
(b) | Vibratory roller Bomag 212 or similar | hour | 70
(d) | Front end loader backhoe (60 kW) | hour | 70
(e) | Excavator (125 kW) | hour | 70
(f) | Compressor (450 cfm with hoses and tools) | hour | 70
(h) | Tpper Trucks:
| (i) 6 m³ capacity | hour | 70
(i) | Tractor loader backhoe 4 x 4 (55 kW) | hour | 70
(j) | Water truck 7000 litre | hour | 70
(k) | Bulldozer (125 kW) | hour | 70
C1.2 | TOTAL CARRIED FORWARD
Province of KwaZulu-Natal |  |  | Contract No. ZNB01544/00000/00/HOD/INF/22/T
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C1.2
THE CONSTRUCTION OF THE WHITE MFOLOZI RIVER BRIDGE NO.3600 AND GRAVEL LINK ROAD D2047 FROM KM 7.318 TO KM 14.300 IN THE ZULULAND DISTRICT UNDER EMPANGENI REGION
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
TOTAL BROUGHT FORWARD
(l) | Pedestrian roller (700 kg) | hour | 70
(m) | Water pump (75 mm diameter with 50 m hose) | hour | 70
(n) | Concrete Mixer (250l) Springbok | hour | 50
C1.2.8.3 | Vehicles (specify size)
(a) | Light delivery vehicle | km | 3000
(b) | Flatbed truck | km | 1000
(c) | Dump Truck | km | 40
(d) | Water Bowser 10 000 litre | km | 40
C1.2.8.4 | Materials
(a) | Procurement of materials | PC Sum | 1 | 250000 | 250000
(b) | Contractor's handling costs, profit and all other charges in respect of item C1.2.8.4(a) | % | 250000
PSC1.2.10 | Provision for a Community Liaision Officer | PC Sum | 1 | 235000 | 235000
PSC1.2.11 | Provision for Geotechnical Investigations throughout the construction duration. | Prov Sum | 1 | 200000 | 200000
PSC1.2.12 | Provision for diversion of the river | Prov Sum | 1 | 100000 | 100000
PSC1.2.13 | Provision of architectural finish to the bridge structure | Prov Sum | 1 | 2500000 | 2500000
C1.2 | TOTAL CARRIED FORWARD TO SUMMARY

## C1.3
Province of KwaZulu-Natal |  |  | Contract No. ZNB01544/00000/00/HOD/INF/22/T
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C1.3
THE CONSTRUCTION OF THE WHITE MFOLOZI RIVER BRIDGE NO.3600 AND GRAVEL LINK ROAD D2047 FROM KM 7.318 TO KM 14.300 IN THE ZULULAND DISTRICT UNDER EMPANGENI REGION
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C1.3 | CONTRACTOR'S SITE ESTABLISHMENT AND GENERAL OBLIGATIONS
C1.3.1 | The Contractor's general obligations
C1.3.1.1 | Fixed obligations | Lump Sum | 1
C1.3.1.3 | Time-related obligations | month | 20
C1.3.2 | Contract sign boards | m2 | 11.75
C1.3 | TOTAL CARRIED FORWARD TO SUMMARY

## C1.4
Province of KwaZulu-Natal |  |  | Contract No. ZNB01544/00000/00/HOD/INF/22/T
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C1.4
THE CONSTRUCTION OF THE WHITE MFOLOZI RIVER BRIDGE NO.3600 AND GRAVEL LINK ROAD D2047 FROM KM 7.318 TO KM 14.300 IN THE ZULULAND DISTRICT UNDER EMPANGENI REGION
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C1.4 | FACILITIES FOR THE ENGINEER
C1.4.1 | Site accommodation
C1.4.1.1 | Offices and conference room | m2 | 80
C1.4.1.3 | Open concrete working floors and verandas | m2 | 40
C1.4.1.5 | Store rooms inside the laboratory | m2 | 18
C1.4.1.6 | Car ports | No | 5
C1.4.1.7 | Ablution unit (2m x 1m x 1m) | No | 6
C1.4.1.9 | Kithcen unit (equipment as specified) | No | 2
C1.4.2.6 | Roller blinds, opaque type | m2 | 6
C1.4.2.7 | Venetian blinds | m2 | 6
C1.4.2.8 | Notice boards (2,0 m x 1,5 m softboard) | m2 | 10
C1.4.2.9 | White boards (2 m x 1 m) | m2 | 4
C1.4.3 | Items measured by number
C1.4.3.2 | Office chair | No | 8
C1.4.3.5 | Office desk with 3 drawers (at least one lockable drawer) | No | 2
C1.4.3.7 | Drawing table | No | 2
C1.4.3.8 | Conference table | No | 1
C1.4.3.10 | Filling cabinet | No | 2
C1.4.3.11 | General purpose steel cabinet with shelves | No | 2
C1.4.3.12 | Wall mounted pivot plan filling system | No | 1
C1.4.3.13 | 220/250 volt power outlet plug point | No | 4
C1.4.3.14 | 400/231 volt 2-phase power outlet plug point | No | 4
C1.4.3.15 | Single 1 500 mm, 58 watt fluorescent tube ceilling light | No | 8
C1.4.3.16 | Single 1 500 mm, 22 watt LED tube ceilling light | No | 4
C1.4.3.19 | Wash-hand basin | No | 10
C1.4.3.23 | Fire extinguisher 9,0 kg, dry powder type | No | 4
C1.4.3.24 | Air-conditioning unit | No | 3
C1.4.3.28 | UPS / Voltage stabiliser | No | 2
C1.4.4.1 | Cell phones costs, including pro-rate rentals, for calls made in connection with contract administration | PC Sum | 1 | 10000 | 10000
C1.4.4.2 | Handling cost and profit in respect of item C1.4.4.1 | % | 10000
C1.4 | TOTAL CARRIED FORWARD
Province of KwaZulu-Natal |  |  | Contract No. ZNB01544/00000/00/HOD/INF/22/T
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C1.4
THE CONSTRUCTION OF THE WHITE MFOLOZI RIVER BRIDGE NO.3600 AND GRAVEL LINK ROAD D2047 FROM KM 7.318 TO KM 14.300 IN THE ZULULAND DISTRICT UNDER EMPANGENI REGION
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
TOTAL BROUGHT FORWARD
C1.4.4.5 | The provision of internet conectivity and WIFI data for Engineer's site staff | PC Sum | 1 | 10000 | 10000
C1.4.4.6 | Handling cost and profit in respect of item C1.4.4.5 | % | 10000
C1.4.4.7 | The provision of paper and ink for a combination colour printer/copier/scanner | PC Sum | 1 | 5000 | 5000
C1.4.4.8 | Handling cost and profit in respect of item C1.4.4.7 | % | 5000
C1.4.4.11 | The provision of a complete 440/231 volt three phase electrical power installation, including all poles, insulators, wiring, switchboards, mains connection, meters, etc. | PC Sum | 1 | 10500 | 10500
C1.4.4.15 | The provision of all gas installations required at the site offices, laboratories and at the Engineer's staff accommodation (if required), including gas storage cylinders, tubing, regulators, gas burners and shut-off cocks | PC Sum | 1 | 10500 | 10500
C1.4.5 | Services at site offices, laboratories and site accommodation
C1.4.5.1 | Fixed costs | Lump Sum | 1
C1.4.5.2 | Running costs | month | 20
C1.4 | TOTAL CARRIED FORWARD

## C1.5
Province of KwaZulu-Natal |  |  | Contract No. ZNB01544/00000/00/HOD/INF/22/T
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C1.5
THE CONSTRUCTION OF THE WHITE MFOLOZI RIVER BRIDGE NO.3600 AND GRAVEL LINK ROAD D2047 FROM KM 7.318 TO KM 14.300 IN THE ZULULAND DISTRICT UNDER EMPANGENI REGION
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C1.5 | ACCOMMODATION OF TRAFFIC
1.5.5 | Maintenance of temporary deviations
1.5.5.9 | Grading of temporary deviations and existing roads used as detours | km | 7
C1.5.7 | Temporary traffic control facilities
C1.5.7.1 | Delineators including mounting bases and ballast:
| (a) Single sided, reversible left or right (TW401 / TW402) (800 mm x 200 mm) | No | 20
| (b) Double sided, reversible left or right (TW401 / TW402) (800 mm x 200 mm) | No | 20
C1.5.7.2 | Traffic cones, minimum height 750 mm | No | 40
C1.5.7.3 | Flagmen | man-shift | 840
C1.5.7.4 | Traffic Controllers | man-shift | 40
C1.5.7.5 | Provision of illuminated traffic signs
(c) | Illuminated road sign - R & TR series (1200 mm diameter) | No | 10
(d) | Illuminated road sign - TW series (triangular, 1500 mm sides) | No | 10
C1.5.7.8 | Traffic control stations | month | 5
C1.5.5.10 | Watering of temporary deviations and existing roads used as detours | kl | 1500
C1.5.5.11 | Other road maintenance work ordered by the Engineer | Prov Sum | 1 | 50000 | 50000
C1.5.5.12 | Handling cost, profit and all other charges in respect of item C1.5.5.12 | % | 50000
C1.5.11 | Provision of safety equipment for visitors
C1.5.11.1 | Provision of reflective safety vests for visitors | No | 10
C1.5.11.2 | Provision of hard hats for visitors | No | 10
PSC1.5.14 | Penalties:
(a) | Fixed penalty per occurrence | No | 5000 | 5000 | Rate only
(b) | Time-related penalty | h | 500 | 2500 | Rate only
C1.5 | TOTAL CARRIED FORWARD

## C1.6
Province of KwaZulu-Natal |  |  | Contract No. ZNB01544/00000/00/HOD/INF/22/T
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C1.6
THE CONSTRUCTION OF THE WHITE MFOLOZI RIVER BRIDGE NO.3600 AND GRAVEL LINK ROAD D2047 FROM KM 7.318 TO KM 14.300 IN THE ZULULAND DISTRICT UNDER EMPANGENI REGION
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C1.6 | CLEARING AND GRUBBING
C1.6.1 | Clearing
C1.6.1.1 | Clearing with machines and some hand labour where necessary | ha | 10.5
C1.6.1.2 | Clearing with hand labour only when labour enhanced work is specified | ha | 2.8
C1.6.2 | Grubbing
C1.6.2.1 | Grubbing with machines and some hand labour where necessary | ha | 10.5
C1.6.2.2 | Grubbing with hand labour only when labour enhanced work is specified or it is not practical to use a machine | ha | 2.8
C1.6.3.1 | Girth equal to or exceeding 1,0 m up to and including 2,0 m | No | 10
C1.6.7 | Re-clearing of previously cleared areas | ha | 1
C1.6 | TOTAL CARRIED FORWARD TO SUMMARY

## C1.7
Province of KwaZulu-Natal |  |  | Contract No. ZNB01544/00000/00/HOD/INF/22/T
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C1.7
THE CONSTRUCTION OF THE WHITE MFOLOZI RIVER BRIDGE NO.3600 AND GRAVEL LINK ROAD D2047 FROM KM 7.318 TO KM 14.300 IN THE ZULULAND DISTRICT UNDER EMPANGENI REGION
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C1.7 | LOADING AND HAULING
C1.7.2 | Hauling
C1.7.2.1 | Hauling material for use in the Works and off-loading it on the site of the Works:
(a) | Soil, gravel, crushed stone and pavement layer material | m3 - km | 79406.731
C1.7 | TOTAL CARRIED FORWARD TO SUMMARY

## C3.1
Province of KwaZulu-Natal |  |  | Contract No.
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C3.1
ESTABLISHMENT OF PANELS OF CONTRACTORS FOR THE ONSTRUCTION AND MAINTENAMNCE OF VARIOUS ROADS AND TRUCTURES IN KZN PROVINCE
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C3.1 | DRAINS
C3.1.1 | Excavation for open drains, catch drain and toe drain:
C3.1.1.1 | Excavating all material situated within the following depth ranges below the surface level using conventional methods :
(a) | 0m to 1.5m | m3 | 3340
(b) | exceeding 1.5m and up to 3.0m | m3 | 835
C3.1.1.2 | Extra over sub-item C3.1.1.1 for excavation in hard and boulder material , irrespective of depth | m3 | 626
C3.1.4 | Excavation and disposal of material for subsoil drainage systems
C3.1.4.1 | Excavating in all material situated within the following depth ranges below the surface :
(a) | 0m to 1.5m | m3 | 2059
(b) | Exceeding 1.5m and up to 3.0m | m3 | 468
C3.1.4.4 | Extra over sub-item C3.1.4.1 for excavation in hard and boulder material, irrespective of depth | m3 | 379
C3.1.5 | Impermeable backfilling to subsoil drainage system
C3.1.5.1 | Un-stabilised natural gravel obtained from approved sources on the site | m3 | 144
C3.1.7 | Natural pemeable material in subsoil drainage system ( approved crushed stone ):
C3.1.7.2 | Crushed stone obtained from commercial sources (state grade) | m3 | 500
C3.1.8 | Natural permeable material in subsoil drainage system (approved natural sand)
C3.1.8.2 | Natural sand from commercial sources ( state grade) | m3 | 150
C3.1.9 | Pipes in subsoil drainage systems :
C3.1.9.1 | U-PVC pipes and fittings , normal duty, complete with coupling ( 100mm internal dia. perforated or slotted synthetic-fibre fabric)) | m3 | 3432
C3.1.11. | Geotextile (grade C or similar) | m2 | 5242
C3.1.13 | Concrete outlet structures, manhole boxes, junction boxes and cleaning eyes for subsoil drainage systems:
C3.1.13.1 | Outlet structures (specify each type and drawing reference) | No | 20
C3.1.13.2 | Inspection boxes (specify each type and drawing reference.) | No | 20
C3.1.13.3 | Junction boxes (specify each type and drawing reference) | No | 20
C3.1 | TOTAL CARRIED FORWARD
Province of KwaZulu-Natal |  |  | Contract No.
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C3.1
ESTABLISHMENT OF PANELS OF CONTRACTORS FOR THE ONSTRUCTION AND MAINTENAMNCE OF VARIOUS ROADS AND TRUCTURES IN KZN PROVINCE
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
TOTAL BROUGHT FORWARD
C3.1.13.4 | Cleaning eyes ( specify each type and drawing reference) | No | 20
C3.1.14 | Caps for subsoil drain pipe :
C3.1.14.1 | Concrete caps | No | 20
C3.1 | TOTAL CARRIED FORWARD TO SUMMARY

## C4.1
Province of KwaZulu-Natal |  |  | Contract No. | ZNB01544/00000/00/HOD/INF/22/T
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C4.1.1
THE CONSTRUCTION OF THE WHITE MFOLOZI RIVER BRIDGE NO.3600 AND GRAVEL LINK ROAD D2047 FROM KM 7.318 TO KM 14.300 IN THE ZULULAND DISTRICT UNDER EMPANGENI REGION
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C4.1 | BORROW MATERIALS
C4.1.1 | Compiling and implementing M&U plans
C4.1.1.1 | For borrow pits | No | 1
C4.1.3 | Construction and maintenance of temporary haul and access roads
C4.1.3.1 | Temporary unsealed roads | km | 5
C4.1.4 | Removing of the overburden
C4.1.4.1 | In borrow pits | m3 | 1000
C4.1.5 | Excavating of materials in the borrow pits and quarries, material obtained from
C4.1.5.1 | Soft excavation | m3 | 5000
C4.1.5.2 | Boulder excavation class A | m3 | 500
C4.1.5.3 | Boulder excavation class B | m3 | 500
C4.1.15 | Shaping and finishing the borrow pit and quarry areas, and the stockpile sites
C4.1.15.1 | Shaping and finishing the borrow pit and quarry areas, and the stockpile sites:
(a) | Borrow pits | ha | 0.5
C4.1.15.2 | Finishing of the borrow pit and quarry areas, and the stockpile sites using labour enhanced methods of construction:
(a) | Borrow pits | ha | 0.5
C4.1 | TOTAL CARRIED FORWARD

## C4.2
Province of KwaZulu-Natal |  |  | Contract No. ZNB01544/00000/00/HOD/INF/22/T
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C4.2
THE CONSTRUCTION OF THE WHITE MFOLOZI RIVER BRIDGE NO.3600 AND GRAVEL LINK ROAD D2047 FROM KM 7.318 TO KM 14.300 IN THE ZULULAND DISTRICT UNDER EMPANGENI REGION
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C4.2 | CUT MATERIALS
C4.2.1 | Compiling and implementing M&U plans for cuttings
C4.2.1.1 | Cuttings exceeding 5 000 m³ up to 10 000 m³ | No | 1
C4.2.1.2 | Cuttings exceeding 10 000 m³ up to 20 000 m³ | No | 1
C4.2.1.3 | Cuttings exceeding 20 000 m³ up to 50 000 m³ | No | 1
C4.2.1.4 | Cuttings exceeding 50 000 m³ up to 100 000 m³ | No | 1
C4.2.3 | Excavating of materials in cuttings, material obtained from:
C4.2.3.1 | Soft excavation | m3 | 83136.6234
C4.2.3.2 | Boulder excavation class A | m3 | 12470.4935
C4.2.3.4 | Hard excavation (other than by blasting) | m3 | 3117.6234
C4.2.9 | Excavate material to spoil in sites designated by the Contractor, material obtained from
C4.2.9.1 | Soft excavation, overburden and unsuitable material | m3 | 529
C4.2.9.2 | Boulder excavation class A | m3 | 212
C4.2.9.3 | Boulder excavation class B | m3 | 212
C4.2.9.4 | Hard excavation (other than by blasting) | m3 | 1247
C4.2.12 | Finishing off fill slopes, medians and interchange areas
(a) | Cut slopes | m2 | 26447.4
C4.2 | TOTAL CARRIED FORWARD

## C4.4
Province of KwaZulu-Natal |  |  | Contract No. | ZNB01544/00000/00/HOD/INF/22/T
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C4.4
THE CONSTRUCTION OF THE WHITE MFOLOZI RIVER BRIDGE NO.3600 AND GRAVEL LINK ROAD D2047 FROM KM 7.318 TO KM 14.300 IN THE ZULULAND DISTRICT UNDER EMPANGENI REGION
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C4.4 | COMMERCIAL MATERIALS
C4.4.2 | Commercial materials identified by the Contractor from commercial, private or other non-commercial suppliers
C4.4.2.1 | Pavement layer material:
(j) | Type G7 material | m3 | 1000
(l) | Type G9 material | m3 | 1000
C4.4 | TOTAL CARRIED FORWARD

## C5.1
Province of KwaZulu-Natal |  |  | Contract No.
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C5.1
ESTABLISHMENT OF PANELS OF CONTRACTORS FOR THE ONSTRUCTION AND MAINTENAMNCE OF VARIOUS ROADS AND TRUCTURES IN KZN PROVINCE
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C5.1 | ROADBED
C5.1.1 | Roadbed construction and compaction
C5.1.1.1 | Compaction of insitu material to 90% of MDD | m3 | 5880
C5.1.4 | Removal of unsuitable material to spoil
C5.1.4.1 | In layer thicknesses of 200mm and less
(a) | Stable material | m3 | 6649
(b) | Unstable material | m3 | 4604
C5.1.5 | In-situ treatment of roadbed in hard material
C5.1.5.1 | In-situ treatment by ripping | m3 | 14211
C5.1 | TOTAL CARRIED FORWARD TO SUMMARY

## C5.2
Province of KwaZulu-Natal |  |  | Contract No. ZNB01544/00000/00/HOD/INF/22/T
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C5.2
THE CONSTRUCTION OF THE WHITE MFOLOZI RIVER BRIDGE NO.3600 AND GRAVEL LINK ROAD D2047 FROM KM 7.318 TO KM 14.300 IN THE ZULULAND DISTRICT UNDER EMPANGENI REGION
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C5.2 | FILL
C5.2.1 | Compiling and implementing M&U plans for fills
C5.2.1.1 | Fills exceeding 5 000 m³ up to 10 000 m³ | No | 1
C5.2.1.2 | Fills exceeding 10 000 m³ up to 20 000 m³ | No | 1
C5.2.1.3 | Fills exceeding 20 000 m³ up to 50 000 m³ | No | 1
C5.2.1.4 | Fills exceeding 50 000 m³ up to 100 000 m³ | No | 1
C5.2.2 | Fill construction
C5.2.2.1 | Normal fill material in compacted layer thicknesses of 200 mm and less:
(a) | Compacted to 90% MDD | m3 | 82875
C5.2.11 | Finishing off fill slopes, medians and interchange areas
C5.2.11.1 | Fill slopes | m2 | 25000
C5.2 | TOTAL CARRIED FORWARD TO SUMMARY

## C5.3
Province of KwaZulu-Natal |  |  | Contract No. ZNB01544/00000/00/HOD/INF/22/T
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C5.3
THE CONSTRUCTION OF THE WHITE MFOLOZI RIVER BRIDGE NO.3600 AND GRAVEL LINK ROAD D2047 FROM KM 7.318 TO KM 14.300 IN THE ZULULAND DISTRICT UNDER EMPANGENI REGION
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C5.3 | ROAD PAVEMENT LAYERS
C5.3.2.1 | Construction of layers using conventional construction methods:
(g) | Gravel wearing course layer ( layer thickness 150mm compacted to 95% of MDD, G7 Quality) | m3 | 9760
(k) | Upper subbase gravel layer (layer thickness 300mm compacted to 97% of MDD, G9 quality) | m3 | 10633
C5.3 | TOTAL CARRIED FORWARD TO SUMMARY

## C6.1
Province of KwaZulu-Natal |  |  | Contract No. ZNB01544/00000/00/HOD/INF/22/T
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C6.1
THE CONSTRUCTION OF THE WHITE MFOLOZI RIVER BRIDGE NO.3600 AND GRAVEL LINK ROAD D2047 FROM KM 7.318 TO KM 14.300 IN THE ZULULAND DISTRICT UNDER EMPANGENI REGION
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C6.1 | PAVER LAID CONCRETE LAYERS
C6.1.3 | Construction of continuously reinforced concrete pavement (Excluding texturing and curing)
C6.1.3.1 | Continuously reinforced concrete pavement (CRCP):
(b) | Labour enhanced construction (100mm) | m² | 2400
C6.1.4 | Texturing and curing the concrete pavement
C6.1.4.3 | Curing:
(b) | Labour enhanced construction | m² | 2400
C6.1.6 | Joints
C6.1.6.1 | Expansion joints complete (excluding dowels) | m | 1000
C6.1 | TOTAL CARRIED FORWARD TO SUMMARY

## C11.4
Province of KwaZulu-Natal |  |  | Contract No. ZNB01544/00000/00/HOD/INF/22/T
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C11.4
THE CONSTRUCTION OF THE WHITE MFOLOZI RIVER BRIDGE NO.3600 AND GRAVEL LINK ROAD D2047 FROM KM 7.318 TO KM 14.300 IN THE ZULULAND DISTRICT UNDER EMPANGENI REGION
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C11.4 | ROAD RESTRAINT SYSTEMS
C11.4.1 | Erecting of guardrails at 3,81 m spacing
C11.4.1.1 | Complete galvanized system compliant to SANS 1350:
(a) | On timber posts (Drawing reference) | m | 3271
C11.4.1.2 | Terminal sections for 3,81 guardrails comprising of:
(d) | End treatments where single guardrail sections are specified (SD 1102/2 on drawing no. SD1102/A) | No | 97
C11.4.4 | Extra over for horizontally curved guard rails
C11.4.4.1 | Extra over C11.4.1 for horizontally curved guard rails factory bent to a radius of less than 45 m | m | 491
C11.4.6 | Reflective plates
C11.4.6.1 | Steel plates | No | 909
C11.4.13 | Steel base plates for guardrail posts on structures | No | 909
C11.4.14 | Nailing of gang nail plates on top of timber guardrail posts | No | 909
C11.4 | TOTAL CARRIED FORWARD TO SUMMARY

## C13.1
Province of KwaZulu-Natal |  |  | Contract No. ZNB01544/00000/00/HOD/INF/22/T
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C13.1
THE CONSTRUCTION OF THE WHITE MFOLOZI RIVER BRIDGE NO.3600 AND GRAVEL LINK ROAD D2047 FROM KM 7.318 TO KM 14.300 IN THE ZULULAND DISTRICT UNDER EMPANGENI REGION
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C13.1 | FOUNDATIONS
C13.1.3 | Excavation:
C13.1.3.1 | Excavating soft material situated within the following successive depth ranges:
(a) | 0 m up to 1,5 m | m3 | 600
(b) | > 1,5 m and < 3,0 m | m3 | 900
(c) | Etc. in increments of 1,5 m | m3 | 1000
C13.1.3.2 | Extra over subitem C13.1.3.1 for excavation in hard material irrespective of depth | m3 | 150
C13.1.3.3 | Extra over subitem C13.1.3.1 for additional excavation required by the Engineer after excavation is complete | m3 | 150
C13.1.4 | Excavation by labour enhanced methods:
C13.1.4.1 | Excavate in soft material situated within the following successive depth ranges:
(a) | 0 m up to 1,5 m | m3 | 150
C13.1.6 | Access and drainage:
C13.1.6.1 | Access | Prov Sum | 1 | 1000000 | 1000000
C13.1.7 | Backfill to excavations utilising:
C13.1.7.1 | Material from excavation | m3 | 2350
C13.1.7.2 | Imported material | m3 | 2500
C13.1.9 | Fill within a restricted area (extra over item C5.2.2) | m3 | 4850
C13.1.14 | Foundation fill consisting of:
C13.1.14.4 | Mass concrete (15/19) | m3 | 300
C13.1.16 | Establishment on site for drilling of holes and grouting of rock fissures:
| (i) 45 mm diameter holes for Y25 Dowel Bars | Lump Sum | 1
C13.1.17 | Moving to and setting up equipment at each hole to be drilled for grouting:
| (i) Abutments | No | 215
| (ii) Piers | No | 460
C13.1.18 | Drilling of holes for grouting:
| (i) 45 mm diameter holes for Y25 Dowel Bars | m | 2025
C13.1.19 | Grouting (Superflow bedding grout or similar approved for dowel bar holes) | kg | 6375
C13.1 | TOTAL CARRIED FORWARD
Province of KwaZulu-Natal |  |  | Contract No. ZNB01544/00000/00/HOD/INF/22/T
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C13.1
THE CONSTRUCTION OF THE WHITE MFOLOZI RIVER BRIDGE NO.3600 AND GRAVEL LINK ROAD D2047 FROM KM 7.318 TO KM 14.300 IN THE ZULULAND DISTRICT UNDER EMPANGENI REGION
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
TOTAL BROUGHT FORWARD
C13.1.20 | Dowel bars:
C13.1.20.2 | Supply and installation of dowel bars (type, diameter, length, corrosion protection, together with type of grout, indicated)
(b) High tensile bars
| (i) Y25 mm diam dowel bars as detailed | kg | 7800
C13.1.22 | Foundation lining (0,25 m Um PVC damproof membrane under approadch slab), using labour enhanced methods | m2 | 120
C13.1 | TOTAL CARRIED FORWARD SUMMARY

## C13.2
Province of KwaZulu-Natal |  |  | Contract No. ZNB01544/00000/00/HOD/INF/22/T
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C13.2
THE CONSTRUCTION OF THE WHITE MFOLOZI RIVER BRIDGE NO.3600 AND GRAVEL LINK ROAD D2047 FROM KM 7.318 TO KM 14.300 IN THE ZULULAND DISTRICT UNDER EMPANGENI REGION
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C13.2 | FALSEWORK, FORMWORK AND CONCRETE FINISH
C13.2.2 | Vertical formwork to provide:
(a) Class F1 finish to:
| (i) Abutment bases | m2 | 100
| (ii) Hidden faces of abutment breast walls and screen walls | m2 | 840
| (iii) Abutment slab sides | m2 | 10
| (iv) Approach slab sides | m2 | 15
| (v) Pier footings | m2 | 200
| (b) Class F2 finish to: | m2
| (i) Exposed faces of abutment walls and screen walls | m2 | 550
| (ii) Piers column sides | m2 | 2300
| (iv) Piers column cutwaters (cercular ends) | m2 | 320
| (v) Vertical surfaces of deck sides | m2 | 350
| (vi) Vertical surfaces of diaphragms/deck ends | m2 | 150
C13.2.3 | Horizontal formwork to provide:
(b) Class F2 finish to:
| (i) Deck diaphragms soffit | m² | 25
| (iii) Abutment slab soffit | m² | 160
C13.2.4 | Inclined formwork to provide:
(b) Class F2 finish to:
| (ii) Soffit of abutment approach slab seat | m² | 30
| (ii) Deck inclined deck sides | m² | 200
C13.2.5 | Permanent formwork
C13.2.5.2 | Supply and install deck precast plank permanent shutters as per Engineers detail.(inclusive of all concrete works, formwork, reinforcing steel, and all concrete). | m2 | 1200
C13.2.6 | Formwork to form open joints
| (i) Between vertical and horizontal surfaces at the deck ends and the abutments | m2 | 20
C13.2 | TOTAL CARRIED FORWARD

## C13.3
Province of KwaZulu-Natal |  |  | Contract No. ZNB01544/00000/00/HOD/INF/22/T
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C13.3
THE CONSTRUCTION OF THE WHITE MFOLOZI RIVER BRIDGE NO.3600 AND GRAVEL LINK ROAD D2047 FROM KM 7.318 TO KM 14.300 IN THE ZULULAND DISTRICT UNDER EMPANGENI REGION
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C13.3 | STEEL REINFORCEMENT
C13.3.1 | Reinforcement for:
C13.3.1.1 | (a) Piers Bases
| (i) Mild-steel bars | t | 2
| (ii) High-yield-stress-steel bars | t | 50
(b) Pier columns
| (i) Mild-steel bars | t | 4
| (ii) High-yield-stress-steel bars | t | 160
(c) Abutment Bases
| (i) Mild-steel bars | t | 1
| (ii) High-yield-stress-steel bars | t | 50
(d) Abutment frontwalls and sidewalls
| (i) Mild-steel bars | t | 2
| (ii) High-yield-stress-steel bars | t | 90
(g) Deck diaphragms
| (i) Mild-steel bars | t | 1
| (ii) High-yield-stress-steel bars | t | 7
(h) Deck slabs
| (i) Mild-steel bars | t | 1
| (ii) High-yield-stress-steel bars | t | 50
(i) Parapets
| (i) Mild-steel bars | t | 1
| (ii) High-yield-stress-steel bars | t | 25
C13.3 | TOTAL CARRIED FORWARD TO SUMMARY

## C13.6
Province of KwaZulu-Natal |  |  | Contract No. ZNB01544/00000/00/HOD/INF/22/T
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C13.6
THE CONSTRUCTION OF THE WHITE MFOLOZI RIVER BRIDGE NO.3600 AND GRAVEL LINK ROAD D2047 FROM KM 7.318 TO KM 14.300 IN THE ZULULAND DISTRICT UNDER EMPANGENI REGION
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C13.6 | BEARINGS
C13.6.5 | Specialist proprietary bearings:
C13.6.5.1 | Prime cost sum allowed for purchasing and taking delivery of bearing | Prime Cost | 1 | 200000 | 200000
C13.6.5.2 | Percentage on prime cost sum for charges and profit | % | 200000
C13.6.6 | Installing the proprietary bearings
a) Rubber Bearings
| (i) 1103kN - 300x250x5(0)74mm | No | 175
C13.6 | TOTAL CARRIED FORWARD TO SUMMARY

## C13.7
Province of KwaZulu-Natal |  |  | Contract No. ZNB01544/00000/00/HOD/INF/22/T
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C13.7
THE CONSTRUCTION OF THE WHITE MFOLOZI RIVER BRIDGE NO.3600 AND GRAVEL LINK ROAD D2047 FROM KM 7.318 TO KM 14.300 IN THE ZULULAND DISTRICT UNDER EMPANGENI REGION
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C13.7 | JOINTS
C13.7.2 | Filled joints:
C13.7.2.1 | (a) 10mm wide movement joints in Concrete Parapets filled with Jointex | m2 | 55
| (b) 20mm wide movement joints in NJ Parapets filled with Jointex | m2 | 35
| (c) 40mm wide movement joints in Parapets filled with Jointex | m2 | 10
C13.7.4 | Sealing joints with:
C13.7.4.1 | (a) Approved silicon sealant for 10mm wide movement joints to Concrete Parapets | m | 220
| (b) Approved silicon sealant for 20mm wide movement joints F-Type NJ Parapets | m | 200
| (c) Approved silicon sealant for 40mm wide movement joints | m | 30
C13.7.9 | Specialist proprietary expansion joints:
C13.7.9.1 | Prime cost sum allowed for purchasing and taking delivery of expansion joints | Prime Cost | 1 | 350000 | 350000
C13.7.9.2 | Percentage on prime cost sum for charges and profit | % | 350000
C13.7.10 | Installation of specialist proprietary expansion joints:
C13.7.10.1 | Plug Type Joint as specified in Engineers Drawings | m | 150
(Drawing No : 3600/07)(Detail at top of Pier)
C13.7 | TOTAL CARRIED FORWARD

## C13.8
Province of KwaZulu-Natal |  |  | Contract No. ZNB01544/00000/00/HOD/INF/22/T
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C13.8
THE CONSTRUCTION OF THE WHITE MFOLOZI RIVER BRIDGE NO.3600 AND GRAVEL LINK ROAD D2047 FROM KM 7.318 TO KM 14.300 IN THE ZULULAND DISTRICT UNDER EMPANGENI REGION
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C13.8 | ANCILLARY STRUCTURAL ELEMENTS
C13.8.1 | Concrete barriers and parapets
C13.8.1.2 | Parapets
| (b) Concrete F Shape Parapet Type A (NJ parapets (1380x560) as detailed on Plan No. 3600/01 | m | 350
C13.8.2 | End blocks
| (b) End blocks to Concrete F-Shape Parapet Type A (1380mm high)(NJ parapets each 4000mm long by 560mm wide) | No | 6
C13.8.7 | Numbers for structures:
C13.8.7.3 | Numbers formed in concrete | No | 5
C13.8.10 | Drainage pipes and weep holes:
C13.8.10.1 | Drainage pipes:
| (i) 50mm dia uPVC drainage pipe to abutment seating beam as per Engineers detail. | No. | 10
| (ii) M65 Netlon drainage pipe behind abutments as detailed as per Engineers detail. | m | 120
| (iii) 200 mm DN3 Netlon drainage strips behind abutments and retaining walls | m | 150
| (iv) 110 mm diameter deck drain scupper pipes | No. | 54
C13.8.10.2 | Weep holes:
(b) | (i) uPVC 50mm dia. drainage pipes each 800mm long | No | 180
C13.8.12 | Synthetic-fibre filter fabric:
| (a) bidim grade A4 geofabric for abutments retaining walls (or approved equivalent) | m2 | 800
C13.8.13 | Concrete channels adjoining structural works (300 mm X 300 mm) | m³ | 5.4
C13.8 | TOTAL CARRIED FORWARD

## C20.1
Province of KwaZulu-Natal |  |  | Contract No.
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C20.1
ESTABLISHMENT OF PANELS OF CONTRACTORS FOR THE ONSTRUCTION AND MAINTENAMNCE OF VARIOUS ROADS AND TRUCTURES IN KZN PROVINCE
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C20.1 | TESTING OF MATERIALS AND JUDGEMENT OF WORKMANSHIP
C20.1.2 | Special tests requested by the engineer
C20.1.2.2 | Employer's contribution to other special tests
| (a) Requested by the Engineer | Prime Cost | 1 | 500000 | 500000
C13.8.2 | (i) Handling costs and profit in respect of item C20.1.2.2(a) | % | 500000
C20.1 | TOTAL CARRIED FORWARD

## Chapter E
Province of KwaZulu-Natal |  |  | Contract No. ZNB01544/00000/00/HOD/INF/22/T
Department of Transport
SCHEDULE E: EXPANDED PUBLIC WORKS PROGRAMME (EPWP) |  |  |  |  | CHAPTER E
THE CONSTRUCTION OF THE WHITE MFOLOZI RIVER BRIDGE NO.3600 AND GRAVEL LINK ROAD D2047 FROM KM 7.318 TO KM 14.300 IN THE ZULULAND DISTRICT UNDER EMPANGENI REGION
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
E | EXPANDED PUBLIC WORKS PROGRAMME (EPWP)
E6.01 | Provision of training venue facility, including the cost of transport the learners to and from this facility | Lump Sum | 1 | 250000 | 250000
E6.02 | Training of learners (including S3/S4 in-service) employed by the contractor or by the Targeted Enterprise subcontractors:
(a) | Generic Skills:
(a.i) | Training costs | Prov Sum | 1 | 150000 | 150000
(a.ii) | Handling costs and profit in respect of subitem E6.02(a)(i) above. | % | 150000
(b) | Entrepreneurial skills:
(b.i) | Training costs | Prov Sum | 1 | 150000 | 150000
(b.ii) | Handling costs and profit in respect of subitem E6.02(b)(i) above. | % | 150000
(c) | Construction skills:
(c.i) | Training costs | Prov Sum | 1 | 150000 | 150000
(c.ii) | Handling costs and profit in respect of subitem E6.02(c)(i) above. | % | 150000
(d) | Transportation and accommodation costs of selected learners only, while receiving off-site training:
(d.i) | Transportation and accommodation costs | Prov Sum | 1 | 150000 | 150000
(d.ii) | Handling costs and profit in respect of subitem E6.02(d)(i) above. | % | 150000
E6.03 | Payments associated with the NYS programme:
(a) | Employment of NYS workers | Prov Sum | 1 | 200000 | 200000
(b) | Provision of tools and apparel for the NYS workers | Prov Sum | 1 | 200000 | 200000
(c) | Handling cost and profit in respect of subitem E6.03(a) and (b) above | % | 400000
(d) | Training of NYS workers:
(d.i) | Provision of training for NYS workers | Prov Sum | 1 | 200000 | 200000
(d.ii) | Handling costs and profit in respect of subitem subitem E6.03(d)(i) above | % | 200000
(e) | Liaison with the Employer’s project manager and the training service provider:
(e.i) | Liaison conducted by the construction manager | hr | 300
(e.ii) | Liaison conducted by senior site foreman | hr | 200
(f) | EPWP Branding (refer to spec)
(i) | Provisional Sum for EPWP Branding | Prov Sum | 1 | 150000 | 150000
(ii) | Handling costs and profit in respect of sub-item F5.03(f)(i) above | % | 150000
E | TOTAL CARRIED FORWARD TO SUMMARY

## Chapter F
Province of KwaZulu-Natal |  |  | Contract No. ZNB01544/00000/00/HOD/INF/22/T
Department of Transport
SCHEDULE F: SMALL CONTRACTOR DEVELOPMENT |  |  |  |  | CHAPTER F
THE CONSTRUCTION OF THE WHITE MFOLOZI RIVER BRIDGE NO.3600 AND GRAVEL LINK ROAD D2047 FROM KM 7.318 TO KM 14.300 IN THE ZULULAND DISTRICT UNDER EMPANGENI REGION
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
F | SMALL CONTRACTOR DEVELOPMENT
F10.1 | Procurement of Targeted Enterprises:
(a) | Management and execution of Targeted Enterprise procurement process:
(a.i) | Procurement process for the appointment of CIDB contractor grading designation 1 Targeted Enterprise subcontractor (100 copies of the tender document required for each individual tender) | No | 6
(a.ii) | Procurement process for the appointment of CIDB contractor grading designation 2 Targeted Enterprise subcontractor (80 copies of the tender document required for each individual tender) | No | 2
(a.iii) | Procurement process for the appointment of CIDB contractor grading designation 3 Targeted Enterprise subcontractor (60 copies of the tender document required for each individual tender) | No | 1
(a.iv) | Procurement process for the appointment of CIDB contractor grading designation 4 Targeted Enterprise subcontractor (50 copies of the tender document required for each individual tender) | No | 4
F10.2 | Construction Works for Targeted Enterprise subcontractors:
(a) | Payments associated with the construction Works carried out by Targeted Enterprise subcontractors | Prov Sum | 1 | 15347911.476 | 15347911.476
(b) | Handling costs and profit in respect of subitem F10.02(a) | % | 15347911.476
(c) | Supply of materials and small construction equipment to assist Targeted Enterprise subcontractors | Prov Sum | 1 | 10231940.984 | 10231940.984
(d) | Handling costs and profit in respect of subitem F10.02(c) | % | 10231940.984
(e) | Management of the Targeted Enterprise subcontractors | Month | 18
(g) | Contractor's charge for the management of the Targeted Enterprise subcontractors appointed in term of Part G | Sum | 1
F | TOTAL CARRIED FORWARD
Province of KwaZulu-Natal |  |  | Contract No. ZNB01544/00000/00/HOD/INF/22/T
Department of Transport
SCHEDULE F: SMALL CONTRACTOR DEVELOPMENT |  |  |  |  | CHAPTER F
THE CONSTRUCTION OF THE WHITE MFOLOZI RIVER BRIDGE NO.3600 AND GRAVEL LINK ROAD D2047 FROM KM 7.318 TO KM 14.300 IN THE ZULULAND DISTRICT UNDER EMPANGENI REGION
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
TOTAL BROUGHT FORWARD
F10.03 | Training of Targeted Enterprise subcontractors:
(a) | Generic Skills
(a.i) | Training costs | Prov Sum | 1 | 150000 | 150000
(a.ii) | Handling costs and profit in respect of subitem F10.03(a)(i) | % | 150000
(b) | Entrepreneurial skills:
(b.i) | Training costs | Prov Sum | 1 | 150000 | 150000
(b.ii) | Handling costs and profit in respect of subitem F10.03(b)(i) | % | 150000
(c) | Construction skills:
(c.i) | Training costs | Prov Sum | 1 | 150000 | 150000
(c.ii) | Handling costs and profit in respect of subitem F10.03(c)(i) | % | 150000
(d) | Transportation and accommodation costs of selected learners only, while receiving off-site training:
(d.i) | Transportation and accommodation costs | Prov Sum | 1 | 150000 | 150000
(d.ii) | Handling costs and profit in respect of subitem F10.03(d)(i) | % | 150000
(e) | Training venue facility, including the cost of transporting the learners to and from the facility | Lump Sum | 1 | 150000 | 150000
F | TOTAL CARRIED FORWARD TO SUMMARY

## Summary
Province of KwaZulu-Natal | Contract No. ZNB01544/00000/00/HOD/INF/22/T
Department of Transport
THE CONSTRUCTION OF THE WHITE MFOLOZI RIVER BRIDGE NO.3600 AND GRAVEL LINK ROAD D2047 FROM KM 7.318 TO KM 14.300 IN THE ZULULAND DISTRICT UNDER EMPANGENI REGION
C2.3 SUMMARY OF BILL OF QUANTITIES
SCHEDULE | FROM PAGE | AMOUNT
TOTAL SCHEDULE A: ROADWORKS
TOTAL SCHEDULE E : EXPANDED PUBLIC WORKS PROGRAMME (EPWP)
TOTAL SCHEDULE F : SMALL CONTRACTOR DEVELOPMENT
SUBTOTAL 1
CONTINGENCIES (10% of Subtotal 1)
SUBTOTAL 2
CONTRACT PRICE ADJUSTMENT AND RISE & FALL (10% of Subtotal 2)
SUBTOTAL 3
VAT (15% of Subtotal 3)
TOTAL CARRIED FORWARD TO FORM OF OFFER