## P34-5 BoQ
PROJECT NAME: P34-5
CONTRACT NUMBER: ZNB01543/00000/00/HOD/INF/22T
ITEM No | DESCRIPTION | UNIT | LI | QUANTITY | RATE | AMOUNT
SCHEDULE A: ROADWORKS |  |  |  | SECTION 1.2
ITEM NO | DESCRIPTION | UNIT | LI | QUANTITY | RATE | AMOUNT
1.2 | GENERAL REQUIREMENTS AND PAYMENTS
C1.2.1 | Environmental Management
C1.2.1.1 | Monitoring of compliance with and reporting on the EMP | Month |  | 18 |  | 0
C1.2.1.2 | Dedicated Environmental Officer | Month |  | 18 |  | 0
C1.2.2 | Programming and Reporting
C1.2.2.3 | Submission of a scheme 2 initial Programme | L/Sum |  | 1 |  | 0
C1.2.2.4 | Submission of a scheme 2 Full Programme | L/Sum |  | 1 |  | 0
C1.2.2.5 | Reviewing and updating scheme 2 Programme every month | Month |  | 18 |  | 0
C1.2.2.6 | Preparation and submission of all information and reports specified in the Contract Document | Month |  | 18 |  | 0
C1.2.3 | Routine and maintenance of existing public roads within the site of the works or other public roads outside the site of work which are used as detour
C1.2.3.1 | Grass cutting | ha |  | 5 |  | 0
C1.2.3.2 | Drain Cleaning | km |  | 3 |  | 0
C1.2.3.3 | Cleaning out culverts | m³ |  | 100 |  | 0
C1.2.3.4 | Collection of rubbish/litter | km |  | 10 |  | 0
C1.2.3.11 | Other road maintenance work ordered by the engineer | P/Sum |  | 1 | 200000 | 200000
C1.2.3.12 | (b) Handling costs and profit in respect of subitem 1.2.3.11 | % |  | 200000 |  | 0
C1.2.4 | Stakeholder Liaison | Month |  | 18 |  | 0
C1.2.5 | Safety
C1.2.5.1 | Health & safety plan | P/sum |  | 1 |  | 0
C1.2.5.2 | Implementation of Health & safety plan | Month |  | 18 |  | 0
C1.2.6 | Work adjacent to properties
C1.2.6.1 | Survey of adjacent properties | No |  | 100 |  | 0
C1.2.6.2 | Preventive and/ or mitigation measures | Prov/Sum |  | 1 | 2500000 | 2500000
C1.2.6.3 | Handling costs and profit in respect of subitem 1.2.6.2 | % |  | 2500000 |  | 0
C1.2.8 | Dayworks
C1.2.8.1 | (a) Unskilled labourer | hr |  | 3000 |  | 0
| (b) Skilled labourer | hr |  | 1000 |  | 0
C1.2.8.2 | Construction equipment
| (a) Motor grader G40 | hr |  | 40 |  | 0
| (b) Vibratory Roller | hr |  | 40 |  | 0
| (d) Front end loader backhoe | hr |  | 1000 |  | 0
| (h) Other equipment (Pedestrain roller) | hr |  | 500 |  | 0
C1.2.8.3 | Vehicles
| (b) Flatbed truck 8t | km |  | 3600 |  | 0
| (c ) Dump truck | km |  | 600 |  | 0
C1.2.8.4 | Material
| a) Procurement of material | P/Sum |  | 1 | 300000 | 300000
| b) Handling cost & profit and all other charges in respect and all other charges in respect of item C1.2.8.4(a) | % |  | 300000 |  | 0
PSC 1.2.10 | Community Participation
| (a) Cost for community participation (PLC & CLO) | Prov/Sum |  | 1 | 550000 | 550000
| (b) Contractor's handling cost profit and all other charges in respect of item C1.2.8.4(a) | % |  | 550000 |  | 0
23850
1.2 | TOTAL CARRIED FORWARD |  |  |  |  | 3550000
| Total Carried Forward to Summary |  |  | Pages: | 1 | 0
ITEM No | DESCRIPTION | UNIT | LI | QUANTITY | RATE | AMOUNT
SCHEDULE A: ROADWORKS |  |  |  | SECTION 1.3
ITEM NO | DESCRIPTION | UNIT | LI | QUANTITY | RATE | AMOUNT
1.3 | CONTRACTOR'S ESTABLISHMENT ON SITE AND GENERAL OBLIGATIONS
C1.3.1 | The Contractor's general obligations:
C1.3.1.1 | (a) Fixed obligations | Sum |  | 1 |  | 0
C1.3.1.2 | (b) Value-related obligations | Sum |  | 1 |  | 0
C1.3.1.3 | (c) Time-related obligations | month |  | 18 |  | 0
C1.3.2 | Contract sign boards | m² |  | 11.75 |  | 0
1.3 | CONTRACTOR'S ESTABLISHMENT ON SITE AND GENERAL OBLIGATIONS |  |  |  |  | 0
SCHEDULE A: ROADWORKS |  |  |  | SECTION 1400
#REF!
ITEM NO | DESCRIPTION | UNIT | LI | QUANTITY | RATE | AMOUNT
1.4 | FACILITIES FOR THE ENGINEER
C1.4.1.1 | Offices and conference room: | m² |  | 110 |  | 0
C1.4.1.6 | Car ports | No |  | 6 |  | 0
C1.4.1.7 | Ablution unit | No |  | 4 |  | 0
C1.4.1.9 | Kitchen unit | No |  | 1 |  | 0
C1.4.2 | Items measured by area
C1.4.2.9 | White boards | m² |  | 8 |  | 0
C1.4.2.11 | Galvanised wire mesh fence 1.8m high with 2.0m x1.8m storeroom gate with padlock | m² |  | 1000 |  | 0
C1.4.3 | Items measured by numbers
C1.4.3.1 | Office swivel chairs | No. |  | 6 |  | 0
C1.4.3.2 | Office chair | No. |  | 20 |  | 0
C1.4.3.3 | Office desk with 3 drawers | No. |  | 6 |  | 0
C1.4.3.8 | Conference table (7.5m x2.0m) | No. |  | 2 |  | 0
C1.4.3.11 | General purpose steel cabinet with shelves lockup | No. |  | 2 |  | 0
C1.4.3.13 | 220/250 volt power outlet pug point | No. |  | 12 |  | 0
C1.4.3.15 | Single 1 500mm,58-watt fluorescent tube ceiling light | No. |  | 10 |  | 0
C1.4.3.23 | Fire extinguisher 9,0kg dry powder type | No. |  | 3 |  | 0
C1.4.3.24 | Air conditioning unit | No. |  | 6 |  | 0
C1.4.3.27 | Waste paper basket | No |  | 6 |  | 0
C1.4.3.28 | UPS/ Voltage stabiliser (2hrs rating) | No |  | 2 |  | 0
C1.4.3.29 | A3/A4 colour printer, copier, scanner | No |  | 1 |  | 0
C1.4.3.30 | A4 colour printer, copier , scanner | No |  | 1 |  | 0
1.4 | TOTAL CARRIED TO NEXT PAGE |  |  |  |  | 0
SCHEDULE A: ROADWORKS |  |  |  | SECTION 1.2
#REF!
ITEM NO | DESCRIPTION | UNIT | LI | QUANTITY | RATE | AMOUNT
| Brought forward |  |  |  |  | 0
C1.4.3.31 | Rain guage | No |  | 2 |  | 0
C1.4.3.32 | Maximum/minimum atmospheric temperature gauge | No |  | 2 |  | 0
C1.4.3.33 | Digital thermometer/ for surface temperature measurement | No |  | 2 |  | 0
C1.4.3.35 | 3 m aluminium straight edge complete with aluminium measuring wedges | No |  | 2 |  | 0
C1.4.3.36 | Measuring wheel | No |  | 1 |  | 0
C1.4.3.37 | First aid kit | No |  | 1 |  | 0
C1.4.4. | Prime-cost items & items paid for in a lump sum:
C1.4.4.5 | The provision of internet connectivity and wifi data for Engineer's site staff | PC sum |  | 1 | 100000 | 100000
C1.4.4.6 | Handling costs & profit in respect of subitem C1.4.4.5 | % |  | 100000 |  | 0
C1.4.4.7 | The provision of paper and ink for combination colour orinter/copier/scanner | P/Sum |  | 1 | 150000 | 150000
C1.4.4.8 | Handling costs & profit in respect of subitem C1.4.4.8 | % |  | 150000 |  | 0
C1.4.4.9 | The provision of complete 220/250-volt single phase electrical power installation, including all poles insulator wiring switchboards, main connection meter etc | P/Sum |  | 1 | 1000000 | 1000000
C1.4.4.10 | Handling costs & profit in respect of subitem C1.4.4.9 | % |  | 1000000 |  | 0
C1.4.5 | Services at site offices, laboratories and site accommodation
C1.4.5.1 | Fixed costs | L/Sum |  | 1 |  | 0
C1.4.5.2 | Running costs | Month |  | 18 |  | 0
C1.4.6 | Office Staff
C1.4.6.2 | Technical assistant sourced with the area | Month |  | 18 |  | 0
C1.4.7 | Site inspection transport
C1.4.7.1 | Provision of a bus, mini-bus or combi van for site inspection purpose (22-seater mini bus as instructed by engineer) | per day |  | 18 |  | 0
C1.4.7.2 | Travel on site as per item C1.4.7.1 | km |  | 2200 |  | 0
C1.4.8 | Site security measures for the Engineer's facilities
C1.4.8.1 | Supply and installation of all required security measures at the Engineer's site offices and laboratories
| (ii) Handling costs & profit in respect of subitem B14.08(e)(i) | L/Sum |  | 1 |  | 0
C1.4.8.2 | Provision of security guards/ watchmen and an armed response service at the Engineer's site offices and laboratories | month |  | 18 |  | 0
1.4 | FACILITIES FOR THE ENGINEER |  |  |  |  | 1250000
SCHEDULE A: ROADWORKS |  |  |  | SECTION C1.5
ITEM No | DESCRIPTION | UNIT | LI | QUANTITY | RATE | AMOUNT
C1.5 | ACCOMMODATION OF TRAFFIC
C1.5.2 | Accommodating traffic & maintain deviations | Month |  | 18 |  | 0
C1.5.3 | Liaison with traffic authorities | Month |  | 18 |  | 0
C1.5.5.10 | Watering of temporary deviations and existing roads used as detours | kl |  | 500 |  | 0
C1.5.5.11 | Other road mintainance work ordered by the engineer | P/Sum |  | 1 | 300000 | 300000
C1.5.5.12 | Handling cost, profit and all other charges in respect of item C1.5.5.11 | % |  | 300000
C1.5.7 | Temporary traffic control facilities
C1.5.7.1 | Delineators including mounting bases and ballast
| (a) Single sided | No | LI | 200 |  | 0
| b) Double sided | No | LI | 1000 |  | 0
| c) Traffic cones, minimum height 750mm | No | LI | 300 |  | 0
C1.5.7.3 | (a) Flagmen | man-day | LI | 2640 |  | 0
C1.5.7.4 | Traffic Controllers | man-day | LI | 2640 |  | 0
C1.5.7.5 | Provision of illuminated traffic signs
| a) Illuminated road sign R-TR 600mm | No |  | 12 |  | 0
| d)Illuminated road sign TW series | No |  | 20 |  | 0
| e) Mobile variable message sign with speed | No |  | 2 |  | 0
C1.5.7.6 | Maintainance of illuminated traffic signs
| a) Sign mounted flashing amber light (a pair of two light mounted on a separate back board | Month |  | 18 |  | 0
| b) Flashing LED illuminated arrow bard | Month |  | 18 |  | 0
| c) Illuminated road sign R-TR | Month |  | 18 |  | 0
| d) Illuminated road sign TW | Month |  | 18 |  | 0
C1.5.7.7 | Traffic calming devices
| a) 25mm highx100mm wide asphalt rumble | m |  | 200 |  | 0
| c) 150mm high x3m wide asphalt speed control buhumps | m |  | 284 |  | 0
C1.5.7.8 | Traffic control station | Month |  | 18 |  | 0
C1.5.7.9 | Cleaning of traffic control facilities | Month |  | 18 |  | 0
C1.5.8 | Traffic safety officer | Month |  | 18 |  | 0
C1.5.9 | Traffic safety vehicle | Month |  | 18 |  | 0
C1.5.11 | Provision of safety equipment for visitors
C1.5.11.1 | Provision of reflective safety vest | No |  | 10 |  | 0
C1.5.12 | Additional traffic accommodation facilities ordered by Engineer
C1.5.12.1 | Provision of additional traffic accommodation facilities ordered by Engineer | P/Sum |  | 1 | 250000 | 250000
C1.5.12.2 | Handling cost profit and all other charges in respect of item C1.5.12.1 | % |  | 250000 |  | 0
C1.5 | ACCOMMODATION OF TRAFFIC |  |  |  |  | 550000
SCHEDULE A: ROADWORKS |  |  |  | SECTION 1.6
#REF!
ITEM No | DESCRIPTION | UNIT | LI | QUANTITY | RATE | AMOUNT
1.6 | CLEARING AND GRUBBING
C1.6.1 | Clearing
C1.6.1.1 | Clearing with machines and some hand labour where necessary | ha |  | 6 |  | 0
C1.6.1.2 | Clearing with hand labour only when labour enhanced work is specified | ha | LI | 25 |  | 0
C1.6.3 | Cleaning of the silted pipes | m³ |  | 12000 |  | 0
C1.6 | CLEARING AND GRUBBING |  |  |  |  | 0
#REF! |  |  |  | #REF!
#REF!
SCHEDULE A: ROADWORKS |  |  |  | SECTION 1.7
#REF!
ITEM No | DESCRIPTION | UNIT | LI | QUANTITY | RATE | AMOUNT
1.7 | LOADING & HAULING
C1.7.1 | Loading
C1.7.2.1 | Material for use in the works and off loading it on site of the works
| a) Soil, gravel, crushed stone and pavement layer material | m³-km | LI | 689040 |  | 0
1.7 | LOADING & HAULING |  |  |  |  | 0
#REF! |  |  |  | #REF!
#REF!
SCHEDULE A: ROADWORKS |  |  |  | SECTION 2.1
#REF!
ITEM No | DESCRIPTION | UNIT | LI | QUANTITY | RATE | AMOUNT
2.1 | GENERAL REQUIREMENTS AND TRENCHING FOR SERVICES
C2.1.1 | Location, identification and relocation of existing services ( Irrigation sysstem at km18.760 and main waterline
C2.1.1.4 | Permanent service relocation or protection work by contractor | PC/Sum |  | 1 | 500000 | 500000
C2.1.1.5 | Handling cost and profit in respect of item C2.1.1.4 | % | LI | 500000 |  | 0
C2.1.2 | Existing services detention and verification
C2.1.2.3 | Survey to verify existing service positions | PC/Sum | LI | 1 | 35000 | 35000
C2.1.2.4 | Handling cost and profit in respect of item C2.1.2.3 | % | LI | 35000 |  | 0
C2.1.2.5 | Using hand excavation to locate, expose and verify services | m³ | LI | 2500 |  | 0
C2.1.3 | Obtaining construction or workpermit | L/Sum |  | 1 |  | 0
2.1 | GENERAL REQUIREMENTS AND TRENCHING FOR SERVICES |  |  |  |  | 535000
SCHEDULE A: ROADWORKS |  |  |  | SECTION C3.1
ITEM NO | DESCRIPTION | UNIT | LI | QUANTITY | RATE | AMOUNT
C3.1 | DRAINS
C3.1.1 | Excavation for open drains:
C3.1.1.1 | (a) Excavating all material situated within the following depth ranges below the surface level:
| (i) 0 m up to 1,5 m | m³ |  | 4110 |  | 0
C3.1 | DRAINS |  |  |  |  | 0
SCHEDULE A: ROADWORKS |  |  |  | SECTION C4.1
ITEM NO | DESCRIPTION | UNIT | LI | QUANTITY | RATE | AMOUNT
C4.1 | BORROW MATERIALS
C4.1.12 | Stockpiling the material
4.1.12.2 | Material directly from excavation | m³ |  | 6523 |  | 0
C4.1.15 | Shaping and finishing off the borrowpit, quarries and stockpile sites
| b) Stockpile sites | ha |  | 1 |  | 0
C4.1 | BORROW MATERIALS |  |  |  |  | 0
SCHEDULE A: ROADWORKS |  |  |  | SECTION C4.3
ITEM NO | DESCRIPTION | UNIT | LI | QUANTITY | RATE | AMOUNT
C4.3 | EXISTING ROAD MATERIALS
C4.3.5 | Providing the milling machine on the site
C4.3.5.2 | Large milling machine with cutting width exceeding 1.2m | No |  | 1 |  | 0
C4.3.5.6 | Milling and removal of existing asphaly layer with an average milling depth (Contractor take ownership)
C4.3.5.6.1 | Not exceeding 50mm | m³ |  | 6410 |  | 0
C4.3.5.6.2 | exceeding 50mm but not exceeding 100mm | m³ |  | 6410 |  | 0
C4.3.5.6.3 | Exceeding 100mm | m³ |  | 550 |  | 0
C4.3.8 | Widening of existing cuttings
C4.3.8.3 | Natural gravel material up to 300mm depth | m³ |  | 21537 |  | 0
C4.3.17 | Spoil of asphalt material
C4.3.17.1 | Spoil of asphalt material | m³ |  | 13370 |  | 0
C4.3.17.2 | Crushed stone ,macadam ,gravel and sand material | m³ |  | 11272 |  | 0
C4.3.19.1 | Paved blocks | m² |  | 5100 |  | 0
C4.3 | EXISTING ROAD MATERIALS |  |  |  |  | 0
SCHEDULE A: ROADWORKS |  |  |  | SECTION C4.4
#REF!
ITEM NO | DESCRIPTION | UNIT | LI | QUANTITY | RATE | AMOUNT
C4.4 | COMMERCIAL MATERIALS
C4.4.2 | Commercial material identified by the contractor from commercial, private, or other non commercial supplier commercial source
C4.4.2.1 | Pavement layer material
C4.3.6 | b) Type G2 Material | m³ |  | 20105 |  | 0
C4.4 | COMMERCIAL MATERIALS |  |  |  |  | 0
SCHEDULE A: ROADWORKS |  |  |  | SECTION C4.5
ITEM NO | DESCRIPTION | UNIT | LI | QUANTITY | RATE | AMOUNT
C4.5 | ALTERNATIVE MATERIALS
C4.5.1 | Additional material investigations
C4.5.1.1 | Cost of sampling and laboratory test | P/Sum |  | 1 | 500000 | 500000
C4.5.1.2 | Contractor's handling cost, profit in respect of item C4.5.1.1 | % |  | 500000 |  | 0
C4.5 | ALTERNATIVE MATERIALS |  |  |  |  | 500000
SCHEDULE A: ROADWORKS |  |  |  | SECTION C5.3
ITEM NO | DESCRIPTION | UNIT | LI | QUANTITY | RATE | AMOUNT
C5.3 | ROAD PAVEMENT LAYERS
C5.3.1 | Compiling and implementing M&U plans for the construction of all the pavement layers | No |  | 1 |  | 0
C5.3.2 | Construction of pavement layers
C5.3.2.1 | Construction of layers using conventional construction methods
| h) gravel wearing course layer( layer thickness of 150mm compacted to 95% | m³ |  | 1800 |  | 0
| 1) Upper subbase gravel layer( chemmical stabilize layer thickness of 200mm compacted to 97% | m³ |  | 20105 |  | 0
C5.3 | ROAD PAVEMENT LAYERS |  |  |  |  | 0
SCHEDULE A: ROADWORKS |  |  |  | SECTION C5.4
ITEM NO | DESCRIPTION | UNIT | LI | QUANTITY | RATE | AMOUNT
C5.4 | STABILIZATION
C5.4.2.1 | Chemical stabilization (200mm layer thickness subbase layer to be stabilised) | m³ |  | 20105 |  | 0
C5.4.5 | Cementitious stabilizing agents for pavement layers
C5.4.5.2 | Additional of cementitious stabilization agents (NPC cement for pavement layer and spreading the agent using bags and labour enhancement methods
| a) Cement (NPC | t |  | 0 |  | 0
| b) Lime | t | LI | 2688 |  | 0
C5.4.10 | Provision and application of water for curing | kl |  | 400 |  | 0
C5.4 | STABILIZATION |  |  |  |  | 0
SCHEDULE A: ROADWORKS |  |  |  | SECTION C8.1
ITEM NO | DESCRIPTION | UNIT | LI | QUANTITY | RATE | AMOUNT
C8.1 | PRIME COAT
C8.1.1 | Prime coat:
C8.1.1.2 | (c) MC-30 cut-back bitumen | l | LI | 85820 |  | 0
C8.1.2 | Aggregate for blinding
C8.1.2.2 | Crusher sand | m³ | LI | 245 |  | 0
C8.1.3 | Extra over item C8.1.1 for applying the prime coat in areas accessible only to hand held equipment | l | LI | 5000 |  | 0
C8.1 | PRIME COAT |  |  |  |  | 0
SCHEDULE A: ROADWORKS |  |  |  | SECTION C9.1
ITEM NO | DESCRIPTION | UNIT | LI | QUANTITY | RATE | AMOUNT
C9.1 | ASPHALT LAYER
9.1.1 | Asphalt mix designs
9.1.3 | Application of bond coat
9.1.3.1 | (b) Tack coat of 30% stable-grade emulsion | litre | LI | 61300 |  | 0
9.1.5 | Asphalt surfacing
9.1.5.2 | New construction
| (a) Stone skeletal mix-continuously graded as defined (40mm layer thickness 80/100 pen bitumen and 10mm stone | m² |  | 86420 |  | 0
9.1.7.1 | Placing and compacting asphalt in restricted area | m² | LI | 3500 |  | 0
9.1.8.2 | Surfacing ( (40mm layer thickness)
9.1.13 | Coring of asphalt | No | LI | 300 |  | 0
C9.1 | ASPHALT LAYER |  |  |  |  | 0
SCHEDULE A: ROADWORKS |  |  |  | SECTION 5900
ITEM NO | DESCRIPTION | UNIT | LI | QUANTITY | RATE | AMOUNT
C11.9 | FINISHING THE ROAD AND ROAD RESERVE AND TREATING OLD ROADS
C11.9.1 | Finishing the road and road reserve:
C11.9.1.1 | (b) Single carriageway road | km |  | 10 |  | 0
C11.9 | FINISHING THE ROAD AND ROAD RESERVE AND TREATING OLD ROADS |  |  |  |  | 0
SCHEDULE A: ROADWORKS |  |  |  | SECTION 5900
ITEM NO | DESCRIPTION | UNIT | LI | QUANTITY | RATE | AMOUNT
C20.1 | TESTING MATERIAL AND JUDGEMENT OF WORKMANSHIP
C20.1.2.2 | Employer's contribution to other special tests
| (a) Specify test | PC |  | 1 | 300000 | 300000
| b) Handling costs and profit in respect of item C20.1.2.2(a) | % |  | 300000 |  | 0
C20.1 | TESTING MATERIAL AND JUDGEMENT OF WORKMANSHIP |  |  |  |  | 300000
SCHEDULE F: EXPANDED PUBLIC WORKS PROGRAMME |  |  |  | SCHEDULE F
ITEM NO | DESCRIPTION | UNIT | LI | QUANTITY | RATE | AMOUNT
F1000 | EXPANDED PUBLIC WORKS PROGRAMME (EPWP)
F5.01 | Provision of the training venue facility including the cost of transporting the learners to and from this facilitity | PC Sum |  | 1 |  | 0
F5.02 | Training of learners employed by the main contractor or by the Targeted Enterprise subcontractors:
(a) Generic Skills.
| (i) Training costs | PC Sum |  | 1 | 250000 | 250000
| (ii) Handling costs and profit in respect of subitem G10.03(a)(i)above. | % |  | 250000 |  | 0
(b) Entrepreneurial skills:
| (i) Training costs | PC Sum |  | 1 | 250000 | 250000
| (ii) Handling costs and profit in respect of subitem G10.03(b)(i)above. | % |  | 250000 |  | 0
(c) Construction skills:
| (i) Training costs | PC Sum |  | 1 | 300000 | 300000
| (ii) Handling costs and profit in respect of subitem G10.03(c)(i)above. | % |  | 300000 |  | 0
F5.03 | Payments associated with the NYS programme only
| (a) Employment of NYS youth workers | Prov Sum |  | 1 | 950000 | 950000
| (b) Provision of tools and apparel for the NYS workers | Prov Sum |  | 1 | 60000 | 60000
| c) Handling cost and profit in respect of subitem F5.03 (a) and (b) above | % |  | 1010000 |  | 0
(d) Training of NYS youth workers
| (i) Provision of training for the NYS youth workers. | Prov Sum |  | 1 | 1660000 | 1660000
| (ii) Handling cost and profit in respect of subitem F5.03 (d)(i) above | % |  | 1660000 |  | 0
(e) Liaison with the Employer's project manager and the training service provider
| (i) Liaison conducted by the Construction manager | hr. |  | 300 |  | 0
| (ii) Liaison conducted by the senior site foreman | hr |  | 600 |  | 0
| (f) Branding of EPWP PPE refer to page C172 | Prov Sum |  | 1 | 35000 | 35000
| (i) Handling cost and profit in respect of subitem F5.03 (f) above | % |  | 35000 |  | 0
F1000 | EXPANDED PUBLIC WORKS PROGRAMME (EPWP) |  |  |  |  | 3505000
SCHEDULE G: CONTRACT PARTICIPATION GOALS |  |  |  | SCHEDULE G
ITEM No | DESCRIPTION | UNIT | LI | QUANTITY | RATE | AMOUNT
G1000 | CONTRACT PARTICIPATION GOALS
G10.01 | Procurement of Targeted Enterprise subcontractors as described in Part G
(a) Contractor's charge for the management and execution of the Targeted Enterprise procurement process:
| (i) Procurement process for totality of all tenders concluded for the appointment of CIDB contractor grading designation 1CE PE Targeted Enterprise subcontractors (1 x individual tenders prescribed, 100 copies of the tender doc required for each individual tender) | No. |  | 10 |  | 0
| (ii) Procurement process for the totality of all tenders concluded for the appointment of CIDB contractor grading designation 2CE PE Targeted Enterprise subcontractors (2 x individual tenders prescribed, 80 copies of the tender doc required for each individual tender) | No. |  | 6 |  | 0
| (iii) Procurement process for the totality of all tenders concluded for the appointment of CIDB contractor grading designation 3CE PE Targeted Enterprise subcontractors (3 x individual tenders prescribed, 60 copies of the tender doc required for each individual tender) | No. |  | 3 |  | 0
| (iv) Procurement process for the totality of all tenders concluded for the appointment of CIDB contractor grading designation 4CE PE Targeted Enterprise subcontractors (zero individual tenders prescribed, 50 copies of the tender doc required for each individual tender) | No. |  | 1 |  | 0
| (v) Procurement process for the totality of all tenders concluded for the appointment of CIDB contractor grading designation 5CE PE Targeted Enterprise subcontractors (zero individual tenders prescribed, 40 copies of the tender doc required for each individual tender) | No. |  | 1 |  | 0
| (vi) Procurement process for the totality of all tenders concluded for the appointment of CIDB contractor grading designation 6CE PE Targeted Enterprise subcontractors (zero individual tenders prescribed, 40 copies of the tender doc required for each individual tender) | No. |  | 1 |  | 0
G1000 | TOTAL CARRIED FORWARD TO SUMMARY |  |  |  |  | 0
SCHEDULE G: CONTRACT PARTICIPATION GOALS |  |  |  | SCHEDULE G
ITEM No | DESCRIPTION | UNIT | LI | QUANTITY | RATE | AMOUNT
Brought forward | [5 empty] | 0
G10.02 | Construction Works for Targeted Enterprises
| (a) Payments associated with the construction Works carried out by Targeted Enterprise subcontractors appointed in terms of Part G | P C Sum |  | 1 | 30772796.84 | 30772796.84
| (b) Handling costs and profit in respect of subitem G10.02(a) above | % |  | 30772796.84 |  | 0
| (c) Supply of materials and small plant to assist Targeted Enterprise subcontractors appointed in terms of Part G | P C Sum |  | 1 | 8797829.47 | 8797829.47
| (d) Handling costs and profit in respect of subitem G10.02(c) above | % |  | 8797829.47 |  | 0
| e) Contractor's management fee for managing emerging contractors under CPG | Sum |  | 1 |  | 0
G10.03 | Training of learners employed by the main contractor or by the Targeted Enterprise subcontractors:
(a) Generic Skills.
| (i) Training costs | Prov Sum |  | 1 | 350000 | 350000
| (ii) Handling costs and profit in respect of subitem G10.03(a)(i)above. | % |  | 350000 |  | 0
(b) Entrepreneurial skills:
| (i) Training costs | Prov Sum |  | 1 | 500000 | 500000
| (ii) Handling costs and profit in respect of subitem G10.03(b)(i)above. | % |  | 500000 |  | 0
(c) Construction skills:
| (i) Training costs | Prov Sum |  | 1 | 600000 | 600000
| (ii) Handling costs and profit in respect of subitem G10.03(c)(i)above. | % |  | 600000 |  | 0
| d) Transportation and accommodation costs of selected learners only while reciving off site training | Prov Sum |  | 1 | 125000 | 125000
| (ii) Handling costs and profit in respect of subitem G10.03(d)(i)above. | % |  | 125000 |  | 0
G1000 | CONTRACT PARTICIPATION GOALS |  |  |  |  | 41145626.31

## A
| #REF! |  | 6685000
#REF! |  |  |  | #REF!
#REF!
SCHEDULE A: ROADWORKS
SUMMARY OF SECTIONS
#REF!
SECTION | DESCRIPTION | FROM PAGE | AMOUNT
1.2 | GENERAL REQUIREMENTS AND PAYMENTS |  | 3550000
1.3 | CONTRACTOR'S ESTABLISHMENT ON SITE AND GENERAL OBLIGATIONS |  | 0
1.4 | FACILITIES FOR THE ENGINEER |  | 1250000
1.5 | ACCOMMODATION OF TRAFFIC |  | 550000
1.6 | CLEARING AND GRUBBING |  | 0
1.7 | LOADING & HAULING |  | 0
2.1 | GENERAL REQUIREMENTS AND TRENCHING FOR SERVICES |  | 535000
3.1 | DRAINS |  | 0
4.1 | BORROW MATERIALS |  | 0
4.2 | EXISTING ROAD MATERIALS |  | 0
4.4 | COMMERCIAL MATERIALS |  | 0
4.5 | ALTERNATIVE MATERIALS |  | 500000
5.3 | ROAD PAVEMENT LAYERS |  | 0
5.4 | STABILIZATION |  | 0
8.1 | PRIME COAT |  | 0
9.1 | ASPHALT LAYER |  | 0
11.9 | FINISHING THE ROAD AND ROAD RESERVE AND TREATING OLD ROADS |  | 0
20.1 | TESTING MATERIAL AND JUDGEMENT OF WORKMANSHIP |  | 300000
| TOTAL CARRIED FORWARD |  | 6685000 |  | 6685000
1002750

## Sch F
| Total Carried Forward to Summary |  |  |  |  | 3505000
ITEM No | DESCRIPTION | UNIT | LI | QUANTITY | RATE | AMOUNT
#REF! |  |  |  | #REF!
#REF!
SCHEDULE F: EXPANDED PUBLIC WORKS PROGRAMME |  |  |  | SCHEDULE F
#REF!
ITEM NO | DESCRIPTION | UNIT | LI | QUANTITY | RATE | AMOUNT
F1000 | EXPANDED PUBLIC WORKS PROGRAMME (EPWP)
F5.01 | Provision of the training venue facility including the cost of transporting the learners to and from this facilitity | PC Sum |  | 1 |  | 0
F5.02 | Training of learners employed by the main contractor or by the Targeted Enterprise subcontractors:
(a) Generic Skills.
| (i) Training costs | PC Sum |  | 1 | 250000 | 250000
| (ii) Handling costs and profit in respect of subitem G10.03(a)(i)above. | % |  | 250000 |  | 0
(b) Entrepreneurial skills:
| (i) Training costs | PC Sum |  | 1 | 250000 | 250000
| (ii) Handling costs and profit in respect of subitem G10.03(b)(i)above. | % |  | 250000 |  | 0
(c) Construction skills:
| (i) Training costs | PC Sum |  | 1 | 300000 | 300000
| (ii) Handling costs and profit in respect of subitem G10.03(c)(i)above. | % |  | 300000 |  | 0
F5.03 | Payments associated with the NYS programme only
| (a) Employment of NYS youth workers | Prov Sum |  | 1 | 950000 | 950000
| (b) Provision of tools and apparel for the NYS workers | Prov Sum |  | 1 | 60000 | 60000
| c) Handling cost and profit in respect of subitem F5.03 (a) and (b) above | % |  | 1010000 |  | 0
(d) Training of NYS youth workers
| (i) Provision of training for the NYS youth workers. | Prov Sum |  | 1 | 1660000 | 1660000
| (ii) Handling cost and profit in respect of subitem F5.03 (d)(i) above | % |  | 1660000 |  | 0
(e) Liaison with the Employer's project manager and the training service provider
| (i) Liaison conducted by the Construction manager | hr. |  | 300 |  | 0
| (ii) Liaison conducted by the senior site foreman | hr |  | 600 |  | 0
| (f) Branding of EPWP PPE refer to page C172 | Prov Sum |  | 1 | 35000 | 35000
| (i) Handling cost and profit in respect of subitem F5.03 (f) above | % |  | 35000 |  | 0
F1000 | EXPANDED PUBLIC WORKS PROGRAMME (EPWP) |  |  |  |  | 3505000

## Sch G
| Total Carried Forward to Summary |  |  |  |  | 41145626.31 |  | 0 |  |  |  | Rate per document: | 100
ITEM No | DESCRIPTION | UNIT | LI | QUANTITY | RATE | AMOUNT | LI Rate | LI Amount | LI Calculation | LI Comments
#REF! |  |  |  | #REF!
#REF!
SCHEDULE G: CONTRACT PARTICIPATION GOALS |  |  |  | SCHEDULE G
#REF!
ITEM No | DESCRIPTION | UNIT | LI | QUANTITY | RATE | AMOUNT | LI Rate | LI Amount | LI Calculation
G1000 | CONTRACT PARTICIPATION GOALS
G10.01 | Procurement of Targeted Enterprise subcontractors as described in Part G
(a) Contractor's charge for the management and execution of the Targeted Enterprise procurement process:
| (i) Procurement process for totality of all tenders concluded for the appointment of CIDB contractor grading designation 1CE PE Targeted Enterprise subcontractors (1 x individual tenders prescribed, 100 copies of the tender doc required for each individual tender) | No. |  | 10 |  | 0
| (ii) Procurement process for the totality of all tenders concluded for the appointment of CIDB contractor grading designation 2CE PE Targeted Enterprise subcontractors (2 x individual tenders prescribed, 80 copies of the tender doc required for each individual tender) | No. |  | 6 |  | 0
| (iii) Procurement process for the totality of all tenders concluded for the appointment of CIDB contractor grading designation 3CE PE Targeted Enterprise subcontractors (3 x individual tenders prescribed, 60 copies of the tender doc required for each individual tender) | No. |  | 3 |  | 0
| (iv) Procurement process for the totality of all tenders concluded for the appointment of CIDB contractor grading designation 4CE PE Targeted Enterprise subcontractors (zero individual tenders prescribed, 50 copies of the tender doc required for each individual tender) | No. |  | 1 |  | 0
| (v) Procurement process for the totality of all tenders concluded for the appointment of CIDB contractor grading designation 5CE PE Targeted Enterprise subcontractors (zero individual tenders prescribed, 40 copies of the tender doc required for each individual tender) | No. |  | 1 |  | 0
| (vi) Procurement process for the totality of all tenders concluded for the appointment of CIDB contractor grading designation 6CE PE Targeted Enterprise subcontractors (zero individual tenders prescribed, 40 copies of the tender doc required for each individual tender) | No. |  | 1 |  | 0
G1000 | TOTAL CARRIED FORWARD |  |  |  |  | 0 |  | 0
#REF! |  |  |  | #REF!
#REF!
SCHEDULE G: CONTRACT PARTICIPATION GOALS |  |  |  | SCHEDULE G
#REF! | [13 empty] | 524377.8435
ITEM No | DESCRIPTION | UNIT | LI | QUANTITY | RATE | AMOUNT | LI Rate | LI Amount | [5 empty] | 476707.1304
Brought forward | [5 empty] | 0 |  | 0 | [5 empty] | 433370.1186
G10.02 | Construction Works for Targeted Enterprises
| (a) Payments associated with the construction Works carried out by Targeted Enterprise subcontractors appointed in terms of Part G | P C Sum |  | 1 | 30772796.84 | 30772796.84
| (b) Handling costs and profit in respect of subitem G10.02(a) above | % |  | 30772796.84 |  | 0 |  |  |  |  | 39570626.31
| (c) Supply of materials and small plant to assist Targeted Enterprise subcontractors appointed in terms of Part G | P C Sum |  | 1 | 8797829.47 | 8797829.47
| (d) Handling costs and profit in respect of subitem G10.02(c) above | % |  | 8797829.47 |  | 0
| e) Contractor's management fee for managing emerging contractors under CPG | Sum |  | 1 |  | 0
G10.03 | Training of learners employed by the main contractor or by the Targeted Enterprise subcontractors:
(a) Generic Skills.
| (i) Training costs | Prov Sum |  | 1 | 350000 | 350000
| (ii) Handling costs and profit in respect of subitem G10.03(a)(i)above. | % |  | 350000 |  | 0
(b) Entrepreneurial skills:
| (i) Training costs | Prov Sum |  | 1 | 500000 | 500000
| (ii) Handling costs and profit in respect of subitem G10.03(b)(i)above. | % |  | 500000 |  | 0
(c) Construction skills:
| (i) Training costs | Prov Sum |  | 1 | 600000 | 600000
| (ii) Handling costs and profit in respect of subitem G10.03(c)(i)above. | % |  | 600000 |  | 0
| d) Transportation and accommodation costs of selected learners only while reciving off site training | Prov Sum |  | 1 | 125000 | 125000
| (ii) Handling costs and profit in respect of subitem G10.03(d)(i)above. | % |  | 125000 |  | 0
G1000 | TOTAL CARRIED FORWARD |  |  |  |  | 41145626.31 |  | 0

## Summary
#REF! |  |  |  | #REF!
#REF!
C2.3 SUMMARY OF BILL OF QUANTITIES
| DESCRIPTION | FROM PAGE | AMOUNT
TOTAL SCHEDULE A: ROADWORKS |  |  | 6685000
TOTAL SCHEDULE D: DAYWORKS |  |  | 0
TOTAL SCHEDULE F: EXPANDED PUBLIC WORKS PROGRAMME |  |  | 3505000
TOTAL SCHEDULE G: CONTRACT PARTICIPATION GOALS |  |  | 41145626.31
Subtotal 1 |  |  | 51335626.31
CONTINGENCIES |  |  | 5133562.631
Subtotal 2 |  |  | 56469188.941
CONTRACT PRICE ADJUSTMENT (0% of Subtotal 2) |  |  | 5646918.8941
Subtotal 3 |  |  | 62116107.8351
VAT (15% of Subtotal 3) |  |  | 9317416.18
TOTAL CARRIED FORWARD TO FORM OF OFFER |  |  | 71433524.0151
Signed on behalf of the Tenderer: ……………………………………………………. (Signature) Date: ………………………………………………….. Tenderer’s Name: ………………………………………………………………. (Company Name)
102614069.8451
DISCLAIMER
Kindly note that the responsibility lies with Tenderer to check the tender document and the tender addenda (if issued) to verify that all the information is correct and all changes have been incorporated as no claims will be entertained in this regard afterwards. Accordingly, we confirm that the hard copies of the original tender document and the tender addenda are to be regarded to contain the correct items and quantities. | [5 empty] | 7