## Information
Client Line 1: | Province of KwaZulu-Natal
Client Line 2: | Department of Transport
Contract No | ZNB01871/00000/00/PMC/INF/23/T
Contract Description | THE UPGRADE OF MSUNDUZI RIVER BRIDGE (GRIMTHORPE AVE TO BISHOPSTOWE) DISTRICT ROAD D669 KM 2.54

## C1.2
Province of KwaZulu-Natal |  |  | Contract No. ZNB01871/00000/00/PMC/INF/23/T
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C1.2
THE UPGRADE OF MSUNDUZI RIVER BRIDGE (GRIMTHORPE AVE TO BISHOPSTOWE) DISTRICT ROAD D669 KM 2.54
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C1.2 | GENERAL REQUIREMENTS AND PAYMENT
C1.2.1 | Environmental Management
C1.2.1.1 | Monitoring of compliance with and reporting on the EMP | month | 18 |  | 0
C1.2.1.2 | Dedicated environmental officer (if specified in the Contract Documentation) | month | 18 |  | 0
C1.2.2 | Programming and Reporting
C1.2.2.3 | Submission of a Scheme 2 Initial Programme | Lump Sum | 1 |  | 0
C1.2.2.4 | Submission of a Scheme 2 Final Programme | month | 18 |  | 0
C1.2.2.5 | Reviewing and updating a Scheme 2 Programme | month | 18 |  | 0
C1.2.2.6 | Preparation and submission of all information and reports specified in the Contract Documentation | month | 18 |  | 0
C1.2.4 | Stakeholder liaison | month | 18 |  | 0
C1.2.5 | Safety
C1.2.5.1 | Health and safety plan | Lump Sum | 1 |  | 0
C1.2.5.2 | Implementation of health and safety plan | month | 18 |  | 0
C1.2.6 | Work adjacent to properties
C1.2.6.1 | Survey of adjacent properties | No | 7 |  | 0
C1.2.6.2 | Preventive and/or mitigation measures | Prov Sum | 20000 | 1 | 20000
C1.2.6.3 | Handling cost, profit and all other charges in respect of item C1.2.6.2 | % | 20000 |  | 0
C1.2 | TOTAL CARRIED FORWARD |  |  |  | 20000
Province of KwaZulu-Natal |  |  | Contract No. ZNB01871/00000/00/PMC/INF/23/T
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C1.2
THE UPGRADE OF MSUNDUZI RIVER BRIDGE (GRIMTHORPE AVE TO BISHOPSTOWE) DISTRICT ROAD D669 KM 2.54
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
| TOTAL BROUGHT FORWARD |  |  |  | 20000
C1.2.8 | Dayworks
C1.2.8.1 | Personnel
(a) | Unskilled labourer | hour | 40 |  | 0
(b) | Semi-skilled labourer | hour | 30 |  | 0
(c) | Skilled labourer | hour | 10 |  | 0
(d) | Gang leader | hour | 10 |  | 0
(e) | Foreman | hour | 10 |  | 0
(f) | Skilled Artisan | hour | 30 |  | 0
C1.2.8.2 | Construction Equipment (specify size and/or model number)
(a) | Motor grader | hour | 15 |  | 0
(b) | Vibratory roller | hour | 15 |  | 0
(c) | Pneumatic roller | hour | 15 |  | 0
(d) | Front end loader backhoe | hour | 15 |  | 0
(e) | Excavator | hour | 15 |  | 0
(f) | Compressor | hour | 50 |  | 0
(h) | Generators, alternators or welding sets | hour | 20 |  | 0
(i) | Concrete mixer | hour | 50 |  | 0
C1.2.8.3 | Vehicles (specify size)
(a) | Light delivery vehicle | km | 1000 |  | 0
(b) | Flatbed truck | km | 1000 |  | 0
(c) | Dump Truck | km | 1000 |  | 0
C1.2.8.4 | Materials
(a) | Procurement of materials | Prov Sum | 50000 | 1 | 50000
(b) | Contractor's handling costs, profit and all other charges in respect of item C1.2.8.4(a) | % | 50000 |  | 0
C1.2.9 | Disposal of non-usable assets
C1.2.9.2 | Disposal of non-usable assets not identified at time of tender | Prov Sum | 10000 | 1 | 10000
C1.2.9.3 | Handling cost, profit and all other charges in respect of item C1.2.9.2 | % | 10000 |  | 0
C1.2 | TOTAL CARRIED TO SUMMARY |  |  |  | 80000

## C1.3
Province of KwaZulu-Natal |  |  | Contract No. ZNB01871/00000/00/PMC/INF/23/T
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C1.3
THE UPGRADE OF MSUNDUZI RIVER BRIDGE (GRIMTHORPE AVE TO BISHOPSTOWE) DISTRICT ROAD D669 KM 2.54
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C1.3 | CONTRACTOR'S SITE ESTABLISHMENT AND GENERAL OBLIGATIONS
C1.3.1 | The Contractor's general obligations
C1.3.1.1 | Fixed obligations | Lump Sum | 1 |  | 0
C1.3.1.3 | Time-related obligations | month | 18 |  | 0
C1.3.2 | Contract sign boards | m2 | 7 |  | 0
C1.3 | TOTAL CARRIED FORWARD TO SUMMARY |  |  |  | 0

## C1.4
Province of KwaZulu-Natal |  |  | Contract No. ZNB01871/00000/00/PMC/INF/23/T
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C1.4
THE UPGRADE OF MSUNDUZI RIVER BRIDGE (GRIMTHORPE AVE TO BISHOPSTOWE) DISTRICT ROAD D669 KM 2.54
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C1.4 | FACILITIES FOR THE ENGINEER
C1.4.1 | Site accommodation
C1.4.1.1 | Offices and conference room | m2 | 35 |  | 0
C1.4.1.6 | Car ports | No | 2 |  | 0
C1.4.1.7 | Ablution unit (equipment as specified) | No | 4 |  | 0
C1.4.1.9 | Kitchen unit (including stove, refrigerator, dining table, chairs, concrete working table, cupboard, sink, refuse-bin, taps, hot and cold water supply, electricity plug points, electrical light fittings, burglar proofing, washing lines and 100mm thick open concrete floor slab) | No | 1 |  | 0
C1.4.2 | Items measured by area
C1.4.2.9 | White boards | m2 | 10 |  | 0
C1.4.3 | Items measured by number
C1.4.3.1 | Office swivel chair | No | 3 |  | 0
C1.4.3.2 | Office chair | No | 6 |  | 0
C1.4.3.3 | Draughtsman's stool | No | 1 |  | 0
C1.4.3.5 | Office desk with 3 drawers (at least one lockable drawer) | No | 3 |  | 0
C1.4.3.7 | Drawing table | No | 1 |  | 0
C1.4.3.8 | Conference table | No | 1 |  | 0
C1.4.3.10 | Filling cabinet | No | 2 |  | 0
C1.4.3.11 | General purpose steel cabinet with shelves | No | 2 |  | 0
C1.4.3.12 | Wall mounted pivot plan filling system | No | 1 |  | 0
C1.4.3.13 | 220/250 volt power outlet plug point | No | 10 |  | 0
C1.4.3.14 | 400/231 volt 3-phase power outlet plug point | No | 4 |  | 0
C1.4.3.15 | Single 1 500 mm, 58 watt fluorescent tube ceilling light | No | 10 |  | 0
C1.4.3.16 | Single 1 500 mm, 22 watt LED tube ceilling light | No | 10 |  | 0
C1.4.3.17 | 11 watt compact fluorescent bulb ceiling light | No | 10 |  | 0
C1.4.3.18 | 7 watt LED bulb ceiling light | No | 10 |  | 0
C1.4.3.23 | Fire extinguisher 9,0 kg, dry powder type | No | 5 |  | 0
C1.4.3.24 | Air-conditioning unit | No | 3 |  | 0
C1.4 | TOTAL CARRIED FORWARD |  |  |  | 0
Province of KwaZulu-Natal |  |  | Contract No. ZNB01871/00000/00/PMC/INF/23/T
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C1.4
THE UPGRADE OF MSUNDUZI RIVER BRIDGE (GRIMTHORPE AVE TO BISHOPSTOWE) DISTRICT ROAD D669 KM 2.54
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
| TOTAL BROUGHT FORWARD |  |  |  | 0
C1.4.3.27 | Waste paper basket | No | 3 |  | 0
C1.4.3.29 | A3 / A4 colour printer, copier, scanner | No | 1 |  | 0
C1.4.3.31 | Rain gauge | No | 1 |  | 0
C1.4.3.32 | Minimum / maximum atmospheric temperature guage | No | 1 |  | 0
C1.4.3.35 | 3,0 m aluminium straight edge complete with two measuring wedges | No | 1 |  | 0
C1.4.3.36 | Measuring wheel | No | 1 |  | 0
C1.4.3.37 | First aid kit | No | 1 |  | 0
C1.4.4 | Prime cost items
C1.4.4.1 | Cell phones costs, including pro-rate rentals, for calls made in connection with contract administration | PC Sum | 80000 | 1 | 80000
C1.4.4.2 | Handling cost and profit in respect of item C1.4.4.1 | % | 80000 |  | 0
C1.4.4.5 | The provision of internet conectivity and WIFI data for Engineer's site staff | PC Sum | 20000 | 1 | 20000
C1.4.4.6 | Handling cost and profit in respect of item C1.4.4.5 | % | 20000 |  | 0
C1.4.4.7 | The provision of paper and ink for a combination colour printer/copier/scanner | PC Sum | 10000 | 1 | 10000
C1.4.4.8 | Handling cost and profit in respect of item C1.4.4.7 | % | 10000 |  | 0
C1.4.4.9 | The provision of a complete 220/250 volt single phase electrical power installation, including all poles, insulators, wiring, switchboards, mains connection, meters, etc. | PC Sum | 100000 | 1 | 100000
C1.4.4.10 | Handling cost and profit in respect of item C1.4.4.9 | % | 100000 |  | 0
C1.4.5 | Services at site offices, laboratories and site accommodation
C1.4.5.1 | Fixed costs | Lump Sum | 1 |  | 0
C1.4.5.2 | Running costs | month | 18 |  | 0
C1.4.8 | Site security measures for the Engineer's facilities
C1.4.8.1 | Supply and installation of all required security measures at the Engineer's site offices and laboratories | Lump Sum | 1 |  | 0
C1.4.8.2 | Provision of security gaurds / watchmen and an armed response service at the Engineer's site offices and laboratories | month | 18 |  | 0
C1.4 | TOTAL CARRIED FORWARD TO SUMMARY |  |  |  | 210000
made provision for lab

## C1.5
Province of KwaZulu-Natal |  |  | Contract No. ZNB01871/00000/00/PMC/INF/23/T
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C1.5
THE UPGRADE OF MSUNDUZI RIVER BRIDGE (GRIMTHORPE AVE TO BISHOPSTOWE) DISTRICT ROAD D669 KM 2.54
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C1.5 | ACCOMMODATION OF TRAFFIC
C1.5.1 | Accommodation of pedestrian and non-motorised traffic
C1.5.2 | Accommodation of vehicular traffic | month | 18 |  | 0
C1.5.3 | Liaison with traffic authorities | month | 18 |  | 0
C1.5.4 | Construction of temporary deviations
| The applicable payment items required for the construction of temporary deviations shall be taken from the relevant chapters and sections in Chapter 1, 3, 5, 9 and 10 and inserted into the Pricing Schedule here. Each payment item for the construction of temporary deviations shall be preceded by the main payment item number C1.5.4 / followed by the payment number for the applicable payment item | Unit must relate to relevant pay item from the relevant chapters and sections
C1.5.4 / C1.6.1.1 | Clearing with machines and some hand labour where necessary | ha | 0.166 |  | 0
C1.5.4 / C1.6.2.1 | Clearing with hand labour only when labour enhanced work is specified | ha | 0.1 |  | 0
C1.5.4 / C1.7.2.1 | Hauling material for use in the Works and off-loading it on the site of the Works:
(a) | Soil, gravel, crushed stone and pavement layer material | m3 - km | 248 |  | 0
(b) | Boulders and hard material | m3 - km | 28 |  | 0
C1.5.4 / C1.7.2.2 | Hauling material to spoil and off-loading it at a designated spoil or stockpile are:
(a) | Cleared and grubbed material (organic matter and all other unsuitable or waste material) | m3 - km | 3320 |  | 0
(b) | Soil and gravel material | m3 - km | 4950 |  | 0
(c) | Boulders, hard material and concrete | m3 - km | 550 |  | 0
C1.5.4 / C3.2.1.2 | Excavating soft material 0 m to 1,5 m below the surface level using labour enhanced construction methods, or instructed by hand under Clause A3.2.7.2d): | m3 | 72 |  | 0
C1.5.4 / C3.2.1.4 | Extra over sub-item C3.2.1.1 for excavation in hard or boulder material, irrespective of depth | m3 | 30 |  | 0
C1.5.4 / C3.2.2 | Backfilling:
C1.5.4 / C3.2.2.1 | Using the excavated material | m3 | 59 |  | 0
C1.5.4 / C3.2.3 | Concrete pipe culverts:
C1.5.4 / C3.2.3.3 | On Class C bedding (type and diameter indicated)
(b) | 600mm dia. Class 100D | m | 15 |  | 0
(d ) | 900mm dia. Class 100D | m | 15 |  | 0
C1.5.4 / C4.2.9 | Excavate material to spoil in sites designated by the Contractor, material obtained from
C1.5.4 / C4.2.9.1 | Soft excavation, overburden and unsuitable material | m3 | 248 |  | 0
C1.5.4 / C4.2.9.2 | Boulder excavation class A | m3 | 14 |  | 0
C1.5.4 / C4.2.9.4 | Hard excavation (other than by blasting) | m3 | 14 |  | 0
C1.5.4 / C4.4.2 | Commercial materials identified by the Contractor from commercial, private or other non-commercial suppliers
C1.5.4 / C4.4.2.1 (q) | Gravel wearing course | m3 | 550 |  | 0
C1.5 | TOTAL CARRIED FORWARD |  |  |  | 0
Province of KwaZulu-Natal |  |  | Contract No. ZNB01871/00000/00/PMC/INF/23/T
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C1.5
THE UPGRADE OF MSUNDUZI RIVER BRIDGE (GRIMTHORPE AVE TO BISHOPSTOWE) DISTRICT ROAD D669 KM 2.54
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
| TOTAL BROUGHT FORWARD |  |  |  | 0
C1.5.4 / C5.1.1 | Roadbed construction and compaction
C1.5.4 / C5.1.1.1 | Compaction of in-situ material to 90% of MDD | m3 | 331 |  | 0
C1.5.4 / C5.2.2 | Fill construction
C1.5.4 / C5.2.2.1 | Normal fill material in compacted layer thicknesses of 200 mm and less:
(a) | Compacted to 90% MDD | m3 | 15 |  | 0
C1.5.4 / C5.3.2.1 | Construction of layer of using conventional construction methods
(g) | Gravel wearing course layer (150mm thick) compactedt o 95% of MDD | m3 | 550 |  | 0
C1.5.4 / C13.1.1 | Provision of designs and drawings of temporary works by an ECSA-registered Professional Engineer or Technologist or Geotechnical Engineer
a) | Temporary causeway design using the given design guideline, drawing no TEMP BR/01 | lump sum | 1 |  | 0
C1.5.4/ PC13.1.3 | Excavation (Temporary causeway)
PC13.1.3.1 | Excavating soft material situated within the following successive depth ranges:
(a) | 0m up to 1,5m | m3 | 161 |  | 0
C1.5.4/ C13.1.6 | Access and drainage: (at temporary causeway)
PC13.1.6.1 | Access | lump sum | 1 |  | 0
PC13.1.6.2 | Drainage | lump sum | 1 |  | 0
C1.5.4/ PC13.1.7 | Backfill to excavations utilising:
PC13.1.7.2 | Imported material | m3 | 77 |  | 0
PC13.1.7.3 | Soil cement | m3 | 52 |  | 0
C1.5.4/ PC13.1.14 | Foundation fill consisting of:
PC13.1.14.4 | Mass concrete, class C12/15-20 | m3 | 160 |  | 0
C1.5.4/ PC13.1.20 | Dowel bars:
PC13.1.20.1 | Drilling and preparation of holes, 38mm dia and each 1m deep | m | 92 |  | 0
C13.1.20.2 | Supply and installation of dowel bars, Y25 bars, 2m long, including an approved non-shrink cementitious grout | kg | 710 |  | 0
C1.5.4/ C13.2.2 | Vertical formwork
C13.2.2.1 | Class F1 surface finish to:
(a) | Mass concrete footing | m2 | 26 |  | 0
(b) | Causeway top slab and concrete infill | m2 | 33 |  | 0
(c) | Causeway retaining walls at approaches | m2 | 48 |  | 0
(d) | Causeway approach slabs | m2 | 96 |  | 0
(e) | Causeway guide blocks | m2 | 17 |  | 0
C1.5.4/ C13.3.1 | Reinforcement for:
C13.3.1.1 | Causeway with approach slabs
(a) | Mild-steel bars | t | 1 |  | 0
(b) | High-yield-stress-steel bars(Y-bars, 450 Mpa) | t | 5 |  | 0
C1.5.4/ C13.4.1 | Cast in situ concrete:
C13.4.1.1 | Strength concrete (class C):
(a) | Causeway top slab and concrete infill (C20/25-20) | m3 | 24 |  | 0
(b) | Causeway retaining walls at approaches(C20/25-20) | m3 | 12 |  | 0
(c) | Causeway approach slabs (C20/25-20) | m3 | 35 |  | 0
(d) | Causeway guide blocks(C20/25-20) | m3 | 2 |  | 0
C1.5.4/ C3.2.5 | Rectangular culverts with prefabricated elements:
PC3.2.5.1 | Prefabricated portal culverts; wall and roof combination
(a) | 2100 mm x 1500 mm, class 75S | m | 39.04 |  | 0
C1.5.4/ C13.7.2 | Filled joints:
C13.7.2.1 | 10 mm thick bitumen impregnated fibreboard | m2 | 6 |  | 0
C1.5 | TOTAL CARRIED FORWARD |  |  |  | 0
Province of KwaZulu-Natal |  |  | Contract No. ZNB01871/00000/00/PMC/INF/23/T
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C1.5
THE UPGRADE OF MSUNDUZI RIVER BRIDGE (GRIMTHORPE AVE TO BISHOPSTOWE) DISTRICT ROAD D669 KM 2.54
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
| TOTAL BROUGHT FORWARD |  |  |  | 0
C1.5.5 | Maintenance of temporary deviations
C1.5.5.1 | Grass cutting | ha | 0.16 |  | 0
C1.5.5.2 | Drain cleaning | km | 0.65 |  | 0
C1.5.5.3 | Cleaning out culverts | m3 | 40 |  | 0
C1.5.5.4 | Collection of rubbish / litter | km | 0.65 |  | 0
C1.5.5.9 | Grading of temporary deviations and existing roads used as detours | km | 0.32 |  | 0
C1.5.5.10 | Watering of temporary deviations and existing roads used as detours | kl | 1500 |  | 0
C1.5.5.11 | Other road maintenance work ordered by the Engineer | Prov Sum | 1000000 | 1 | 1000000
C1.5.5.12 | Handling cost, profit and all other charges in respect of item C1.5.5.12 | % | 1000000 |  | 0
C1.5.6 | Removal of temporary deviations (including removal of temporary structure) | km | 0.32 |  | 0
C1.5.7 | Temporary traffic control facilities
C1.5.7.1 | Delineators including mounting bases and ballast:
(a) | Single sided, reversible left or right (size indicated) | No | 200 |  | 0
(b) | Double sided, reversible left or right (size indicated) | No | 10 |  | 0
C1.5.7.2 | Traffic cones, minimum height 750 mm | No | 60 |  | 0
C1.5.7.3 | Flagmen | man-shift | 2376 |  | 0
C1.5.7.7 | Traffic calming devices:
(b) | 50 mm high x 500 mm wide asphalt rumble strips | m | 100 |  | 0
C1.5.7.9 | Cleaning of trafffic control facilities | month | 18 |  | 0
C1.5.8 | Traffic safety officer | Man-month | 18 |  | 0
C1.5.11 | Provision of safety equipment for visitors
C1.5.11.1 | Provision of reflective safety vests for visitors | No | 5 |  | 0
C1.5.11.2 | Provision of hard hats for visitors | No | 5 |  | 0
C1.5.12 | Additional traffic accommodation facilities ordered by the Engineer:
C1.5.12.1 | Provision of additional traffic accomodation facilities | Prov Sum | 30000 | 1 | 30000
C1.5.12.2 | Handling cost, profit and all other charges in respect of item C1.5.12.1 | % | 30000 |  | 0
PC1.5.13 | Removal of exiting fencing | PC Sum | 100000 | 1 | 100000
PC1.5.14 | Replacement of fencing | PC Sum | 300000 | 1 | 300000
C1.5 | TOTAL CARRIED FORWARD TO SUMMARY |  |  |  | 1430000 | 1430000 | 1703595 | -273595
additional contract period and additional requirements for coto

## C2.1
Province of KwaZulu-Natal |  |  | Contract No. ZNB01871/00000/00/PMC/INF/23/T
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C2.1
THE UPGRADE OF MSUNDUZI RIVER BRIDGE (GRIMTHORPE AVE TO BISHOPSTOWE) DISTRICT ROAD D669 KM 2.54
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C2.1 | GENERAL REQUIREMENTS AND TRENCHING FOR SERVICES
C2.1.1 | Location,Identification and relocation of existing services
C2.1.1.1 | Contractors's obligations | Lump Sum | 1 |  | 0
C2.1.1.2 | Permanent services relocation or protection work by others | PC Sum | 2500000 | 1 | 2500000
C2.1.1.3 | Handling costs and profit in respect of item C2.1.1.2 above | % | 2500000 |  | 0
C2.1.1.4 | Permanent services relocation or protection work by Contractor | PC Sum | 500000 | 1 | 500000
C2.1.2.5 | Using hand excavation to locate,expose and verify services | m³ | 100 |  | 0
C2.1.5 | Provision of record drawings and applicable data | Lump Sum | 1 |  | 0
C2.1 | TOTAL CARRIED FORWARD |  |  |  | 3000000

## C20.1
Province of KwaZulu-Natal |  |  | Contract No. ZNB01871/00000/00/PMC/INF/23/T
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER C20.1
THE UPGRADE OF MSUNDUZI RIVER BRIDGE (GRIMTHORPE AVE TO BISHOPSTOWE) DISTRICT ROAD D669 KM 2.54
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C20.1 | TESTING MATERIALS AND JUDGEMENT OF WORKMANSHIP
C20.1.1 | Special tests on elastomeric bearings (150% vertical load and 150% shear distortion)
| (a) 300x250x61 elastomeric bearings | No. | 42
C20.1.2 | Special tests requested by the Engineer
C20.1.2.1 | Employer’s contribution to concrete durability tests
| (a) Tests for water sorptivity | PC Sum | 150000 | 1 | 150000
| (i) Handling costs and profit in respect of item C20.1.2.1(a) | % | 150000 |  | 0
| (b) Tests for oxygen permeability | PC Sum | 150000 | 1 | 150000
| (i) Handling costs and profit in respect of item C20.1.2.1(b) | % | 150000 |  | 0
| (d) Tests for concrete cover | PC Sum | 150000 | 1 | 150000
| (i) Handling costs and profit in respect of item C20.1.2.1(d) | % | 150000 |  | 0
C20.1.2.2 | Employer’s contribution to other special tests
(a) | Concrete strength and roadworks related tests | PC Sum | 2000000 | 1 | 2000000
(a.i) | Handling costs and profit in respect of item C20.1.2.2(a) | % | 2000000 |  | 0
C20.1 | TOTAL CARRIED FORWARD TO SUMMARY |  |  |  | 2450000

## A
Province of KwaZulu-Natal |  |  |  | Contract No. ZNB01871/00000/00/PMC/INF/23/T
Department of Transport
THE UPGRADE OF MSUNDUZI RIVER BRIDGE (GRIMTHORPE AVE TO BISHOPSTOWE) DISTRICT ROAD D669 KM 2.54
SCHEDULE A: ROADWORKS - SUMMARY
CHAPTER | DESCRIPTION |  |  | FROM PAGE | AMOUNT
C1.2 | GENERAL REQUIREMENTS AND PAYMENT |  |  |  | 80000
C1.3 | CONTRACTOR'S SITE ESTABLISHMENT AND GENERAL OBLIGATIONS | 0 | #VALUE! |  | 0
C1.4 | FACILITIES FOR THE ENGINEER | 0 | #VALUE! |  | 210000
C1.5 | ACCOMMODATION OF TRAFFIC | 0 | #VALUE! |  | 1430000
C2.1 | GENERAL REQUIREMENTS AND TRENCHING FOR SERVICES | 0 | #VALUE! |  | 3000000
C20.1 | TESTING MATERIALS AND JUDGEMENT OF WORKMANSHIP |  |  |  | 2450000
TOTAL SCHEDULE A: ROADWORKS |  |  |  |  | 7170000

## C11.1-B
Province of KwaZulu-Natal |  |  | Contract No. ZNB01871/00000/00/PMC/INF/23/T
Department of Transport
SCHEDULE B: BRIDGE WORKS |  |  |  |  | CHAPTER C11.1
THE UPGRADE OF MSUNDUZI RIVER BRIDGE (GRIMTHORPE AVE TO BISHOPSTOWE) DISTRICT ROAD D669 KM 2.54
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C11.1 | PITCHING, STONEWORK, CAST IN SITU CONCRETE FOR PROTECTION AGAINST EROSION
C11.1.5 | Concrete pitching or paving
C11.1.5.1 | Segmental block paving, class C20/25-14, Type S-A, 60 mm thick | m2 | 230 |  | 0
C11.1.6 | Concrete edge beams, concrete class C16/20-20 | m3 | 1 |  | 0
C11.1.7 | Provision of approved herbicide and ant poison:
C11.1.7.1 | Provision of materials | PC sum | 5000 | 1 | 5000
C11.1.7.2 | Contractor’s charges and profit added to the prime cost sum | % | 5000 |  | 0
C11.1 | TOTAL CARRIED FORWARD TO SUMMARY |  |  |  | 5000

## C11.2-B
Province of KwaZulu-Natal |  |  | Contract No. ZNB01871/00000/00/PMC/INF/23/T
Department of Transport
SCHEDULE B: BRIDGE WORKS |  |  |  |  | CHAPTER C11.2
THE UPGRADE OF MSUNDUZI RIVER BRIDGE (GRIMTHORPE AVE TO BISHOPSTOWE) DISTRICT ROAD D669 KM 2.54
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C11.2 | NON-STRUCTURAL GABIONS
C11.2.1 | Foundation trench excavation:
C11.2.1.1 | Excavating all material situated within the following depth ranges below the surface level
(a) | 0m to 1,5m | m3 | 152 |  | 0
C11.2.2 | Surface preparation for bedding the gabion boxes and mattresses | m2 | 500 |  | 0
C11.2.3 | Gabion boxes and mattresses:
C11.2.3.1 | Galvanized gabion boxes, 1m x 1m x 4m with mesh type 80 and 2,7mm dia class A wire, and diaphragms at 1m centres | m3 | 224 |  | 0
C11.2.3.3 | Galvanized gabion mattresses, 0,3m deep, with mesh type 60 and 2,2mm dia class A galvanized wire , and diaphragms at 1m centres | m3 | 148 |  | 0
C11.2.4 | Geotextile, nonwoven, continuous filament, needlepunched, polyester geotextile, grade A4, underneath gabions | m2 | 710 |  | 0
C11.2 | TOTAL CARRIED FORWARD TO SUMMARY |  |  |  | 0

## C11.4-B
Province of KwaZulu-Natal |  |  | Contract No. ZNB01871/00000/00/PMC/INF/23/T
Department of Transport
SCHEDULE B: BRIDGE WORKS |  |  |  |  | CHAPTER C11.4
THE UPGRADE OF MSUNDUZI RIVER BRIDGE (GRIMTHORPE AVE TO BISHOPSTOWE) DISTRICT ROAD D669 KM 2.54
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C11.4 | ROAD RESTRAINT SYSTEMS
C11.4.1 | Erecting of guardrails at 3,81m spacing
C11.4.1.2 | Terminal sections for 3,81 guardrails comprising of:
(f) | Bridge adaptors, 11.4m long , including extra rails and posts, complete as shown on the drawings | No | 4 |  | 0
C11.4 | TOTAL CARRIED FORWARD TO SUMMARY |  |  |  | 0

## C12.6-B
Province of KwaZulu-Natal |  |  | Contract No. ZNB01871/00000/00/PMC/INF/23/T
Department of Transport
SCHEDULE B: BRIDGE WORKS |  |  |  |  | CHAPTER C12.6
THE UPGRADE OF MSUNDUZI RIVER BRIDGE (GRIMTHORPE AVE TO BISHOPSTOWE) DISTRICT ROAD D669 KM 2.54
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C12.6 | MECHANICALLY STABILISED EARTH AND GABIONS
PC12.6.1 | Establishment on site for MSE
PC12.6.1.1 | For reinforced concrete facing | lump sum | 1 |  | 0
PC12.6.2 | Excavation for wall base foundation , over the full width of the reinforced earth mass | m3 | 2475 |  | 0
C12.6.3 | Concrete for wall base foundation, concrete class C12/15-20 | m3 | 15 |  | 0
C12.6.5 | Preparation of surface for laying metallic strips or geosynthetic | m2 | 1820 |  | 0
C12.6.6 | Metallic reinforcing strips, 45mm x 5mm in section, high adherence hot dip galvanized medium tensile steel | m | 7238 |  | 0
C12.6.10 | Fixing mechanism to facings
C12.6.10.1 | For Strips | No | 1496 |  | 0
PC12.6.11 | Backfill (Fill from comercial source inc all haulage, stockpiling, etc)
PC12.6.11.1 | Grade G5A material, free draining material with less than 5% passing the 75 micron sieve, in layers of 150mm, compacted to 93% mod AASHTO, between the two MSE wall facings, below the 100 year flood level | m3 | 2300 |  | 0
PC12.6.11.2 | Grade G5A material, in layers of 150mm, compacted to 93% mod AASHTO, between the two MSE wall facings, above the 100 year flood level | m3 | 2700 |  | 0
PC12.6.12 | Facings, concrete class D25/30-20-XC4, 140mm thick
PC12.6.12.1 | For supply of concrete panel facings
(a) | Non reinforced panels | m2 | 385 |  | 0
(b) | Reinforced panels | m2 | 444 |  | 0
(c) | Corner elements | m2 | 4 |  | 0
PC12.6.12.4 | For erection of concrete panel facings, including joint fillers/geotextiles | m2 | 833 |  | 0
PC12.6.18 | Temporary MSE wall complete with foundations, reinforcement strips and concrete panel facings, as designed by the contractor | m2 | 20 |  | 0
C13.8.12 | Synthetic-fibre filter fabric, nonwoven, continuous filament, needlepunched, polyester geotextile, grade A4, wrapped around drainage strip | m2 | 1700 |  | 0
C13.8.14 | Crushed stone in drainage strips, 20mm stone size | m3 | 215 |  | 0
C12.6 | TOTAL CARRIED FORWARD TO SUMMARY |  |  |  | 0

## C13.1-B
Province of KwaZulu-Natal |  |  | Contract No. ZNB01871/00000/00/PMC/INF/23/T
Department of Transport
SCHEDULE B: BRIDGE WORKS |  |  |  |  | CHAPTER C13.1
THE UPGRADE OF MSUNDUZI RIVER BRIDGE (GRIMTHORPE AVE TO BISHOPSTOWE) DISTRICT ROAD D669 KM 2.54
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C13.1 | FOUNDATIONS
C13.1.2 | Additional foundation investigations:
C13.1.2.1 | Provisional sum allowed for additional foundation investigations | Prov Sum | 20000 | 1 | 20000
C13.1.2.2 | Handling costs and profit in respect of item C13.1.2.1 | % | 20000 |  | 0
PC13.1.3 | Excavation:
PC13.1.3.1 | Excavating soft material situated within the following successive depth ranges:
(a) | 0m up to 1,5m | m3 | 452 |  | 0
(b) | > 1,5m and < 3,0m | m3 | 312 |  | 0
(c) | > 3m and < 4,5m | m3 | 202 |  | 0
(d) | > 4,5m and < 6,0m | m3 | 108 |  | 0
C13.1.3.2 | Extra over subitem C13.1.3.1 for excavation in hard material irrespective of depth | m3 | 617 |  | 0
C13.1.3.3 | Extra over subitem C13.1.3.1 for additional excavation required by the Engineer after excavation is complete | m3 | 20 |  | 0
PC13.1.3.4 | Extra over subitem C13.1.3.1 for excavation by hand | m3 | 25 |  | 0
C13.1.6 | Access and drainage:
C13.1.6.1 | Access | lump sum | 1 |  | 0
C13.1.6.2 | Drainage | lump sum | 1 |  | 0
PC13.1.7 | Backfill to excavations utilising:
C13.1.7.1 | Material from excavation | m3 | 720 |  | 0
PC13.1.7.2 | Imported material | m3 | 80 |  | 0
PC13.1.7.3 | Soil cement | m3 | 20 |  | 0
PC13.1.7.4 | Compacted River sand | m3 | 103 |  | 0
C13.1.9 | Fill within a restricted area (extra over item C5.2.2) | m3 | 828 |  | 0
C13.1.10 | Haul in excess of 1,0 km on excavated material and on material imported for backfill, foundation fill and fill for caissons | m3 /km | 2000 |  | 0
PC13.1.12 | Overbreak in excavation in hard material | m2 | 302 |  | 0
PC13.1.14 | Foundation fill consisting of:
PC13.1.14.4 | Mass concrete, class C12/15-20 | m3 | 70 |  | 0
PC13.1.14.5 | Concrete blinding, 75mm thick, class C12/15-20 | m3 | 73 |  | 0
PC13.1.20 | Dowel bars:
PC13.1.20.1 | Drilling and preparation of holes, 38mm dia and each 1,8m deep | m | 178 |  | 0
C13.1.20.2 | Supply and installation of dowel bars, Y25 galvanized bars, 2.7m long (2.5m+0.2m bend), including an approved non-shrink cementitious grout | kg | 1043 |  | 0
C13.1.21 | Foundation lining, 0.25 mm polyethylene sheeting | m2 | 70 |  | 0
C13.1 | TOTAL CARRIED FORWARD TO SUMMARY |  |  |  | 20000

## C13.2-B
Province of KwaZulu-Natal |  |  | Contract No. ZNB01871/00000/00/PMC/INF/23/T
Department of Transport
SCHEDULE B: BRIDGE WORKS |  |  |  |  | CHAPTER C13.2
THE UPGRADE OF MSUNDUZI RIVER BRIDGE (GRIMTHORPE AVE TO BISHOPSTOWE) DISTRICT ROAD D669 KM 2.54
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C13.2 | FALSEWORK, FORMWORK AND CONCRETE FINISH
C13.2.2 | Vertical formwork
C13.2.2.1 | Class F1 surface finish to:
(a) | Abutment footings | m2 | 69 |  | 0
(b) | Abutment walls | m2 | 442 |  | 0
(c) | Approach slabs | m2 | 11 |  | 0
(d) | Pier footings | m2 | 49 |  | 0
(e) | Parapet footing on top of MSE-walls | m2 | 388 |  | 0
C13.2.2.2 | Class F2 surface finish to:
(a) | Pier walls | m2 | 322 |  | 0
(b) | Pier heads | m2 | 63 |  | 0
(c) | Abutment walls | m2 | 306 |  | 0
(d) | In-situ deck slab | m2 | 119 |  | 0
(e) | In-situ deck diaphragm beams | m2 | 216 |  | 0
(f) | Parapet footing on top of MSE-walls | m2 | 176 |  | 0
(g) | Pier walls, rounded, 800mm dia. | m2 | 36 |  | 0
(h) | Pier walls, rounded, 1200mm dia. | m2 | 10 |  | 0
C13.2.2.3 | Class F3 surface finish to:
(a) | In-situ deck slab upstand wall | m2 | 12 |  | 0
(b) | Parapet footing on top of MSE-walls | m2 | 59 |  | 0
C13.2.3 | Horizontal formwork
C13.2.3.2 | Class F2 surface finish to:
(a) | Pier heads | m2 | 14 |  | 0
(b) | In-situ deck slab cantilevers | m2 | 78 |  | 0
(c) | In-situ deck diaphragm beams | m2 | 61 |  | 0
C13.2.4 | Inclined formwork
C13.2.4.1 | Class F1 surface finish to:
(a) | Abutment walls | m2 | 22 |  | 0
C13.2.6 | Formwork to form open joints (bridge deck expansion joints, 30mm wide) , ie removal of filler material | m2 | 77 |  | 0
C13.2.10 | Provision of designs and drawings of falsework and formwork by an ECSA registered Professional Engineer or Technologist, for abutment walls, pier walls, pier heads, deck slab cantilever portion, and in-situ diaphragm beams | lump sum | 1 |  | 0
C13.2 | TOTAL CARRIED FORWARD TO SUMMARY |  |  |  | 0

## C13.3-B
Province of KwaZulu-Natal |  |  | Contract No. ZNB01871/00000/00/PMC/INF/23/T
Department of Transport
SCHEDULE B: BRIDGE WORKS |  |  |  |  | CHAPTER C13.3
THE UPGRADE OF MSUNDUZI RIVER BRIDGE (GRIMTHORPE AVE TO BISHOPSTOWE) DISTRICT ROAD D669 KM 2.54
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C13.3 | STEEL REINFORCEMENT
C13.3.1 | Reinforcement for:
C13.3.1.1 | Parapets and end blocks
(a) | Mild-steel bars | t | 2 |  | 0
(b) | High-yield-stress-steel bars (Y) | t | 18 |  | 0
C13.3.1.2 | Abutments
(a) | Mild-steel bars | t | 1 |  | 0
(b) | High-yield-stress-steel bars (Y) | t | 46 |  | 0
C13.3.1.3 | Piers
(a) | Mild-steel bars | t | 1 |  | 0
(b) | High-yield-stress-steel bars (Y) | t | 24 |  | 0
C13.3.1.4 | In-situ deck slab and diaphragm beams
(a) | Mild-steel bars | t | 1 |  | 0
(b) | High-yield-stress-steel bars (Y) | t | 25 |  | 0
(e) | 12,9mm dia prestress cable, not to be stressed, placed in transverse beams. (1440 m in total ) | t | 1.5 |  | 0
C13.3.1.5 | Parapet footing on top of MSE-walls
(a) | Mild-steel bars | t | 1 |  | 0
(b) | High-yield-stress-steel bars (Y) | t | 34 |  | 0
C13.3.4 | Extra-over item C13.3.1.1 (a), (b), for galvanising of parapet reinforcement | t | 20 |  | 0
C13.3 | TOTAL CARRIED FORWARD TO SUMMARY |  |  |  | 0

## C13.4-B
Province of KwaZulu-Natal |  |  | Contract No. ZNB01871/00000/00/PMC/INF/23/T
Department of Transport
SCHEDULE B: BRIDGE WORKS |  |  |  |  | CHAPTER C13.4
THE UPGRADE OF MSUNDUZI RIVER BRIDGE (GRIMTHORPE AVE TO BISHOPSTOWE) DISTRICT ROAD D669 KM 2.54
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C13.4 | CONCRETE
C13.4.1 | Cast in situ concrete
C13.4.1.1 | Strength concrete (class C):
(a) | Abutment Footings (C25/30-20 ) | m3 | 131 |  | 0
(b) | Pier Footings (C25/30-20 ) | m3 | 49 |  | 0
(c) | Parapet footing on top of MSE-walls (C25/30-20) | m3 | 291 |  | 0
(d) | Approach slabs (C25/30-20 ) | m3 | 21 |  | 0
PC13.4.1.2 | Durable concrete (class D):
(a) | Pier walls (D25/30-20-XC4) | m3 | 138 |  | 0
(b) | Pier heads (D25/30-20-XC4) | m3 | 21 |  | 0
(c) | Abutment walls (D25/30-20-XC4) | m3 | 241 |  | 0
(d) | Deck diapragm beams (D25/30-20-XC4) | m3 | 74 |  | 0
(e) | Deck top slab (incl upsatnd beam for pedestrian parapet (D25/30-20-XC4) | m3 | 140 |  | 0
C13.4.3 | Extra over item C13.4.1 for the protection of concrete from adverse environmental conditions, if required:
PC13.4.3.2 | Durable concrete (class D):
(a) | Deck top slab (D25/30-20-XC4) | m3 | 140 |  | 0
C13.4.5 | Curing and surface protection of cast in situ concrete, as and where specifically required:
C13.4.5.1 | Abutment footings (curing compound) | m2 | 215 |  | 0
C13.4.5.2 | Pier footings (curing compound) | m2 | 110 |  | 0
C13.4.5.3 | Parapet footing on top of MSE-walls (curing compound) | m2 | 1117 |  | 0
C13.4.5.4 | Approach slabs (curing compound) | m2 | 81 |  | 0
C13.4.5.5 | Pier walls (curing compound) | m2 | 358 |  | 0
C13.4.5.6 | Pier heads (curing compound) | m2 | 73 |  | 0
C13.4.5.7 | Abutment walls (curing compound) | m2 | 1045 |  | 0
C13.4.5.8 | Deck ends and sides (curing compound) | m2 | 209 |  | 0
C13.4.5.9 | Deck diapragm beams (curing compound) | m2 | 277 |  | 0
C13.4.5.10 | Deck top surface (keep constantly wet) | m2 | 705 |  | 0
C13.4.9 | Manufacturing precast concrete members
(a) | Pretensioned I-8 beams, length 19.6m, class D40/50-20-XC4 concrete, incl. pre-stressing & reinforcement complete as shown on drawing 09. (Concrete volume=7.26m3 and reinf=867kg/beam) | No | 21 |  | 0
(b) | Concrete planks, concrete class D32/40-20-XC4, incl. reinforcement complete as shown on the drawing 08 (ave. concrete volume=0,122m3 and reinf = 28kg/plank) | No | 324 |  | 0
(c) | Coping units, concrete class D25/30-20-XC4, incl. reinforcement complete as shown on the drawing 16 (concrete volume=0,102m3 and reinf = 15kg/unit) | No | 290 |  | 0
C13.4.11 | Transporting and erecting precast concrete members (description of member and approximate mass to be given)
(a) | Pretensioned I-8 beams, length 19,6m, with weight = 19 t/beam | No | 21 |  | 0
(b) | Concrete planks, weight=320 kg /plank | No | 324 |  | 0
(c) | Coping units, 1m long, with weight = 265 kg/unit | No | 290 |  | 0
C13.4.13 | Complete demolition and disposal of existing structural concrete elements or parts existing structures:
C13.4.13.1 | Existing concrete causeway, including all costs and haulage to dispose at a registered municipal dumping site | m3 | 264 |  | 0
C13.4 | TOTAL CARRIED FORWARD TO SUMMARY |  |  |  | 0

## C13.6-B
Province of KwaZulu-Natal |  |  | Contract No. ZNB01871/00000/00/PMC/INF/23/T
Department of Transport
SCHEDULE B: BRIDGE WORKS |  |  |  |  | CHAPTER C13.6
THE UPGRADE OF MSUNDUZI RIVER BRIDGE (GRIMTHORPE AVE TO BISHOPSTOWE) DISTRICT ROAD D669 KM 2.54
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C13.6 | BEARINGS
C13.6.1 | Bearings:
C13.6.1.1 | Elastomeric bearing pads (300x250x61 mm) with 3mm thick reinforcing plates made from 3CR12 stainless steel | No | 42 |  | 0
C13.6.1.2 | Provision of engineering drawings of proprietary bearings and certification after installation by an ECSA Registered Professional Engineer or Technologist | lump sum | 1 |  | 0
C13.6.3 | Bearing strips, Bearings strips, two layers 3-ply roofing felt | m2 | 7 |  | 0
C13.6.4 | Dowels or guides
C13.6.4.1 | Dowels, 1000mm stainless steel 40 dia bars complete with sleeve & plug as on drawings | No | 18 |  | 0
C13.6 | TOTAL CARRIED FORWARD TO SUMMARY |  |  |  | 0

## C13.7-B
Province of KwaZulu-Natal |  |  | Contract No. ZNB01871/00000/00/PMC/INF/23/T
Department of Transport
SCHEDULE B: BRIDGE WORKS |  |  |  |  | CHAPTER C13.7
THE UPGRADE OF MSUNDUZI RIVER BRIDGE (GRIMTHORPE AVE TO BISHOPSTOWE) DISTRICT ROAD D669 KM 2.54
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C13.7 | JOINTS
C13.7.2 | Filled joints:
C13.7.2.1(a) | 10 mm thick bitumen impregnated fibreboard | m2 | 28 |  | 0
(b) | 30 mm expanded polystyrene | m2 | 77 |  | 0
(c) | 50 mm expanded polystyrene | m2 | 145 |  | 0
(d) | Two layers of bituminous paint | m2 | 20 |  | 0
C13.7.4 | Sealing joints with:
C13.7.4.1 | 10x10 mm approved silicon sealant | m | 28 |  | 0
C13.7.5 | Supply and installation of Agrément South Africa certified proprietary expansion joints
C13.7.5.2 | Asphaltic plug type joints
(c) | 400mm x 75mm | m | 13 |  | 0
(d) | 500mm x 75mm | m | 38 |  | 0
C13.7.5.3 | Provision of engineering drawings of proprietary joints and certification after installation by an ECSA registered Professional Engineer or Technologist | lump sum | 1 |  | 0
C13.7.6 | Joint terminations in:
C13.7.6.1 | Barriers and Parapets
(a) | Asphaltic plug type joints 400mm x 75mm | No | 1 |  | 0
(b) | Asphaltic plug type joints 500mm x 75mm | No | 3 |  | 0
C13.7.6.2 | Sidewalks
(a) | Asphaltic plug type joints 400mm x 75mm | No | 1 |  | 0
(b) | Asphaltic plug type joints 500mm x 75mm | No | 3 |  | 0
C13.7.7 | Cover plates (non-metallic) in barriers, parapets and sidewalks where specified on the drawings in:
C13.7.7.1 | Barriers and Parapets
(a) | Asphaltic plug type joints 400mm x 75mm | No | 1 |  | 0
(b) | Asphaltic plug type joints 500mm x 75mm | No | 3 |  | 0
C13.7.7.2 | Sidewalks
(a) | Asphaltic plug type joints 400mm x 75mm | No | 1 |  | 0
(b) | Asphaltic plug type joints 500mm x 75mm | No | 3 |  | 0
C13.7 | TOTAL CARRIED FORWARD TO SUMMARY |  |  |  | 0

## C13.8-B
Province of KwaZulu-Natal |  |  | Contract No. ZNB01871/00000/00/PMC/INF/23/T
Department of Transport
SCHEDULE B: BRIDGE WORKS |  |  |  |  | CHAPTER C13.8
THE UPGRADE OF MSUNDUZI RIVER BRIDGE (GRIMTHORPE AVE TO BISHOPSTOWE) DISTRICT ROAD D669 KM 2.54
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C13.8 | ANCILLARY STRUCTURAL ELEMENTS
C13.8.10 | Drainage pipes and weep holes:
C13.8.10.1 | Drainage pipes:
(a) | 110 mm dia heavy duty uPVC pipes (class 12) in abutments | m | 12 |  | 0
(b) | 110 mm dia 90° heavy duty uPVC lobster-back bends with solvent cement-type socket, in abutments | No | 2 |  | 0
(c) | 75 mm dia normal duty uPVC pipes (class 6) in deck | m | 12 |  | 0
(d) | 250 mm dia heavy duty uPVC pipes (class 12) drainage pipes behind MSE walls | m | 8 |  | 0
(e) | 250 mm dia 90° heavy duty uPVC lobster-back bends with solvent cement-type socket, behind MSE walls | No | 3 |  | 0
C13.8.10.2 | Weep holes:
(a) | 50 mm dia normal duty uPVC pipes (class 6) | m | 18 |  | 0
C13.8.15 | Drainage strips, 200mm wide flownet drainage strips wrapped in an approved geotextile, nonwoven, needlepunched, grade A4 | m | 254 |  | 0
C13.8.16 | Perforated drainage pipes:
C13.8.16.1 | 65 mm dia perforated drainage pipe wrapped in an approved geotextile, nonwoven, needlepunched, grade A4, including the 300x50 mm thick mortar bed complete as shown on the drawings | m | 38 |  | 0
C13.8 | TOTAL CARRIED FORWARD TO SUMMARY |  |  |  | 0

## B
Province of KwaZulu-Natal |  |  |  | Contract No. ZNB01871/00000/00/PMC/INF/23/T
Department of Transport
THE UPGRADE OF MSUNDUZI RIVER BRIDGE (GRIMTHORPE AVE TO BISHOPSTOWE) DISTRICT ROAD D669 KM 2.54
SCHEDULE B: BRIDGE WORKS - SUMMARY
CHAPTER | DESCRIPTION |  |  | FROM PAGE | AMOUNT
C11.1 | PITCHING, STONEWORK, CAST IN SITU CONCRETE FOR PROTECTION AGAINST EROSION | 0 | #VALUE! |  | 5000
C11.2 | NON-STRUCTURAL GABIONS | 0 | #VALUE! |  | 0
C11.4 | ROAD RESTRAINT SYSTEMS | 0 | #VALUE! |  | 0
C12.6 | MECHANICALLY STABILISED EARTH AND GABIONS | #REF! | #REF! |  | 0
C13.1 | FOUNDATIONS | #REF! | #REF! |  | 20000
C13.2 | FALSEWORK, FORMWORK AND CONCRETE FINISH | 0 | #VALUE! |  | 0
C13.3 | STEEL REINFORCEMENT | #REF! | #REF! |  | 0
C13.4 | CONCRETE | #REF! | #REF! |  | 0
C13.6 | BEARINGS | #REF! | #REF! |  | 0
C13.7 | JOINTS | #REF! | #REF! |  | 0
C13.8 | ANCILLARY STRUCTURAL ELEMENTS | #REF! | #REF! |  | 0
TOTAL SCHEDULE B: BRIDGE WORKS |  |  |  |  | 25000

## Section E
Province of KwaZulu-Natal |  |  | Contract No. ZNB01871/00000/00/PMC/INF/23/T
Department of Transport
SCHEDULE E: EXPANDED PUBLIC WORKS PROGRAMME (EPWP) |  |  |  |  | CHAPTER E
THE UPGRADE OF MSUNDUZI RIVER BRIDGE (GRIMTHORPE AVE TO BISHOPSTOWE) DISTRICT ROAD D669 KM 2.54
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
E | EXPANDED PUBLIC WORKS PROGRAMME (EPWP)
E6.01 | Provision of training venue facility, including the cost of transport the learners to and from this facility | Lump Sum | 1 |  | 0
E6.02 | Training of learners employed by the contractor or by the Targeted Enterprise subcontractors:
(a) | Generic Skills:
(a.i) | Training costs | Prov Sum | 150000 | 1 | 150000
(a.ii) | Handling costs and profit in respect of subitem E6.02(a)(i) | % | 150000 |  | 0
(b) | Entrepreneurial skills:
(b.i) | Training costs | Prov Sum | 150000 | 1 | 150000
(b.ii) | Handling costs and profit in respect of subitem E6.02(b)(i) | % | 150000 |  | 0
(c) | Construction skills:
(c.i) | Training costs | Prov Sum | 150000 | 1 | 150000
(c.ii) | Handling costs and profit in respect of subitem E6.02(c)(i) | % | 150000 |  | 0
(d) | Transportation & accommodation costs of selected leaners only, while receiving off-site training:
(d.i) | Transportation and accommodation costs | Prov Sum | 150000 | 1 | 150000
(d.ii) | Handling costs and profit in respect of subitem E6.02(d)(i) | % | 150000 |  | 0
E6.03 | Payments associated with the NYS programme:
(a) | Employment of NYS workers | Prov Sum | 200000 | 1 | 200000
(b) | Provision of tools and apparel for the NYS workers | Prov Sum | 40000 | 1 | 40000
(c) | Handling cost and profit in respect of subitem E6.03(a) and (b) | % | 240000 |  | 0
(d) | Training of NYS youth workers:
(d.i) | Provision of training for NYS youth workers | Prov Sum | 400000 | 1 | 400000
(d.ii) | Handling costs and profit in respect of subitem subitem E6.03(d)(i) | % | 400000 |  | 0
(e) | Liaison with the Employer’s project manager and the training service provider:
(e.i) | Liaison conducted by the Construction Manager | hr | 60 |  | 0
(e.ii) | Liaison conducted by senior site foreman | hr | 100 |  | 0
E | TOTAL CARRIED FORWARD TO SUMMARY |  |  |  | 1240000

## E
Province of KwaZulu-Natal |  | Contract No. ZNB01871/00000/00/PMC/INF/23/T
Department of Transport
THE UPGRADE OF MSUNDUZI RIVER BRIDGE (GRIMTHORPE AVE TO BISHOPSTOWE) DISTRICT ROAD D669 KM 2.54
SCHEDULE E: EXPANDED PUBLIC WORKS PROGRAMME (EPWP) - SUMMARY
CHAPTER | DESCRIPTION | FROM PAGE | AMOUNT
E | EXPANDED PUBLIC WORKS PROGRAMME (EPWP) |  | 1240000
TOTAL SCHEDULE E: EXPANDED PUBLIC WORKS PROGRAMME (EPWP) |  |  | 1240000

## Section F
Province of KwaZulu-Natal |  |  | Contract No. ZNB01871/00000/00/PMC/INF/23/T
Department of Transport
SCHEDULE F: SMALL CONTRACTOR DEVELOPMENT |  |  |  |  | CHAPTER F
THE UPGRADE OF MSUNDUZI RIVER BRIDGE (GRIMTHORPE AVE TO BISHOPSTOWE) DISTRICT ROAD D669 KM 2.54
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
F | SMALL CONTRACTOR DEVELOPMENT
F10.01 | Procurement of Targeted Enterprises
(a) | Management and execution of the Targeted Enterprise procurement process:
(a.i) | Procurement process for the appointment of CIDB contractor grading designation 1 Targeted Enterprise subcontractor (30 copies of the tender document required for each individual tender) | No | 3 |  | 0
(a.ii) | Procurement process for the appointment of CIDB contractor grading designation 2 Targeted Enterprise subcontractor (30 copies of the tender document required for each individual tender) | No | 2 |  | 0
(a.iii) | Procurement process for the appointment of CIDB contractor grading designation 3 Targeted Enterprise subcontractor (15 copies of the tender document required for each individual tender) | No | 1 |  | 0
(a.iv) | Procurement process for the appointment of CIDB contractor grading designation 4 Targeted Enterprise subcontractor (15 copies of the tender document required for each individual tender) | No | 2 |  | 0
F10.02 | Construction Works for Targeted Enterprise subcontractors:
(a) | Payments associated with the construction Works carried out by Targeted Enterprise subcontractors | Prov Sum | 9521318.9 | 1 | 9521318.9
(b) | Handling costs and profit in respect of subitem F10.02(a) | % | 9521318.9 |  | 0
(c) | Supply of materials and small construction equipment to assist Targeted Enterprise subcontractors | Prov Sum | 1088263.62 | 1 | 1088263.62
(d) | Handling costs and profit in respect of subitem F10.02(c) | % | 1088263.62 |  | 0
(e) | Management of Targeted Enterprise subcontractors | month | 18 |  | 0
F | TOTAL CARRIED FORWARD |  |  |  | 10609582.52
Province of KwaZulu-Natal |  |  | Contract No. ZNB01871/00000/00/PMC/INF/23/T
Department of Transport
SCHEDULE A: ROADWORKS |  |  |  |  | CHAPTER F
THE UPGRADE OF MSUNDUZI RIVER BRIDGE (GRIMTHORPE AVE TO BISHOPSTOWE) DISTRICT ROAD D669 KM 2.54
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
| TOTAL BROUGHT FORWARD |  |  |  | 10609582.52
F10.03 | Training Targeted Enterprise subcontractors:
(a) | Generic Skills
(a.i) | Training costs | Prov Sum | 150000 | 1 | 150000
(a.ii) | Handling costs and profit in respect of subitem F10,03(a)(i) | % | 150000 |  | 0
(b) | Entrepreneurial skills:
(b.i) | Training costs | Prov Sum | 150000 | 1 | 150000
(b.ii) | Handling costs and profit in respect of subitem F10,03(b)(i) | % | 150000 |  | 0
(c) | Construction skills:
(c.i) | Training costs | Prov Sum | 150000 | 1 | 150000
(c.ii) | Handling costs and profit in respect of subitem F10,03(c)(i) | % | 150000 |  | 0
(d) | Transportation & accommodation costs of selected leaners only, while receiving off-site training:
(d.i) | Training costs | Prov Sum | 150000 | 1 | 150000
(d.ii) | Handling costs and profit in respect of subitem F10,03 (d)(i) | % | 150000 |  | 0
F | TOTAL CARRIED FORWARD TO SUMMARY |  |  |  | 11209582.52

## F
Province of KwaZulu-Natal |  | Contract No. ZNB01871/00000/00/PMC/INF/23/T
Department of Transport
THE UPGRADE OF MSUNDUZI RIVER BRIDGE (GRIMTHORPE AVE TO BISHOPSTOWE) DISTRICT ROAD D669 KM 2.54
SCHEDULE F:SMALL CONTRACTOR DEVELOPMENT - SUMMARY
CHAPTER | DESCRIPTION | FROM PAGE | AMOUNT
F | SMALL CONTRACTOR DEVELOPMENT |  | 11209582.52
TOTAL SCHEDULE F: SMALL CONTRACTOR DEVELOPMENT |  |  | 11209582.52

## Section G
Province of KwaZulu-Natal |  |  | Contract No. ZNB01871/00000/00/PMC/INF/23/T
Department of Transport
SCHEDULE G: CONTRACT SKILLS DEVELOPMENT GOAL (CSDG) |  |  |  |  | CHAPTER G
THE UPGRADE OF MSUNDUZI RIVER BRIDGE (GRIMTHORPE AVE TO BISHOPSTOWE) DISTRICT ROAD D669 KM 2.54
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
G | CIDB CONTRACT SKILLS DEVELOPMENT GOAL (CSDG)
G7.01 | Payments associated with the Contract Skills Development Goals:
(a) | Employment of Leaners employed under Method 1
| (i) Provision for stipends | Prov Sum | 42000 | 1 | 42000
| (ii) Provision for additional Costs | Prov Sum | 9000 | 1 | 9000
(e) | Liaison with the Employer’s project manager and the training service provider:
| (i) Liaison conducted by the Construction Manager | h | 24 |  | 0
G | TOTAL CARRIED FORWARD TO SUMMARY |  |  |  | 51000

## G
Province of KwaZulu-Natal |  | Contract No. ZNB01871/00000/00/PMC/INF/23/T
Department of Transport
THE UPGRADE OF MSUNDUZI RIVER BRIDGE (GRIMTHORPE AVE TO BISHOPSTOWE) DISTRICT ROAD D669 KM 2.54
SCHEDULE G: CIDB CONTRACT SKILLS DEVELOPMENT GOAL (CSDG) - SUMMARY
CHAPTER | DESCRIPTION | FROM PAGE | AMOUNT
G | CIDB CONTRACT SKILLS DEVELOPMENT GOAL (CSDG) |  | 51000
TOTAL SCHEDULE G: CIDB CONTRACT SKILLS DEVELOPMENT GOAL |  |  | 51000

## Summary
Province of KwaZulu-Natal | Contract No. ZNB01871/00000/00/PMC/INF/23/T
Department of Transport
THE UPGRADE OF P129 FROM GRAVEL TO BLACKTOP FROM KM 3.00 – KM 6.00 IN THE PIETERMARTIZBURG REGION
C2.3 SUMMARY OF BILL OF QUANTITIES
SCHEDULE | FROM PAGE | AMOUNT
TOTAL SCHEDULE A: ROADWORKS |  | 7170000
TOTAL SCHEDULE B: STRUCTURES |  | 25000
TOTAL SCHEDULE E: EXPANDED PUBLIC WORKS PROGRAMME (EPWP) |  | 1240000
TOTAL SCHEDULE F: SMALL CONTRACTOR DEVELOPMENT |  | 11209582.52
TOTAL SCHEDULE G: CIDB CONTRACT SKILLS DEVELOPMENT GOAL |  | 51000
SUBTOTAL 1 |  | 19695582.52
CONTINGENCIES (10% of Subtotal 1) |  | 1969558.252 | 10%
SUBTOTAL 2 |  | 21665140.772
CONTRACT PRICE ADJUSTMENT AND RISE & FALL (10% of Subtotal 2) |  | 2166514.0772 | 10%
SUBTOTAL 3 |  | 23831654.8492
VAT (15% of Subtotal 3) |  | 3574748.2274 | 15%
TOTAL CARRIED FORWARD TO FORM OF OFFER |  | 27406403.0766
Signed on behalf of the Tenderer: ……………………………………………………. (Signature) Date: ………………………………………………….. Tenderer’s Name: ………………………………………………………………. (Company Name)
DISCLAIMER
Kindly note that the responsibility lies with Tenderer to check the tender document and the tender addenda (if issued) to verify that all the information is correct and all changes have been incorporated as no claims will be entertained in this regard afterwards. Accordingly, we confirm that the hard copies of the original tender document and the tender addenda are to be regarded to contain the correct items and quantities.