## Information
Client Line 1: | Province of KwaZulu-Natal
Client Line 2: | Department of Transport
Contract No | ZNB02271/00000/00/DUR/INF/24/T
Contract Description | THE CONSTRUCTION OF MASS EARTHWORKS, LAYERWORKS, SURFACING AND DRAINAGE ON DISTRICT ROAD 1097 (FROM KM 0+000 TO KM 4+674) IN THE DURBAN REGION

## C1.2
Province of KwaZulu-Natal |  |  |  | Contract No. ZNB02271/00000/00/DUR/INF/24/T
Department of Transport
SCHEDULE A: ROADWORKS | [5 empty] | CHAPTER C1.2
THE CONSTRUCTION OF MASS EARTHWORKS, LAYERWORKS, SURFACING AND DRAINAGE ON DISTRICT ROAD 1097 (FROM KM 0+000 TO KM 4+674) IN THE DURBAN REGION
ITEM NO | DESCRIPTION |  | UNIT | QUANTITY | RATE | AMOUNT
C1.2 | GENERAL REQUIREMENTS AND PAYMENT
C1.2.1 | Environmental Management
C1.2.1.1 | Monitoring of compliance with and reporting on the EMP |  | month | 18
C1.2.1.2 | Dedicated environmental officer (if specified in the Contract Documentation) |  | month | 18
C1.2.2 | Programming and Reporting
C1.2.2.1 | Submission of a Scheme 1 Programme |  | Lump Sum | 1
C1.2.2.2 | Reviewing and updating a Scheme 1 Programme |  | month | 18
C1.2.2.6 | Preparation and submission of all information and reports specified in the Contract Documentation |  | month | 18
C1.2 | TOTAL CARRIED FORWARD
Province of KwaZulu-Natal |  |  |  | Contract No. ZNB02271/00000/00/DUR/INF/24/T
Department of Transport
SCHEDULE A: ROADWORKS | [5 empty] | CHAPTER C1.2
THE CONSTRUCTION OF MASS EARTHWORKS, LAYERWORKS, SURFACING AND DRAINAGE ON DISTRICT ROAD 1097 (FROM KM 0+000 TO KM 4+674) IN THE DURBAN REGION
ITEM NO | DESCRIPTION |  | UNIT | QUANTITY | RATE | AMOUNT
| TOTAL BROUGHT FORWARD | LI
C1.2.5 | Safety
C1.2.5.1 | Health and safety plan |  | Lump Sum | 1
C1.2.5.2 | Implementation of health and safety plan |  | month | 18
C1.2.6 | Work adjacent to properties
C1.2.6.1 | Survey of adjacent properties |  | No | 125
C1.2.6.2 | Preventive and/or mitigation measures |  | Prov Sum | 2750000 | 1 | 2750000
C1.2.6.3 | Handling cost, profit and all other charges in respect of item C1.2.6.2 |  | % | 2750000
C1.2.8 | Dayworks
C1.2.8.1 | Personnel
(a) | Unskilled labourer |  | hour | 180
(c) | Skilled labourer |  | hour | 180
(e) | Foreman |  | hour | 180
C1.2.8.2 | Construction Equipment (specify size and/or model number)
(a) | Motor grader |  | hour | 20
(b) | Vibratory roller |  | hour | 20
(c) | Pneumatic roller |  | hour | 20
(d) | Front end loader backhoe |  | hour | 20
(e) | Tractor loader backhoe |  | hour | 20
(f) | Excavator |  | hour | 20
C1.2.8.4 | Materials
(a) | Procurement of materials |  | Prov Sum | 350000 | 1 | 350000
(b) | Contractor's handling costs, profit and all other charges in respect of item C1.2.8.4(a) |  | % | 350000
PSC1.2.10 | Community Participation
| (a) Cost for Community Participation (PLC and CLO) |  | Prime Cost | 464400 | 1 | 464400
| (b) Handling costs and profit in respect of subitem PSC1.2.10(a) above |  | % | 464400
C1.2 | TOTAL CARRIED TO SUMMARY

## C1.3
Province of KwaZulu-Natal |  |  |  | Contract No. ZNB02271/00000/00/DUR/INF/24/T
Department of Transport
SCHEDULE A: ROADWORKS | [5 empty] | CHAPTER C1.3
THE CONSTRUCTION OF MASS EARTHWORKS, LAYERWORKS, SURFACING AND DRAINAGE ON DISTRICT ROAD 1097 (FROM KM 0+000 TO KM 4+674) IN THE DURBAN REGION
ITEM NO | DESCRIPTION | LI | UNIT | QUANTITY | RATE | AMOUNT
C1.3 | CONTRACTOR'S SITE ESTABLISHMENT AND GENERAL OBLIGATIONS
C1.3.1 | The Contractor's general obligations
C1.3.1.1 | Fixed obligations |  | Lump Sum | 1
C1.3.1.2 | Value-related obligations |  | Lump Sum | 1
PSC1.3.1.3 | Time-related obligations |  | month | 18
C1.3.2 | Contract sign boards |  | m2 | 12
C1.3 | TOTAL CARRIED FORWARD TO SUMMARY

## C1.4
Province of KwaZulu-Natal |  |  |  | Contract No. ZNB02271/00000/00/DUR/INF/24/T
Department of Transport
SCHEDULE A: ROADWORKS | [5 empty] | CHAPTER C1.4
THE CONSTRUCTION OF MASS EARTHWORKS, LAYERWORKS, SURFACING AND DRAINAGE ON DISTRICT ROAD 1097 (FROM KM 0+000 TO KM 4+674) IN THE DURBAN REGION
ITEM NO | DESCRIPTION | LI | UNIT | QUANTITY | RATE | AMOUNT
C1.4 | FACILITIES FOR THE ENGINEER
C1.4.1 | Site accommodation
C1.4.1.1 | Offices and conference room |  | m2 | 90
C1.4.1.2 | Laboratories |  | m2 | 60
C1.4.1.3 | Open concrete working floors and verandas |  | m2 | 30
C1.4.1.4 | Roofs over open concrete working floors and verandas |  | m2 | 35
C1.4.1.6 | Car ports |  | No | 8
C1.4.1.7 | Ablution unit (equipment as specified) |  | No | 4
C1.4.1.8 | Change room with a shower |  | No | 2
C1.4.1.9 | Kithcen unit (equipment as specified) |  | No | 2
C1.4.2 | Items measured by area
C1.4.2.6 | Roller blinds, opaque type |  | m2 | 32
C1.4.2.8 | Notice boards |  | m2 | 4
C1.4.2.9 | White boards |  | m2 | 8
C1.4 | TOTAL CARRIED FORWARD
Province of KwaZulu-Natal |  |  |  | Contract No. ZNB02271/00000/00/DUR/INF/24/T
Department of Transport
SCHEDULE A: ROADWORKS | [5 empty] | CHAPTER C1.4
THE CONSTRUCTION OF MASS EARTHWORKS, LAYERWORKS, SURFACING AND DRAINAGE ON DISTRICT ROAD 1097 (FROM KM 0+000 TO KM 4+674) IN THE DURBAN REGION
ITEM NO | DESCRIPTION | LI | UNIT | QUANTITY | RATE | AMOUNT
TOTAL BROUGHT FORWARD
C1.4.3 | Items measured by number
C1.4.3.2 | Office chair |  | No | 20
C1.4.3.4 | Laboratory high chair |  | No | 4
C1.4.3.5 | Office desk with 3 drawers (at least one lockable drawer) |  | No | 8
C1.4.3.8 | Conference table |  | No | 1
C1.4.3.10 | Filling cabinet |  | No | 4
C1.4.3.11 | General purpose steel cabinet with shelves |  | No | 4
C1.4.3.13 | 220/250 volt power outlet plug point |  | No | 10
C1.4.3.15 | Single 1 500 mm, 58 watt fluorescent tube ceilling light |  | No | 8
C1.4.3.19 | Wash-hand basin |  | No | 2
C1.4.3.23 | Fire extinguisher 9,0 kg, dry powder type |  | No | 4
C1.4.3.24 | Air-conditioning unit |  | No | 8
C1.4.3.27 | Waste paper basket |  | No | 10
C1.4.3.28 | UPS / Voltage stabiliser |  | No | 4
C1.4.3.29 | A3 / A4 colour printer, copier, scanner |  | No | 3
C1.4.3.31 | Rain gauge |  | No | 1
C1.4.3.32 | Minimum / maximum atmospheric temperature guage |  | No | 1
C1.4.3.36 | Measuring wheel |  | No | 3
C1.4.3.37 | First aid kit |  | No | 2
C1.4.4 | Prime cost items
C1.4.4.5 | The provision of internet conectivity and WIFI data for Engineer's site staff |  | PC Sum | 36000 | 1 | 36000
C1.4.4.6 | Handling cost and profit in respect of item C1.4.4.5 |  | % | 36000
C1.4.4.7 | The provision of paper and ink for a combination colour printer/copier/scanner |  | PC Sum | 27000 | 1 | 27000
C1.4.4.8 | Handling cost and profit in respect of item C1.4.4.7 |  | % | 27000
C1.4 | TOTAL CARRIED FORWARD
Province of KwaZulu-Natal |  |  |  | Contract No. ZNB02271/00000/00/DUR/INF/24/T
Department of Transport
SCHEDULE A: ROADWORKS | [5 empty] | 0
THE CONSTRUCTION OF MASS EARTHWORKS, LAYERWORKS, SURFACING AND DRAINAGE ON DISTRICT ROAD 1097 (FROM KM 0+000 TO KM 4+674) IN THE DURBAN REGION
ITEM NO | DESCRIPTION | LI | UNIT | QUANTITY | RATE | AMOUNT
TOTAL BROUGHT FORWARD
C1.4.5 | Services at site offices, laboratories and site accommodation
C1.4.5.1 | Fixed costs |  | Lump Sum | 1
C1.4.5.2 | Running costs |  | month | 18
C1.4.8 | Site security measures for the Engineer's facilities
C1.4.8.1 | Supply and installation of all required security measures at the Engineer's site offices and laboratories |  | Lump Sum | 1
C1.4.8.2 | Provision of security gaurds / watchmen and an armed response service at the Engineer's site offices and laboratories |  | month | 18
C1.4 | TOTAL CARRIED FORWARD TO SUMMARY

## C1.5
Province of KwaZulu-Natal |  |  |  | Contract No. ZNB02271/00000/00/DUR/INF/24/T
Department of Transport
SCHEDULE A: ROADWORKS | [5 empty] | CHAPTER C1.5
THE CONSTRUCTION OF MASS EARTHWORKS, LAYERWORKS, SURFACING AND DRAINAGE ON DISTRICT ROAD 1097 (FROM KM 0+000 TO KM 4+674) IN THE DURBAN REGION
ITEM NO | DESCRIPTION | LI | UNIT | QUANTITY | RATE | AMOUNT
C1.5 | ACCOMMODATION OF TRAFFIC
C1.5.2 | Accommodation of vehicular traffic |  | month | 18
C1.5.4 | Construction of temporary deviations
| The applicable payment items required for the construction of temporary deviations shall be taken from the relevant chapters and sections in Chapter 1, 3, 5, 9 and 10 and inserted into the Pricing Schedule here. Each payment item for the construction of temporary deviations shall be preceded by the main payment item number C1.5.4 / followed by the payment number for the applicable payment item |  | Unit must relate to relevant pay item from the relevant chapters and sections
C1.5.4 / C1.6.1.1 | Clearing with machines and some hand labour where necessary | LI | ha | 2
C1.5.4 / C1.6.2.1 | Clearing with hand labour only when labour enhanced work is specified | LI | ha | 2
C1.5.4 / C1.7.2.1 | Hauling material for use in the Works and off-loading it on the site of the Works:
(a) | Soil, gravel, crushed stone and pavement layer material |  | m3 - km | 10000
(b) | Boulders and hard material |  | m3 - km | 1000
C1.5.4 / C1.7.2.2 | Hauling material to spoil and off-loading it at a designated spoil or stockpile are:
(a) | Cleared and grubbed material (organic matter and all other unsuitable or waste material) |  | m3 - km | 15000
(b) | Soil and gravel material |  | m3 - km | 40000
(c) | Boulders, hard material and concrete |  | m3 - km | 25000
C1.5.4 / C3.2.1.2 | Excavating soft material 0 m to 1,5 m below the surface level using labour enhanced construction methods, or instructed by hand under Clause A3.2.7.2d): | LI | m3 | 150
C1.5.4 / C3.2.1.4 | Extra over sub-item C3.2.1.1 for excavation in hard or boulder material, irrespective of depth |  | m3 | 30
C1.5 | TOTAL CARRIED FORWARD
Province of KwaZulu-Natal |  |  |  | Contract No. ZNB02271/00000/00/DUR/INF/24/T
Department of Transport
SCHEDULE A: ROADWORKS | [5 empty] | CHAPTER C1.5
THE CONSTRUCTION OF MASS EARTHWORKS, LAYERWORKS, SURFACING AND DRAINAGE ON DISTRICT ROAD 1097 (FROM KM 0+000 TO KM 4+674) IN THE DURBAN REGION
ITEM NO | DESCRIPTION | LI | UNIT | QUANTITY | RATE | AMOUNT
TOTAL BROUGHT FORWARD
C1.5.4 / C3.2.2 | Backfilling:
C1.5.4 / C3.2.2.1 | Using the excavated material |  | m3 | 100
C1.5.4 / C3.2.3 | Concrete pipe culverts:
C1.5.4 / C3.2.3.3 | On Class C bedding (type and diameter indicated)
(b) | 600mm dia. Class 100D |  | m | 50
C1.5.4 / C5.1.1 | Roadbed construction and compaction
C1.5.4 / C5.1.1.1 | Compaction of in-situ material to 90% of MDD |  | m3 | 600
C1.5.4 / C5.2.2 | Fill construction
C1.5.4 / C5.2.2.1 | Normal fill material in compacted layer thicknesses of 200 mm and less:
(a) | Compacted to 90% MDD |  | m3 | 1600
C1.5.5 | Maintenance of temporary deviations
C1.5.5.1 | Grass cutting |  | ha | 2
C1.5.5.2 | Drain cleaning |  | km | 2
C1.5.5.3 | Cleaning out culverts |  | m3 | 30
C1.5.5.4 | Collection of rubbish / litter |  | km | 2
C1.5.5.8 | Replacement of damaged guardrails |  | m | 100
C1.5.5.9 | Grading of temporary deviations and existing roads used as detours |  | km | 3
C1.5.5.10 | Watering of temporary deviations and existing roads used as detours |  | kl | 15000
C1.5.5.11 | Other road maintenance work ordered by the Engineer |  | Prov Sum | 50000 | 1 | 50000
C1.5.5.12 | Handling cost, profit and all other charges in respect of item C1.5.5.12 |  | % | 50000
C1.5.6 | Removal of temporary deviations |  | km | 3
C1.5 | TOTAL CARRIED FORWARD
Province of KwaZulu-Natal |  |  |  | Contract No. ZNB02271/00000/00/DUR/INF/24/T
Department of Transport
SCHEDULE A: ROADWORKS | [5 empty] | CHAPTER C1.5
THE CONSTRUCTION OF MASS EARTHWORKS, LAYERWORKS, SURFACING AND DRAINAGE ON DISTRICT ROAD 1097 (FROM KM 0+000 TO KM 4+674) IN THE DURBAN REGION
ITEM NO | DESCRIPTION | LI | UNIT | QUANTITY | RATE | AMOUNT
TOTAL BROUGHT FORWARD
C1.5.7 | Temporary traffic control facilities
C1.5.7.1 | Delineators including mounting bases and ballast:
(a) | Single sided, reversible left or right (800 x 200mm) |  | No | 200
(b) | Double sided, reversible left or right (800 x 200mm) |  | No | 200
C1.5.7.2 | Traffic cones, minimum height 750 mm |  | No | 100
C1.5.7.3 | Flagmen | LI | man-shift | 3744
C1.5.7.5 | Provision of illuminated traffic signs
(c) | Illuminated road sign - R & TR series (diamter indicated) |  | No | 31
(d) | Illuminated road sign - TW series (length of sides indicated) |  | No | 27
C1.5.8 | Traffic safety officer |  | Man-month | 18
C1.5.9 | Traffic safety vehicle |  | month | 18
C1.5.11 | Provision of safety equipment for visitors
C1.5.11.1 | Provision of reflective safety vests for visitors |  | No | 10
C1.5.12 | Additional traffic accommodation facilities ordered by the Engineer:
C1.5.12.1 | Provision of additional traffic accomodation facilities |  | Prov Sum | 50000 | 1 | 50000
C1.5.12.2 | Handling cost, profit and all other charges in respect of item C1.5.12.1 |  | % | 50000
C1.5 | TOTAL CARRIED FORWARD

## C1.6
Province of KwaZulu-Natal |  |  |  | Contract No. ZNB02271/00000/00/DUR/INF/24/T
Department of Transport
SCHEDULE A: ROADWORKS | [5 empty] | CHAPTER C1.6
THE CONSTRUCTION OF MASS EARTHWORKS, LAYERWORKS, SURFACING AND DRAINAGE ON DISTRICT ROAD 1097 (FROM KM 0+000 TO KM 4+674) IN THE DURBAN REGION
ITEM NO | DESCRIPTION | LI | UNIT | QUANTITY | RATE | AMOUNT
C1.6 | CLEARING AND GRUBBING
C1.6.1 | Clearing
C1.6.1.1 | Clearing with machines and some hand labour where necessary | LI | ha | 12.3
C1.6.2 | Grubbing
C1.6.2.1 | Clearing with machines and some hand labour where necessary | LI | ha | 12.3
C1.6.3 | Removal and grubbing of large trees and tree stumps:
C1.6.3.1 | Girth equal to or exceeding 1,0 m up to and including 2,0 m |  | No | 20
C1.6.3.2 | Girth exceeding 2,0 m up to and including 3,0 m |  | No | 10
C1.6.3.3 | Girth exceeding 3,0 m |  | No | 5
C1.6.3.4 | Removal of trees in forests and plantations |  | ha | 1
C1.6.4 | Removal of buildings and structures
C1.6.4.1 | (Identify type and location of each building or structure with a separate sub-item) |  | Lump Sum | 1
C1.6.8 | Conservation of vegetation:
C1.6.8.2 | Removal, storage and maintenance of shrubs |  | No | 30
C1.6.8.3 | Removal, storage and maintenance of trees, girth up to and including 1,0 m |  | No | 30
C1.6.8.4 | Removal, storage and maintenance of trees, girth exceeding 1,0 m up to and including 2,0 m |  | No | 10
C1.6.8.5 | Removal, storage and maintenance of trees, girth exceeding 2,0 m up to and including 3,0 m |  | No | 5
C1.6.8.6 | Removal, storage and maintenance of trees, girth exceeding 3,0 m |  | No | 5
C1.6.9 | Conservation of topsoil
C1.6.9.1 | Stockpilling topsoil |  | m3 | 50
C1.6.10 | Disposal of hazardous waste material:
C1.6.10.1 | Disposal of hazardous waste material at an approved hazardous waste material facility |  | Prov Sum | 100000 | 1 | 100000
C1.6.10.2 | Handling cost, profit and all other charges in respect of item C1.6.10.1 |  | % | 100000
C1.6 | TOTAL CARRIED FORWARD TO SUMMARY

## C1.7
Province of KwaZulu-Natal |  |  |  | Contract No. ZNB02271/00000/00/DUR/INF/24/T
Department of Transport
SCHEDULE A: ROADWORKS | [5 empty] | CHAPTER C1.7
THE CONSTRUCTION OF MASS EARTHWORKS, LAYERWORKS, SURFACING AND DRAINAGE ON DISTRICT ROAD 1097 (FROM KM 0+000 TO KM 4+674) IN THE DURBAN REGION
ITEM NO | DESCRIPTION | LI | UNIT | QUANTITY | RATE | AMOUNT
C1.7 | LOADING AND HAULING
C1.7.1 | Loading
C1.7.1.1 | Loading from stockpile using machines and some hand loabour where necessary |  | m3 | 27609
C1.7.2 | Hauling
C1.7.2.1 | Hauling material for use in the Works and off-loading it on the site of the Works:
(a) | Soil, gravel, crushed stone and pavement layer material |  | m3 - km | 44077
(b) | Boulders and hard material |  | m3 - km | 1543
C1.7.2.2 | Hauling material to spoil and off-loading it at a designated spoil or stockpile are:
(a) | Cleared and grubbed material (organic matter and all other unsuitable or waste material) |  | m3 - km | 25000
(b) | Soil and gravel material |  | m3 - km | 151850
(c) | Boulders, hard material and concrete |  | m3 - km | 30370
C1.7 | TOTAL CARRIED FORWARD TO SUMMARY

## C2.1
Province of KwaZulu-Natal |  |  |  | Contract No. ZNB02271/00000/00/DUR/INF/24/T
Department of Transport
SCHEDULE A: ROADWORKS | [5 empty] | CHAPTER C2.1
THE CONSTRUCTION OF MASS EARTHWORKS, LAYERWORKS, SURFACING AND DRAINAGE ON DISTRICT ROAD 1097 (FROM KM 0+000 TO KM 4+674) IN THE DURBAN REGION
ITEM NO | DESCRIPTION | LI | UNIT | QUANTITY | RATE | AMOUNT
C2.1 | GENERAL REQUIREMENTS AND TRENCHING FOR SERVICES
C2.1.1 | Location,Identification and relocation of existing services
C2.1.1.1 | Contractors's obligations |  | Lump Sum | 1
C2.1.1.4 | Permanent services relocation or protection work by Contractor | LI | PC Sum | 500000 | 1 | 500000
PSC2.1.1.3 | Handling costs and profit in respect of item C2.1.1.4 above |  | % | 500000
C2.1.2 | Existing services, detention and verification
C2.1.2.3 | Survey to verify existing service positions | LI | PC Sum | 85000 | 1 | 85000
C2.1.2.4 | Handling costs and profit in respect of item C2.1.2.3 above |  | % | 85000
C2.1.2.5 | Using hand excavation to locate,expose and verify services | LI | m³ | 100
C2.1.3 | Obtaining construction or work permits |  | Lump Sum | 1
C2.1 | TOTAL CARRIED FORWARD TO SUMMARY

## C2.2
Province of KwaZulu-Natal |  |  |  | Contract No. ZNB02271/00000/00/DUR/INF/24/T
Department of Transport
SCHEDULE A: ROADWORKS | [5 empty] | CHAPTER C2.2
THE CONSTRUCTION OF MASS EARTHWORKS, LAYERWORKS, SURFACING AND DRAINAGE ON DISTRICT ROAD 1097 (FROM KM 0+000 TO KM 4+674) IN THE DURBAN REGION
ITEM NO | DESCRIPTION | LI | UNIT | QUANTITY | RATE | AMOUNT
C2.2 | DRY SERVICES
C2.1.1 | Supply, lay and prove ducts
C2.2.1.1 | State for each duct the material type, class, joint type etc. (Unplasticised PVC Pipes):)
(a) | State diameter (100 mm diameter (OD)) | LI | m | 460
C2.2.6 | Duct accessories (markers, marking, draw wires and end caps etc.)
C2.2.6.1 | Duct markers (state type) | LI | No | 65
C2.2 | TOTAL CARRIED FORWARD TO SUMMARY

## C3.2
Province of KwaZulu-Natal |  |  |  | Contract No. ZNB02271/00000/00/DUR/INF/24/T
Department of Transport
SCHEDULE A: ROADWORKS | [5 empty] | CHAPTER C3.2
THE CONSTRUCTION OF MASS EARTHWORKS, LAYERWORKS, SURFACING AND DRAINAGE ON DISTRICT ROAD 1097 (FROM KM 0+000 TO KM 4+674) IN THE DURBAN REGION
ITEM NO | DESCRIPTION | LI | UNIT | QUANTITY | RATE | AMOUNT
C3.2 | CULVERTS
C3.2.1 | Excavation for culvert structures:
C3.2.1.1 | Excavating in all material situated within the following depth ranges below the surface level:
(a) | 0m to 1.5m |  | m3 | 1272
(b) | Exceeding 1.5m and up to 3.0m |  | m3 | 382
C3.2.1.4 | Extra over sub-item C3.2.1.1 for excavation in hard or boulder material, irrespective of depth |  | m3 | 254
C3.2.2 | Backfilling:
C3.2.2.1 | Using the excavated material | LI | m3 | 480
C3.2.2.2 | Using imported selected material:
(a) | From commercial sources | LI | m3 | 792
C3.2.3 | Concrete pipe culverts:
| (i) On Class C bedding (75D, 600mm) |  | m | 66
| (ii) On Class C bedding (75D , 900mm) |  | m | 446
C3.2.8 | Concrete backfill or encasement for culverts (20MPa) | LI | m3 | 40
C3.2.13 | Removing and re-laying existing culverts:
C3.2.13.1 | Removing and stacking existing culverts for re-use
i | Class 75D
i) | 450mm diameter |  | m | 20
ii) | 600mm diameter |  | m | 20
iii) | 900mm diameter |  | m | 20
C3.2 | TOTAL CARRIED FORWARD

## C4.1
Province of KwaZulu-Natal |  |  |  | Contract No. ZNB02271/00000/00/DUR/INF/24/T
Department of Transport
SCHEDULE A: ROADWORKS | [5 empty] | CHAPTER C4.1.1
THE CONSTRUCTION OF MASS EARTHWORKS, LAYERWORKS, SURFACING AND DRAINAGE ON DISTRICT ROAD 1097 (FROM KM 0+000 TO KM 4+674) IN THE DURBAN REGION
ITEM NO | DESCRIPTION | LI | UNIT | QUANTITY | RATE | AMOUNT
C4.1 | BORROW MATERIALS
C4.1.1 | Compiling and implementing M&U plans
C4.1.1.1 | For borrow pits (list all borrow pits separately) |  | No | 1
C4.1.2 | Additional material investigations during the supplementary exploration
C4.1.2.1 | Cost of additional trial pits and/or drilling and laboratory testing |  | Prov Sum | 10000 | 1 | 10000
C4.1.2.2 | Handling costs and profit in respect of item C4.1.2.1 |  | % | 10000
C4.1.4 | Removing of the overburden
C4.1.4.1 | In borrow pits |  | m3 | 100
C4.1.4.2 | In quarries:
(a) | Soft material |  | m3 | 100
C4.1.5 | Excavating of materials in the borrow pits and quarries, material obtained from
C4.1.5.1 | Soft excavation |  | m3 | 2000
C4.1.5.2 | Boulder excavation class A |  | m3 | 1000
C4.1.5.3 | Boulder excavation class B |  | m3 | 1000
C4.1.5.4 | Hard excavation (other than by blasting) |  | m3 | 800
C4.1.5.5 | Hard excavation (by blasting) |  | m3 | 400
C4.1.15.2 | Finishing of the borrow pit and quarry areas, and the stockpile sites using labour enhanced methods of construction:
(a) | Borrow pits (list all borrow pits separately) |  | ha | 1
(b) | Quarries (list all quarries separately) |  | ha | 1
C4.1 | TOTAL CARRIED FORWARD TO SUMMARY

## C4.2
Province of KwaZulu-Natal |  |  |  | Contract No. ZNB02271/00000/00/DUR/INF/24/T
Department of Transport
SCHEDULE A: ROADWORKS | [5 empty] | CHAPTER C4.2
THE CONSTRUCTION OF MASS EARTHWORKS, LAYERWORKS, SURFACING AND DRAINAGE ON DISTRICT ROAD 1097 (FROM KM 0+000 TO KM 4+674) IN THE DURBAN REGION
ITEM NO | DESCRIPTION | LI | UNIT | QUANTITY | RATE | AMOUNT
C4.2 | CUT MATERIALS
C4.2.1 | Compiling and implementing M&U plans for the cuttings
C4.2.1.1 | Cuttings exceeding 5 000 m3 up to 10 000 m3 |  | No | 1
C4.2.1.2 | Cuttings exceeding 10 000 m3 up to 20 000 m3 |  | No | 1
C4.2.2 | Additional material investigations during the supplementary exploration
C4.2.2.1 | Cost of additional trial pits and/or drilling and laboratory testing |  | Prov Sum | 20000 | 1 | 20000
C4.2.2.2 | Handling costs and profit in respect of item |  | % | 20000
C4.2.3 | Excavating of materials in cuttings, material obtained from
C4.2.3.1 | Soft excavation |  | m3 | 28980
C4.2.3.2 | Boulder excavation class A |  | m3 | 1000
C4.2.3.3 | Boulder excavation class B |  | m3 | 1000
C4.2.3.4 | Hard excavation (other than by blasting) |  | m3 | 500
C4.2.3.5 | Hard excavation (by blasting) |  | m3 | 200
C4.2.7 | Removal of unsuitable stable cut material to spoil
C4.2.7.1 | In layer thicknesses of 200 mm and less |  | m3 | 1500
C4.2.7.2 | In layer thicknesses exceeding 200 mm |  | m3 | 450
C4.2.8 | Excavate material to spoil in sites designated by the Employer, material obtained from
C4.2.8.1 | Soft excavation, overburden and unsuitable material |  | m3 | 8424
C4.2.8.2 | Boulder excavation class A |  | m3 | 550
C4.2.8.3 | Boulder excavation class B |  | m3 | 500
C4.2.8.4 | Hard excavation (other than by blasting) |  | m3 | 400
C4.2.8.5 | Hard excavation (by blasting) |  | m3 | 80
C4.2.10 | Backfilling of the unavoidable overbreak in hard and boulder excavation
C4.2.10.1 | Compliant gravel material |  | m3 | 200
C4.2.12 | Finishing the side slopes
C4.2.12.1 | Cuttings:
(a) | In soft material |  | m2 | 6499
(b) | In boulder material class A and B |  | m2 | 100
(c) | In hard material |  | m2 | 100
(d) | In soft material using labour enhanced methods of construction | LI | m2 | 250
C4.2 | TOTAL CARRIED FORWARD TO SUMMARY

## C4.4
Province of KwaZulu-Natal |  |  |  | Contract No. ZNB02271/00000/00/DUR/INF/24/T
Department of Transport
SCHEDULE A: ROADWORKS | [5 empty] | CHAPTER C4.4
THE CONSTRUCTION OF MASS EARTHWORKS, LAYERWORKS, SURFACING AND DRAINAGE ON DISTRICT ROAD 1097 (FROM KM 0+000 TO KM 4+674) IN THE DURBAN REGION
ITEM NO | DESCRIPTION | LI | UNIT | QUANTITY | RATE | AMOUNT
C4.4 | COMMERCIAL MATERIALS
C4.4.2 | Commercial materials identified by the Contractor from commercial, private or other non-commercial suppliers
C4.4.2.1 | Pavement layer material:
(f) | Type G5A material |  | m3 | 12340
(j) | Type G7 Material |  | m3 | 1400
(k) | Type G8 material |  | m3 | 7713
(l) | Type G9 Material |  | m3 | 4628
C4.4.1.5 | Fill material in the earthworks |  | m3 | 640
C4.4.4 | Cementitious stabilising agents
C4.4.4.1 | Cement |  | t | 530
C4.4.4.2 | Road lime |  | t | 125
C4.4.7 | Sampling and material testing by a commercial laboratory for the stabilisation designs
C4.4.7.1 | Cost of sampling and material testing |  | Prov Sum | 100000 | 1 | 100000
C4.4.7.2 | Handling cost and profit in respect of item C4.4.7.1 |  | % | 100000
C4.4 | TOTAL CARRIED FORWARD TO SUMMARY

## C4.5
Province of KwaZulu-Natal |  |  |  | Contract No. ZNB02271/00000/00/DUR/INF/24/T
Department of Transport
SCHEDULE A: ROADWORKS | [5 empty] | CHAPTER C4.5
THE CONSTRUCTION OF MASS EARTHWORKS, LAYERWORKS, SURFACING AND DRAINAGE ON DISTRICT ROAD 1097 (FROM KM 0+000 TO KM 4+674) IN THE DURBAN REGION
ITEM NO | DESCRIPTION | LI | UNIT | QUANTITY | RATE | AMOUNT
C4.5 | ALTERNATIVE MATERIALS
C4.5.1 | Additional material investigations
C4.5.1.1 | Cost of sampling and laboratory testing |  | Prov Sum | 20000 | 1 | 20000
C4.5.1.2 | Handling cost and profit in respect of item C4.5.1.1 |  | % | 20000
C4.5.3 | Cost to procure alternative materials identified by the Employer
C4.5.3.1 | Cost of procuring |  | Prov Sum | 6973120 | 1 | 6973120
C4.5.3.2 | Handling cost and profit in respect of item C4.5.3.1 |  | % | 6973120
C4.5 | TOTAL CARRIED FORWARD TO SUMMARY

## C5.1
Province of KwaZulu-Natal |  |  |  | Contract No. ZNB02271/00000/00/DUR/INF/24/T
Department of Transport
SCHEDULE A: ROADWORKS | [5 empty] | CHAPTER C5.1
THE CONSTRUCTION OF MASS EARTHWORKS, LAYERWORKS, SURFACING AND DRAINAGE ON DISTRICT ROAD 1097 (FROM KM 0+000 TO KM 4+674) IN THE DURBAN REGION
ITEM NO | DESCRIPTION | LI | UNIT | QUANTITY | RATE | AMOUNT
C5.1 | ROADBED
C5.1.1 | Roadbed construction and compaction
C5.1.1.1 | Compaction of in-situ material to 90% of MDD |  | m3 | 4628
C5.1.1.3 | Compaction of imported material to 90% of MDD |  | m3 | 4628
C5.1.4 | Removal of unsuitable material to spoil
C5.1.4.1 | In layer thicknesses of 200mm and less
(a) | Stable material |  | m3 | 926
(b) | Unstable material |  | m3 | 926
C5.1.5 | In-situ treatment of roadbed in hard material
C5.1.5.1 | In-situ treatment by ripping |  | m3 | 4628
C5.1 | TOTAL CARRIED FORWARD TO SUMMARY

## C5.2
Province of KwaZulu-Natal |  |  |  | Contract No. ZNB02271/00000/00/DUR/INF/24/T
Department of Transport
SCHEDULE A: ROADWORKS | [5 empty] | CHAPTER C5.2
THE CONSTRUCTION OF MASS EARTHWORKS, LAYERWORKS, SURFACING AND DRAINAGE ON DISTRICT ROAD 1097 (FROM KM 0+000 TO KM 4+674) IN THE DURBAN REGION
ITEM NO | DESCRIPTION | LI | UNIT | QUANTITY | RATE | AMOUNT
C5.2 | FILL
C5.2.1 | Compilling and implementing M&U plans
C5.2.1.1 | For fills more than 10 000 m3 (list all fills seperately) |  | No | 1
C5.2.1.2 | For fills 1,0 km in length when less than 10 000 m3 (list all fills seperately) |  | No | 1
C5.2.2 | Fill construction
C5.2.2.1 | Normal fill material in compacted layer thicknesses of 200 mm and less:
(b) | Compacted to 93% MDD |  | m3 | 9360
C5.2.5 | Fill in sidewalk
C5.2.5.2 | Fill material in sidewalk compacted to 93% of MDD using labour enhanced methods of construction and light hand equipment | LI | m3 | 1380
C5.2.8.3 | By pad foor vibratory roller |  | m2-pass | 2000
C5.2 | TOTAL CARRIED FORWARD TO SUMMARY

## C5.3
Province of KwaZulu-Natal |  |  |  | Contract No. ZNB02271/00000/00/DUR/INF/24/T
Department of Transport
SCHEDULE A: ROADWORKS | [5 empty] | CHAPTER C5.3
THE CONSTRUCTION OF MASS EARTHWORKS, LAYERWORKS, SURFACING AND DRAINAGE ON DISTRICT ROAD 1097 (FROM KM 0+000 TO KM 4+674) IN THE DURBAN REGION
ITEM NO | DESCRIPTION | LI | UNIT | QUANTITY | RATE | AMOUNT
C5.3 | ROAD PAVEMENT LAYERS
C5.3.1 | Compilling and implementing M&U plans for the construction of all the pavement layers |  | No | 1
C5.3.2 | Construction of pavement layers
PSC5.3.2.1 | Construction of layers using conventional construction methods:
(a) | Lower selected subgrade layer (305mm thick G9) compacted to 93% of MDD |  | m3 | 9409
(c) | Upper selected subgrade layer (250mm thick G8) compacted to 93% of MDD |  | m3 | 7713
(n) | Gravel base layer (chemically stabilised), (200mm thick C4) compacted to 97% of MDD |  | m3 | 5609
(q) | G5A crushed rock/boulder subbase layer (200mm thick) compacted to 97% of MDD |  | m3 | 6170
(t) | G5A crushed rock/boulder base layer (chemically stabilised) (125mm NME) compacted to 102% of MDD |  | m3 | 562
C5.3.9 | Construction of a trial section
C5.3.9.1 | Construction of a trial section using conventional methods of construction
(a) | Stabilised gravel layer (200mm thick C4) trial section |  | m3 | 120
(f) | Stabilised G5A layer (125mm thick NME) trial section |  | m3 | 75
C5.3 | TOTAL CARRIED FORWARD TO SUMMARY

## C5.4
Province of KwaZulu-Natal |  |  |  | Contract No. ZNB02271/00000/00/DUR/INF/24/T
Department of Transport
SCHEDULE A: ROADWORKS | [5 empty] | CHAPTER C5.4
THE CONSTRUCTION OF MASS EARTHWORKS, LAYERWORKS, SURFACING AND DRAINAGE ON DISTRICT ROAD 1097 (FROM KM 0+000 TO KM 4+674) IN THE DURBAN REGION
ITEM NO | DESCRIPTION | LI | UNIT | QUANTITY | RATE | AMOUNT
C5.4 | STABILISATION
C5.4.2 | Chemical stabilisation
C5.4.2.1 | Chemical stabilisation (200mm thick) of pavement layers (G5A chemically stabilized to C4) |  | m3 | 5609
C5.4.5 | Cementitious stabilisation agents for pavement layers
C5.4.5.1 | Addition of cementitious stabilisation agents (Portland) for pavement layers
(a) | Cement (for pavement layer) |  | t | 530
C5.4.8 | Bituminous stabilisation agent (specify agents seperately)
C5.4.8.1 | 60% anionic emulsion |  | ℓ | 17984
C5.4 | TOTAL CARRIED FORWARD TO SUMMARY

## C8.1
Province of KwaZulu-Natal |  |  |  | Contract No. ZNB02271/00000/00/DUR/INF/24/T
Department of Transport
SCHEDULE A: ROADWORKS | [5 empty] | CHAPTER C8.1
THE CONSTRUCTION OF MASS EARTHWORKS, LAYERWORKS, SURFACING AND DRAINAGE ON DISTRICT ROAD 1097 (FROM KM 0+000 TO KM 4+674) IN THE DURBAN REGION
ITEM NO | DESCRIPTION | LI | UNIT | QUANTITY | RATE | AMOUNT
C8.1 | PRIME COAT
C8.1.1.2 | MC - 30 cut-back bitumen | LI | ℓ | 21594
C8.1.1.3 | Inveted bitumen emulsion | LI | ℓ | 16967
C8.1.2 | Aggregate for blinding
C8.1.2.2 | Crusher sand | LI | m3 | 157
C8.1.3 | Extra over item C8.1.1 for applying the prime coat accessible only to hand-held or light equipment |  | ℓ | 2584
C8.1 | TOTAL CARRIED FORWARD TO SUMMARY

## C9.1
Province of KwaZulu-Natal |  |  |  | Contract No. ZNB02271/00000/00/DUR/INF/24/T
Department of Transport
SCHEDULE A: ROADWORKS | [5 empty] | CHAPTER C9.1
THE CONSTRUCTION OF MASS EARTHWORKS, LAYERWORKS, SURFACING AND DRAINAGE ON DISTRICT ROAD 1097 (FROM KM 0+000 TO KM 4+674) IN THE DURBAN REGION
ITEM NO | DESCRIPTION | LI | UNIT | QUANTITY | RATE | AMOUNT
C9.1 | ASPHALT LAYERS
C9.1.1 | Asphalt mix designs
C9.9.1.2 | Sand skeletal mixes:
(a) | Continuously graded base or surfacing (A-E2 and level 2) |  | Lump Sum | 1
C9.1.3.1 | Stable grade 30% net bitumen emulsion as specified. Applied with a calibrated distributer |  | ℓ | 11568
C9.1.3.3 | Applied by hand using brushes on all exposed transverse and longitudinal construction joints |  | ℓ | 200
C9.1.5 | Asphalt surfacing
C9.1.5.1 | New construction
(e) | Sand skeletal mix – continuously graded as defined (40mm thickness, (Medium Grade) using A-E2 modified binder maximum aggregate size 14.0mm) |  | m2 | 3300
C9.1.10 | Variation rates
C9.1.10.1 | Bitumen (state type) |  | t | 10
C9.1.13 | Coring of asphalt layers
C9.1.13.1 | 100 mm diameter |  | No | 100
C9.1 | TOTAL CARRIED FORWARD TO SUMMARY

## C10.1
Province of KwaZulu-Natal |  |  |  | Contract No. ZNB02271/00000/00/DUR/INF/24/T
Department of Transport
SCHEDULE A: ROADWORKS | [5 empty] | CHAPTER C10.1
THE CONSTRUCTION OF MASS EARTHWORKS, LAYERWORKS, SURFACING AND DRAINAGE ON DISTRICT ROAD 1097 (FROM KM 0+000 TO KM 4+674) IN THE DURBAN REGION
ITEM NO | DESCRIPTION | LI | UNIT | QUANTITY | RATE | AMOUNT
C10.1 | GENERAL REQUIREMENTS FOR SURFACE TREATMENTS
C10.1.3 | Multiple stone seals including a cover spray, if specified using:
C10.1.3.1 | 20 mm and 10 mm aggregate (state grade of aggregate and type of binder to be used for each layer) |  | m² | 30849
C10.1.4.1 | Re-establishment of sealing team after embargo period |  | lump sum | 1
C10.1.4.2 | Extra-over for sealing during the specified embargo period (Multiple stone seals, grade 1 aggregate with type S-R1 non-homogenous modified binder tack coat and type S-E1 homogenous modified binder penetration layer) |  | m² | 30849
C10.1.9 | Bituminous binder variations:
C10.1.9.4 | Cationic Spray-grade emulsion (30% cationic spray grade emulsion) |  | ℓ | 4399
C10.1.9.6 | Non-homogeneous modified binder (class S-R1) |  | ℓ | 15456
C10.1.9.7 | Homogeneous modified binder (S-E1 binder) hot applied |  | ℓ | 38254
C10.1.9.11 | Precoating fluid (state type) |  | ℓ | 4399
C10.1.10 | Aggregate variation (state grade):
C10.1.10.3 | 10 mm aggregate |  | m3 | 126
C10.1.10.5 | 20 mm aggregate |  | m3 | 220
C10.1.11 | Application of cover spray:
C10.1.11.2 | 60 % Diluted Anionic stable-grade emulsion (indicate dilution in 50% emulsion/50% water) |  | ℓ | 21739
C10.1.14 | Precoating of aggregate using a frontend loader
C10.1.14.1 | Product containing low flashpoint solvent (Colkate S precoating fluid) |  | ℓ | 7791
C10.1.26 | Trial sections for all seal types specified (Multiple stone seals, grade 1 aggregate with type S-R1 nonhomogeneous modified binder tack coat and type S-E1 homogenous modified binder penetration layer) |  | Lump Sum | 1
C10.1 | TOTAL CARRIED FORWARD TO SUMMARY

## C11.9
Province of KwaZulu-Natal |  |  |  | Contract No. ZNB02271/00000/00/DUR/INF/24/T
Department of Transport
CHAPTER 11 | [5 empty] | CHAPTER C11.9
THE CONSTRUCTION OF MASS EARTHWORKS, LAYERWORKS, SURFACING AND DRAINAGE ON DISTRICT ROAD 1097 (FROM KM 0+000 TO KM 4+674) IN THE DURBAN REGION
ITEM NO | DESCRIPTION | LI | UNIT | QUANTITY | RATE | AMOUNT
C11.9 | FINISHING THE ROAD AND ROAD RESERVE AND TREATING OLD ROADS
C11.9.1 | Finishing the road and road reserve:
C11.9.1.2 | Single carriageway road | LI | km | 5
C11.9 | TOTAL CARRIED FORWARD TO SUMMARY |  |  |  |  | 0

## C20.1
Province of KwaZulu-Natal |  |  |  | Contract No. ZNB02271/00000/00/DUR/INF/24/T
Department of Transport
SCHEDULE A: ROADWORKS | [5 empty] | CHAPTER C20.1
THE CONSTRUCTION OF MASS EARTHWORKS, LAYERWORKS, SURFACING AND DRAINAGE ON DISTRICT ROAD 1097 (FROM KM 0+000 TO KM 4+674) IN THE DURBAN REGION
ITEM NO | DESCRIPTION | LI | UNIT | QUANTITY | RATE | AMOUNT
C20.1 | TESTING MATERIALS AND JUDGEMENT OF WORKMANSHIP
C20.1.2.2 | Employer’s contribution to other special tests
(a) | Specify test |  | Prime Cost | 500000 | 1 | 500000
(a.i) | Handling costs and profit in respect of item C20.1.2.2(a) |  | % | 500000
C20.1 | TOTAL CARRIED FORWARD TO SUMMARY

## Chapter A
| Province of KwaZulu-Natal |  |  |  | Contract No. ZNB02271/00000/00/DUR/INF/24/T
Department of Transport
THE CONSTRUCTION OF MASS EARTHWORKS, LAYERWORKS, SURFACING AND DRAINAGE ON DISTRICT ROAD 1097 (FROM KM 0+000 TO KM 4+674) IN THE DURBAN REGION
SCHEDULE A: ROADWORKS - SUMMARY (MAIN CONTRACTORS BOQ)
| CHAPTER | DESCRIPTION |  |  | FROM PAGE | AMOUNT
| C1.2 | GENERAL REQUIREMENTS AND PAYMENT |  |  | C30
| C1.3 | CONTRACTOR'S SITE ESTABLISHMENT AND GENERAL OBLIGATIONS | 0 | #VALUE! | C32
| C1.4 | FACILITIES FOR THE ENGINEER | 0 | #VALUE! | C33
| C1.5 | ACCOMMODATION OF TRAFFIC | 0 | #VALUE! | C36
| C1.6 | CLEARING AND GRUBBING | 0 | #VALUE! | C40
| C1.7 | LOADING AND HAULING | 0 | #VALUE! | C42
| C2.1 | GENERAL REQUIREMENTS AND TRENCHING FOR SERVICES | 0 | #VALUE! | C43
| C2.2 | DRY SERVICES | 0 | #VALUE! | C44
| C3.2 | CULVERTS | 0 | #VALUE! | C45
| C4.1 | BORROW MATERIALS | 0 | #VALUE! | C47
| C4.2 | CUT MATERIALS | 0 | #VALUE! | C49
| C4.4 | COMMERCIAL MATERIALS | #VALUE! | #VALUE! | C51
| C4.5 | ALTERNATIVE MATERIALS | 0 | #VALUE! | C52
| C5.1 | ROADBED | 0 | #VALUE! | C53
| C5.2 | FILL | 0 | #VALUE! | C54
0 | C5.3 | ROAD PAVEMENT LAYERS | 0 | #VALUE! | C55
| C5.4 | STABILISATION | 0 | #VALUE! | C56
| C8.1 | PRIME COAT | 0 | #VALUE! | C57
| C9.1 | ASPHALT LAYERS | 0 | #VALUE! | C58
| C10.1 | GENERAL REQUIREMENTS FOR SURFACE TREATMENTS | #VALUE! | #VALUE! | C59
| C11.9 | FINISHING THE ROAD AND ROAD RESERVE AND TREATING OLD ROADS | 0 | #VALUE! | C61
| C20.1 | TESTING MATERIALS AND JUDGEMENT OF WORKMANSHIP |  |  | C62
SUBTOTAL CARRIED FORWARD

## Chapter E
Province of KwaZulu-Natal |  |  |  | Contract No. ZNB02271/00000/00/DUR/INF/24/T
Department of Transport
SCHEDULE E: EXPANDED PUBLIC WORKS PROGRAMME (EPWP) | [5 empty] | CHAPTER E
THE CONSTRUCTION OF MASS EARTHWORKS, LAYERWORKS, SURFACING AND DRAINAGE ON DISTRICT ROAD 1097 (FROM KM 0+000 TO KM 4+674) IN THE DURBAN REGION
ITEM NO | DESCRIPTION | LI | UNIT | QUANTITY | RATE | AMOUNT
E | EXPANDED PUBLIC WORKS PROGRAMME (EPWP)
E6.01 | Provision of training venue facility, including the cost of transport the learners to and from this facility |  | Lump Sum | 1
E6.02 | Training of learners employed by the contractor or by the Targeted Enterprise subcontractors:
(a) | Generic Skills:
(a.i) | Training costs |  | Prov Sum | 400000 | 1 | 400000
(a.ii) | Handling costs and profit in respect of subitem E6.02(a)(i) above. |  | % | 400000
(b) | Entrepreneurial skills:
(b.i) | Training costs |  | Prov Sum | 600000 | 1 | 600000
(b.ii) | Handling costs and profit in respect of subitem E6.02(b)(i) above. |  | % | 600000
(c) | Construction skills:
(c.i) | Training costs |  | Prov Sum | 600000 | 1 | 600000
(c.ii) | Handling costs and profit in respect of subitem E6.02(c)(i) above. |  | % | 600000
(d) | Transportation and accommodation costs of selected learners only, while receiving off-site training:
(d.i) | Transportation and accommodation costs |  | Prov Sum | 295000 | 1 | 295000
(d.ii) | Handling costs and profit in respect of subitem E6.02(d)(i) above. |  | % | 295000
E6.03 | Payments associated with the NYS programme:
(a) | Employment of NYS workers |  | Prov Sum | 270000 | 1 | 270000
(b) | Provision of tools and apparel for the NYS workers |  | Prov Sum | 150000 | 1 | 150000
(c) | Handling cost and profit in respect of subitem E6.03(a) and (b) above |  | % | 420000
(d) | Training of NYS workers:
(d.i) | Provision of training for NYS workers |  | Prov Sum | 750000 | 1 | 750000
(d.ii) | Handling costs and profit in respect of subitem subitem E6.03(d)(i) above |  | % | 750000
(e) | Liaison with the Employer’s project manager and the training service provider:
(e.i) | Liaison conducted by the construction manager |  | hr | 350
(e.ii) | Liaison conducted by senior site foreman |  | hr | 200
E | TOTAL CARRIED FORWARD TO SUMMARY

## E
Province of KwaZulu-Natal |  | Contract No. ZNB02271/00000/00/DUR/INF/24/T
Department of Transport
THE CONSTRUCTION OF MASS EARTHWORKS, LAYERWORKS, SURFACING AND DRAINAGE ON DISTRICT ROAD 1097 (FROM KM 0+000 TO KM 4+674) IN THE DURBAN REGION
SCHEDULE E : EXPANDED PUBLIC WORKS PROGRAMME (EPWP)
CHAPTER | DESCRIPTION | FROM PAGE | AMOUNT
E | EXPANDED PUBLIC WORKS PROGRAMME (EPWP)
TOTAL SCHEDULE E : EXPANDED PUBLIC WORKS PROGRAMME (EPWP) |  |  | 0

## Chapter F
Province of KwaZulu-Natal |  |  |  | Contract No. ZNB02271/00000/00/DUR/INF/24/T
Department of Transport
SCHEDULE F: SMALL CONTRACTOR DEVELOPMENT | [5 empty] | CHAPTER F
THE CONSTRUCTION OF MASS EARTHWORKS, LAYERWORKS, SURFACING AND DRAINAGE ON DISTRICT ROAD 1097 (FROM KM 0+000 TO KM 4+674) IN THE DURBAN REGION
ITEM NO | DESCRIPTION | LI | UNIT | QUANTITY | RATE | AMOUNT
F | SMALL CONTRACTOR DEVELOPMENT
F10.1 | Procurement of Targeted Enterprises:
(a) | Management and execution of Targeted Enterprise procurement process:
(a.i) | Procurement process for the appointment of CIDB contractor grading designation 1 Targeted Enterprise subcontractor (100 copies of the tender document required for each individual tender) |  | No | 8
(a.ii) | Procurement process for the appointment of CIDB contractor grading designation 2 Targeted Enterprise subcontractor (80 copies of the tender document required for each individual tender) |  | No | 2
(a.iii) | Procurement process for the appointment of CIDB contractor grading designation 3 Targeted Enterprise subcontractor (60 copies of the tender document required for each individual tender) |  | No | 6
(a.iv) | Procurement process for the appointment of CIDB contractor grading designation 4 Targeted Enterprise subcontractor (50 copies of the tender document required for each individual tender) |  | No | 1
F10.2 | Construction Works for Targeted Enterprise subcontractors:
(a) | Payments associated with the construction Works carried out by Targeted Enterprise subcontractors |  | Prov Sum | 27583718.21 | 1 | 27583718.21
(b) | Handling costs and profit in respect of subitem F10.02(a) |  | % | 27583718.21
(c) | Supply of materials and small construction equipment to assist Targeted Enterprise subcontractors |  | Prov Sum | 2000000 | 1 | 2000000
(d) | Handling costs and profit in respect of subitem F10.02(c) |  | % | 2000000
(e) | Management of the Targeted Enterprise subcontractors |  | Month | 18
F | TOTAL CARRIED FORWARD
Province of KwaZulu-Natal |  |  |  | Contract No. ZNB02271/00000/00/DUR/INF/24/T
Department of Transport
SCHEDULE F: SMALL CONTRACTOR DEVELOPMENT | [5 empty] | CHAPTER F
THE CONSTRUCTION OF MASS EARTHWORKS, LAYERWORKS, SURFACING AND DRAINAGE ON DISTRICT ROAD 1097 (FROM KM 0+000 TO KM 4+674) IN THE DURBAN REGION
ITEM NO | DESCRIPTION |  | UNIT | QUANTITY | RATE | AMOUNT
TOTAL BROUGHT FORWARD
F10.03 | Training of Targeted Enterprise subcontractors:
(a) | Generic Skills
(a.i) | Training costs |  | Prov Sum | 150000 | 1 | 150000
(a.ii) | Handling costs and profit in respect of subitem F10.03(a)(i) |  | % | 150000
(b) | Entrepreneurial skills:
(b.i) | Training costs |  | Prov Sum | 150000 | 1 | 150000
(b.ii) | Handling costs and profit in respect of subitem F10.03(b)(i) |  | % | 150000
(c) | Construction skills:
(c.i) | Training costs |  | Prov Sum | 150000 | 1 | 150000
(c.ii) | Handling costs and profit in respect of subitem F10.03(c)(i) |  | % | 150000
(d) | Transportation and accommodation costs of selected learners only, while receiving off-site training:
(d.i) | Transportation and accommodation costs |  | Prov Sum | 120000 | 1 | 120000
(d.ii) | Handling costs and profit in respect of subitem F10.03(d)(i) |  | % | 120000
F | TOTAL CARRIED FORWARD TO SUMMARY

## F
Province of KwaZulu-Natal |  | Contract No. ZNB02271/00000/00/DUR/INF/24/T
Department of Transport
THE CONSTRUCTION OF MASS EARTHWORKS, LAYERWORKS, SURFACING AND DRAINAGE ON DISTRICT ROAD 1097 (FROM KM 0+000 TO KM 4+674) IN THE DURBAN REGION
SCHEDULE F : SMALL CONTRACTOR DEVELOPMENT
CHAPTER | DESCRIPTION | FROM PAGE | AMOUNT
F | SMALL CONTRACTOR DEVELOPMENT
TOTAL SCHEDULE F : SMALL CONTRACTOR DEVELOPMENT |  |  | 0

## Summary
Province of KwaZulu-Natal | Contract No. ZNB02271/00000/00/DUR/INF/24/T
Department of Transport
THE CONSTRUCTION OF MASS EARTHWORKS, LAYERWORKS, SURFACING AND DRAINAGE ON DISTRICT ROAD 1097 (FROM KM 0+000 TO KM 4+674) IN THE DURBAN REGION
C2.3 SUMMARY OF BILL OF QUANTITIES
SCHEDULE | FROM PAGE | AMOUNT
TOTAL SCHEDULE A : ROADWORKS
TOTAL SCHEDULE E : EXPANDED PUBLIC WORKS PROGRAMME (EPWP)
TOTAL SCHEDULE F : SMALL CONTRACTOR DEVELOPMENT
SUBTOTAL 1
CONTRACT SKILLS DEVELOPMENT GOALS – CSDG (0.25% of SUBTOTAL 1)
SUBTOTAL 2
Add: Contingencies (10% of SUBTOTAL 2)
SUBTOTAL 3
Contract Price Adjustment - CPA (10% of SUBTOTAL 3)
SUBTOTAL 4
VAT (15% of Subtotal 3)
TOTAL CARRIED FORWARD TO FORM OF OFFER