## BOQ
CONTRACT NO. ZNB01315/00000/00/POR/INF/22/T: PROVISION OF MAINTENANCE ON VARIOUS PROVINCIAL ROADS OVER A PERIOD OF 36 MONTHS WITHIN UMZUMBE NORTHERN ZONE 2 UNDER COST CENTRE PORT SHEPSTONE IN THE DURBAN REGION. CIDB GRADE 7CE OR HIGHER
[5 empty] | . | 15219504.0469
ITEM |  | DESCRIPTION | UNIT | QTY | RATE | Amount
C1 | GENERAL
C1.2 | GENERAL REQUIREMENTS AND PROVISIONS
C1.2.1 |  | Environmental Management
| C1.2.1.1 | Monitoring of compliance with and reporting on the EMP | month | 36 |  | 0
| C1.2.1.2 | Dedicated environmental officer (if specified in the Contract Documentation) | month | 36 |  | 0
C1.2.2 |  | Programming and Reporting
| C1.2.2.1 | Submission of a Scheme 1 Programme | lump sum | 1 |  | 0
| C1.2.2.3 | Submission of a Scheme 2 Initial Programme | lump sum | 1 |  | 0
| C1.2.2.4 | Submission of a Scheme 2 Full Programme | lump sum | 1 |  | 0
| C1.2.2.5 | Reviewing and updating a Scheme 2 programme every month | month | 36 |  | 0
C1.2.3 |  | Routine road maintenance of existing public roads within the Site of the Works or other public roads outside the Site of the Works which are used as detours
| C 1.2.3.1 | Grass cutting | ha | 31 |  | 0
0
PSC1.2.5 | PSC1.2.5 | Safety
| PSC1.2.5.1 | Health and safety plan | lump sum | 1
0
| PSC1.2.5.2 | Implementation of health and safety plan |  | 0
|  | (b) Fixed obligations | Lump sum | 1 |  | 0
|  | (c) Time related obligations | Month | 36 |  | 0
C1.2.8 |  | Dayworks
0
| C1.2.8.1 | Personnel |  | 0
0
|  | (a) Unskilled labourer | hr | 2228 |  | 0
|  | (c) Skilled labourer | hr | 844 |  | 0
|  | (e) Foreman | hr | 457 |  | 0
|  | (f)Skilled artisan | hr | 0 |  | 0
| C1.2.8.2 | Construction equipment |  | 0
0
|  | (a) Motor grader, self propelled, mass not less than 9 tons, power approximately 100 Kw | hr | 96 |  | 0
|  | (b) Vibratory roller, 9-12 ton mass | hr | 108 |  | 0
|  | (e) Tractor loader backhoe, 55-70 kW, 0.5m3 bucket | hr | 80 |  | 0
|  | (f) Excavator, minimum power 105 kW | hr | 23 |  | 0
|  | (h) Other equipment |  | 0
|  | (i) Bulldozer (Min 104 kW or similar) | hr | 5 |  | 0
|  | (ii) Tip trucks (Min. 10.0m³ capacity) | hr | 254 |  | 0
|  | (iii) Water cart (Min. 10 000 litre) | hr | 150 |  | 0
| C1.2.8.3 | Vehicles |  | 0
0
|  | (b) Flatbed truck, 10 ton minimum load capacity | km | 252 |  | 0
|  | (c)Dump truck (10 ton) | km | 48 |  | 0
| C1.2.8.4 | Materials
|  | (a)Procurement of materials | Prov.Sum | 1 | 125500 | 125500
|  | (b)Contractor's handling costs, profit and all other charges in respect of item C1.2.8.4(a) | % | 125500 |  | 0
PSC.1.2.3.10 |  | Stakeholder liaison
|  | (a)Project Liaison Committee | Prov.Sum | 1 | 450000 | 450000
|  | (b)Handling cost and profit in respect of subitem PSC 1.2.3.10 (a) | % | 450000 |  | 0
|  | (c) Project Liaison Officer | Prov.Sum | 1 | 450000 | 450000
|  | (d)Handling cost and profit in respect of subitem PSC1.2.3.10 (c) | % | 450000 |  | 0
PSC.1.2.3.11 |  | Compensation for Surveyor
|  | (a) Provision of Survey as requested by the Engineer | Prov.Sum | 1 | 100000 | 100000
|  | (b) Handling cost and profit in respect of subitem PSC 1.2.3.11(a) | % | 100000 |  | 0
PSC.1.2.3.12 |  | Compensation for Geotechnical Consultant
|  | (a) Provision of Geotechnical Engineering Specialist as requested by the Engineer | Prov.Sum | 1 | 100000 | 100000
|  | (b) Handling cost and profit in respect of subitem PSC 1.2.3.12 (a) | % | 100000 |  | 0
PSC.1.2.3.13 |  | Compensation for Environmental Consultant
|  | (a) Provision of Environmental Consultant as requested by the Engineer | Prov.Sum | 1 | 100000 | 100000
|  | (b) Handling cost and profit in respect of subitem PSC 1.2.3.13(a) | % | 100000 |  | 0
PSC.1.2.3.14 |  | Compensation for Health and Safety Agent
|  | (a) Provision of a Health and Safety Agent as requested by the Engineer | Prov.Sum | 1 | 500000 | 500000
|  | (b) Handling cost and profit in respect of subitem PSC 1.2.3.14(a) | % | 500000 |  | 0
PSC.1.2.3.15 |  | Adhoc Designs as conducted by the Engineer
|  | (a) Provision of a Adhoc designs as conducted by Registered Professional (Pr Eng or PR Tech Eng) | Prov.Sum | 1 | 200000 | 200000
|  | (b) Handling cost and profit in respect of subitem PSC 1.2.3.15(a) | % | 200000 |  | 0
Sub-Total | [5 empty] | 2025500
C1.3 | CONTRACTOR'S ESTABLISHMENT ON SITE AND GENERAL ON SITE AND GENERAL OBLIGATIONS
C1.3.1 | PSC1.3.1 | The Contractor's general obligations
| C1.3.1.1 | Fixed obligations | lump sum | 1 |  | 0
| C1.3.1.2 | Value-related obligations | lump sum | 1 |  | 0
| C1.3.1.3 | Time-related obligations | month | 36 |  | 0
C1.3.2 |  | Contract sign boards | m2 | 250 |  | 0
Sub-Total | [5 empty] | 0
C1.6 | CLEARING AND GRUBBING
C1.6.1 |  | Clearing
| C1.6.1.1 | Clearing with machines and some hand labour where necessary | ha | 1.0574 |  | 0
0
C1.6.3 |  | Removal and grubbing of large trees and tree stumps:
| C1.6.3.1 | Girth equal to or exceeding 1,0m up to and including 2,0m | No | 31.0177 |  | 0
Sub-Total | [5 empty] | 0
C1.7 | LOADING AND HAULING
| C1.7.2.2 | Hauling material to spoil and off-loading it at a designated spoil or stockpile area:
|  | (b)Soil and gravel material | m3 - km | 25315.2594 |  | 0
|  | (c)Boulders, hard material and concrete | m3 - km | 4362.5688 |  | 0
Sub-Total | [5 empty] | 0
C3 | DRAINAGE
C3.1 | DRAINS
C3.1.1 |  | Excavation for open drains:
| C3.1.1.1 | Excavating all material situated within the following depth ranges below the surface level using conventional methods:
|  | (a) 0m to 1.5m (V-drain, Mitre drains and Meadow drains) | m³ | 13.1707 |  | 0
0
| C3.1.1.2 | Extra over sub-item C3.1.1.1 for excavation in hard and boulder material, irrespective of depth | m3 | 0.86821 |  | 0
C3.1.2 |  | Clearing, shaping and disposal of accumulated sediment in existing unlined open drains |  | 0
| C3.1.2.1 | Using conventional methods (v-drains, mitre drain) | m³ | 3107.08 |  | 0
0
C3.1.3 |  | Excavation, clearing and disposal of accumulated sediment in existing lined drains and drainage systems |  | 0
0
| C3.1.3.1 | Using conventional methods (up to 1,5m): |  | 0
0
|  | (a)Manholes and inlet and outlet structures | m3 | 3.9938 |  | 0
0
|  | (b)Culvert barrels | m3 | 1.7885 |  | 0
0
|  | (c)Concrete or other lined side drains | m3 | 32.3235 |  | 0
0
| C3.1.3.3 | Using labour enhanced construction methods: |  | 0
0
|  | (a) Manholes and inlet and outlet structures | m3 | 1.9361 |  | 0
0
|  | (b) Culvert barrels | m3 | 2.7088 |  | 0
0
|  | (c) Concrete or other lined side drains | m3 | 92.2039 |  | 0
0
C3.1.15 |  | Repairing or replacing existing drainage systems | provisional sum | 1 | 30000 | 30000
|  | Handling cost, profit and all other charges in respect of item C3.1.15 | % | 30000 |  | 0
Sub-Total | [5 empty] | 30000
C3.3 | CONCRETE KERBING AND CHANNELING, ASPHALT BERMS,CHUTES,DOWNPIPES, AS WELL AS CONCRETE, STONE PITCHED AND GABION LININGS FOR OPEN DRAINS
C3.3.1 |  | Concrete kerbing:
| C3.3.1.1 | Prefabricated kerbing
|  | (a) Precast kerb FIG 3 (to SABS 927 - refer Concrete Pavement Detail) | m | 5.5565 |  | 0
0
| C3.3.1.2 | Cast in situ kerbing |  | 0
0
|  | State type of kerb, class of concrete with reference to drawing | m | 0.64248 |  | 0
0
C3.3.2 |  | Concrete kerbing-channeling combination: |  | 0
0
| C3.3.2.1 | Prefabricated kerbing-channeling (description of type of channel and bedding with reference to drawing) |  | 0
0
|  | (a)Type B Semi Mountable Kerb (Fig 7) as per Dwg | m | 8.6821 |  | 0
0
C3.3.3 |  | Extra over items C3.3.1 and C3.3.2 for concrete kerbing or concrete kerbing and channeling on curves |  | 0
0
| C3.3.3.1 | On curves of radii more than or equal to 5,0m but less than 20m | m | 1.4239 |  | 0
0
C3.3.8 |  | Linings for open drains:
| C3.3.8.1 | Cast in situ concrete (Class 20/19) lining as per SD0601/2 | m3 | 1.4152 |  | 0
0
| C3.3.8.2 | ClassU2 surface finish to cast in situ concrete (type of open drain indicated) |  | 0
0
|  | (b)Type E (1000m wide) | m2 | 14.0737 |  | 0
0
C3.3.9 | C3.3.9 | Formwork to cast in situ concrete lining for open drains (Class F2 surface finish): |  | 0
0
| C3.3.9.1 | To sides with formwork on the internal face only | m2 | 1.7364 |  | 0
0
| C3.3.9.3 | To ends of slabs | m2 | 0.4341 |  | 0
0
C3.3.10 |  | Sealed joints in concrete and stone pitched linings of open drains |  | 0
0
|  | (a)Silicone-based sealant as per Dwg No | m | 2.6046 |  | 0
0
C3.3.12.3 |  | Welded steel fabric | kg | 25.0392 |  | 0
0
Sub-Total | [5 empty] | 0
C4 | EARTHWORKS AND PAVEMENT LAYERS: MATERIALS
C4.3 | EXISTING ROAD MATERIALS
C4.3.2 |  | Cleaning the existing road surface
| C4.3.2.1 | Cost to clean the road surface | provisional sum | 1 | 25000 | 25000
| C4.3.2.2 | Handling costs and profit in respect of item C4.3.2.1 | % | 25000 |  | 0
C4.3.5 |  | Providing the milling machine on the site
| C4.3.5.2 | Large milling machine with a cutting width exceeding 1,2m | No | 0.23498 |  | 0
0
C4.3.6 |  | Milling and removal of existing asphalt layers with an average milling depth (Contractor takes ownership) |  | 0
0
| C4.3.6.2 | Exceeding 50mm but not exceeding 100mm | m3 | 136.4074 |  | 0
0
| C4.3.6.3 | Exceeding 100mm | m3 | 5.1696 |  | 0
C4.3.18 |  | Excavate non-compliant or excess pavement layer material to spoil in sites designated by the Contractor, material consisting of |  | 0
0
| C4.3.18.2 | Crushed stone, macadam, gravel and sand material | m3 | 90.8208 |  | 0
Sub-Total | [5 empty] | 25000
C4.4 | COMMERCIAL MATERIALS
C4.4.2 |  | Commercial materials identified by the Contractor from commercial, private or other non-commercial suppliers (source of material must be licenced)
| C4.4.2.1 | Pavement layer material:
|  | (j) Type G7 materials | m3 | 27.7279 |  | 0
|  | (q) Natural or crushed gravel material for the wearing course of an unsealed road | m3 | 1049.3147 |  | 0
C4.4.4 |  | Cementitious stabilising agents |  | 0
0
|  | (a) Cement CEM II or III | t | 12.2191 |  | 0
Sub-Total | [5 empty] | 0
C5 | EARTHWORKS AND PAVEMENT LAYERS: CONSTRUCTION
C5.1 | ROADBED
C5.1.1 |  | Roadbed construction and compaction:
| C5.1.1.2 | Compaction of in-situ material to 93% of MDD | m3 | 6686.0765 |  | 0
Sub-Total | [5 empty] | 0
C5.2 | FILL
C5.2.2 |  | Fill construction:
| C5.2.2.1 | Normal fill material in compacted layer thicknesses of 200mm and less:
|  | (b) Compacted to 93% of MDD | m3 | 2.3498 |  | 0
C5.2.5 |  | Fill in sidewalk: |  | 0
0
| C5.2.5.2 | Fill material in sidewalk compacted to 93% of MDD using labour enhanced methods of construction and light hand equipment | m3 | 19.9735 |  | 0
Sub-Total | [5 empty] | 0
C5.3 | ROAD PAVEMENT LAYERS
C5.3.2 |  | Construction of pavement layers
|  | (g) Gravel wearing course layer (150 mm) compacted to 95 % of MDD | m³ | 6912.4822 |  | 0
|  | (i) Lower subbase gravel layer (unstabilised) (layer thickness indicated) compacted to 95 % of MDD | m³ | 29.6078 |  | 0
|  | (k) Upper subbase gravel layer (unstabilised), (layer thickness indicated) compacted to 97 % of MDD | m³ | 12.924 |  | 0
|  | (m) Gravel base layer (unstabilised), (layer thickness indicated) compacted to 100 % of MDD | m³ | 12.6891 |  | 0
Sub-Total | [5 empty] | 0
C5.4 | STABILISATION
C5.4.2 |  | Chemical stabilisation:
| C5.4.2.1 | Chemical stabilisation (150 mm) of pavement layers (C4 base layer)
|  | (a) Chemical stabilisation (150mm thick) of pavement layers (C4 base layer) | m3 | 120.4286 |  | 0
0
C5.4.5 |  | Cementitious stabilisation agents for pavement layers:
0
| C5.4.5.2 | Addition of cementitious stabilisation agents (CEM III 32,5N) for pavement layers and spreading the agent using bags and labour enhancement methods. |  | 0
0
|  | (a) Cement (Cem CEM III 32,5N) | t | 10.5742 |  | 0
0
C5.4.10 |  | Provision and application of water for curing | kℓ | 18.0937 |  | 0
Sub-Total | [5 empty] | 0
C6 | CONCRETE LAYERS
C6.1 | PAVER LAID CONCRETE LAYERS
C6.1.1 |  | Construction of trial section (Complete: including texturing and curing)
| C6.1.1.2 | Labour enhanced construction (160mm 35/20) | m2 | 26.0831 |  | 0
0
C6.1.2 |  | Construction of jointed concrete pavement (JCP) (Excluding texturing and curing) |  | 0
0
| C6.1.2.1 | JCP without dowels: |  | 0
|  | (b) Labour enhanced construction (160 mm) | m² | 525.421 |  | 0
0
| C6.1.2.3 | Additional concrete placed to thicken up the slab at joints as specified in the Contract Documentation | m³ | 7.0495 |  | 0
0
C6.1.4 |  | Texturing and curing the concrete pavement |  | 0
0
| C6.1.4.2 | Burlap-dragged and broom finish only | m2 | 525.421 |  | 0
0
| C6.1.4.3 | Curing: |  | 0
0
|  | (b) Labour enhanced construction | m2 | 525.421 |  | 0
0
C6.1.5 |  | Variation in the rate of application of the curing compound | ℓ | 26.553 |  | 0
0
C6.1.6 |  | Joints
0
| C6.1.6.3 | Sealed transverse contraction joints sawn in two separate operations (widths as shown on the drawings - refer Concrete Pavement Detail) | m | 35.4824 |  | 0
0
| C6.1.6.4 | Dowel bars: mild steel inserted in new concrete (indicate diameter, length and position on drawings): |  | 0
|  | Pre-installed on approved frame | No | 114.9065 |  | 0
0
| C6.1.6.5 | Tie-bars: installed in new concrete |  | 0
|  | (b) High tensile steel (12 mm dia, and 650 mm long and 750 c/c shape code 37 tie-bar) | No | 111.2642 |  | 0
0
C6.1.7 |  | Steel reinforcement in concrete pavements |  | 0
0
| C6.1.7.3 | Welded steel fabric | kg | 1173.1505 |  | 0
0
C6.1.8 |  | Drilling of testing of cores |  | 0
0
| C6.1.8.1 | 100mm cores drilled from pavement for testing of compressive strength | No | 1.0574 |  | 0
Sub-Total | [5 empty] | 0
C7 | REPAIR CONCRETE LAYERS
C7.2 | REPAIR TO EXISTING JOINTS AND UNCONTROLLED CRACKS IN CONCRETE PAVEMENTS
C7.2.1 |  | Transverse and longitudinal crack and joint repairs incorporating the following treatments
| C7.2.1.5 | Saw cutting of cracks and joints in one operation (indicate depth and width) | m | 0.82244 |  | 0
0
C7.2.2 |  | Grouting of cracks | m | 0.82244 |  | 0
Sub-Total | [5 empty] | 0
C7.3 | REMOVAL AND REINSTATEMENT OF EXISITNG CONCRETE LAYERS
C7.3.3 |  | Partial Depth Repairs using hand placed fine concrete | m3 | 0.23498 |  | 0
Sub-Total | [5 empty] | 0
C8 | REPAIR EXISITNG LAYERS
C8.1 | PRIME COAT
C8.1.1 |  | Prime coat:
| C8.1.1.1 | MC -10 cut-back bitumen | ℓ | 671.0826 |  | 0
C8.1.3 |  | Extra over item C8.1.1 for applying the prime coat accessible only to hand-held or light equipment |  | 0 |  | 0
0
| PSC8.6.7.1 | Tack Coat | ℓ | 1423.9749 |  | 0
Sub-Total | [5 empty] | 0
C8.8 | PATCHING AND EDGE BREAK REPAIR
C8.8.1 |  | Saw cutting pavement layers for patching
| C8.8.1.1 | Asphalt or bituminous surfacing to an average depth
|  | (a) Not exceeding 50 mm | m | 70.2672 |  | 0
|  | (c) Excedding 100 mm | m | 312.8614 |  | 0
0
| C8.8.1.3 | Granular layers to an average depth |  | 0
0
|  | (b)Not exceeding 200mm | m | 17.0099 |  | 0
0
C8.8.2 |  | Excavation in existing pavements for patching (non-milling) |  | 0
0
| C8.8.2.1 | Asphalt layers |  | 0
0
|  | (a) Not exceeding 10 m² including for edge repairs wider than 250mm | m3 | 0.81 |  | 0
|  | (b) Exceeding 10 m² but not exceeding 50 m² including for edge repairs wider than 250mm | m3 | 1.215 |  | 0
|  | (c) Exceeding 50 m² up to 100 m² including for edge repairs wider than 250mm | m3 | 0.6075 |  | 0
|  | (d) Exceeding 100 m² | m3 | 40.4999 |  | 0
0
| C8.8.2.2 | Cemented layers |  | 0
0
|  | (a) Not exceeding 10 m2, including for edge repairs wider than 250 mm | m3 | 1.8225 |  | 0
|  | (b) Exceeding 10 m2 but not exceeding 50 m2, including for edge repairs wider than 250 mm | m3 | 1.0125 |  | 0
|  | (d) Exceeding 100 m2 | m3 | 143.572 |  | 0
0
| C8.8.2.3 | Other layers (Granular layers) |  | 0
0
|  | (a) Not exceeding 10 m2, including for edge repairs wider than 250 mm | m3 | 0.81 |  | 0
|  | (b) Exceeding 10 m2 but not exceeding 50 m2, including for edge repairs wider than 250 mm | m3 | 1.0125 |  | 0
|  | (d) Exceeding 100 m2 | m3 | 127.5745 |  | 0
0
C8.8.3 |  | Compacting the floor of excavations for patching (97% MOD ) | m2 | 1020.5963 |  | 0
0
C8.8.4 |  | Backfilling of excavations for patching with: |  | 0
0
| C8.8.4.1 | Chemically stabilized pavement material (G2 material using 3% cem III 32,5 N cement) for a patch with a surface area: |  | 0
0
|  | (a) Not exceeding 10 m2, including for edge repairs wider than 250 mm | m3 | 2.6325 |  | 0
|  | (b) Exceeding 10 m2 but not exceeding 50 m2, including for edge repairs wider than 250 mm | m3 | 1.8225 |  | 0
|  | (d) Exceeding 100 m2 | m3 | 271.1465 |  | 0
0
| C8.8.4.3 | Asphalt for a patch with a surface area(Sand skeletal mix – continuously graded) |  | 0
0
|  | (a) Not exceeding 10 m2, including for edge repairs wider than 250 mm | t | 1.8225 |  | 0
|  | (b) Exceeding 10 m2 but not exceeding 50 m2, including for edge repairs wider than 250 mm | t | 2.835 |  | 0
|  | (c) Exceeding 50 m2 up to 100 m2, including for edge repairs wider than 250 mm | t | 1.62 |  | 0
|  | (d) Exceeding 100 m2 | t | 101.2496 |  | 0
0
| C8.8.4.4 | Granular base material (state type and density) for a patch with a surface area |  | 0
C8.8.5 |  | Geosynthetic patching |  | 0
0
PSC8.8/PSC1.5.7.7 |  | Traffic Calming Measure |  | 0
0
|  | (b) Installation of speed hump (Refer to Standard Detail 0314) (See C11.6 for signage) | m | 12.96 |  | 0
Sub-Total | [5 empty] | 0
C9 | ASPHALT LAYERS
C9.1 | ASPHALT LAYERS
C9.1.3 |  | Application of bond coat
| C9.1.3.3 | Applied by hand using brushes on all exposed transverse and longitudinal construction joints | ℓ | 3796.2401 |  | 0
0
C9.1.5 |  | Asphalt surfacing |  | 0
0
|  | (e) Sand skeletal mix – continuously graded (40 mm, PG 47-22/ Paver laid) | m2 | 9710.3021 |  | 0
|  | (j) Sand skeletal mix – continuously graded (30 mm, PG 58-22/ Hand laid) - sidewalks | m2 | 12.6891 |  | 0
C9.1.10 |  | Variation rates |  | 0
|  | (k) Sand skeletal mix - 9,5 mm NMPS continuously graded (20 mm thick, PG 47-22/ Hand Laid) | m2 | 132.1777 |  | 0
0
C9.1.13 |  | Coring of asphalt layers |  | 0
0
| C9.1.13.1 | 100mm diameter | No | 34.0725 |  | 0
Sub-Total | [5 empty] | 0
C11 | ANCILLARY ROADWORKS
C11.6 | ROAD SIGNS
C11.6.1 |  | Road signboards with painted or coloured semi-matt background. Symbols, lettering and borders in semi- matt black or in Class I retro-reflective material, where the sign board is constructed from:
| C11.6.1.7 | Regulatory signs, permanent
|  | (a) 600 mm diameter (pre-painted galvanized steel plate, background class 1, symbol class 1) | No | 5.8746 |  | 0
|  | (b) 900 mm diameter (pre-painted galvanized steel plate, background class 1, symbol class 1) | No | 2.9373 |  | 0
|  | (c) 1200 mm diameter (pre-painted galvanized steel plate, background class 1, symbol class 1) | No | 0.58746 |  | 0
Sub-Total | [5 empty] | 0
C11.9 | FINISHING THE ROAD RESERVE AND TREATING OLD ROADS
C11.9.1 |  | Finishing the road and road reserve:
| C11.9.1.2 | Single carriageway road | km | 10.5742 |  | 0
Sub-Total | [5 empty] | 0
C12 | GEOTECHNICAL
C12.6 | MECHANICALLY STABILISED EARTH AND GABIONS
C12.6.16 |  | Gabion Boxes and Mattresses:
| C12.6.16.1 | Galvanised Gabion Boxes & Mattresses
|  | 1,5m x 1m x 1m x 2 layers (Total 2m high) gabion baskets | m³ | 6.3445 |  | 0
|  | 1m x 1m x 1m layer gabion baskets | m³ | 11 |  | 0
C12.6.17 |  | Geotextile Filter fabric (200g/m² - Grade C Light Separation) | m2 | 24 |  | 0
Sub-Total | [5 empty] | 0
C20 | QUALITY ASSURANCE
C20.1 | TESTING MATERIALS AND JUDGEMENT OF WORKMANSHIP
|  | (a) Compaction test | prime cost sum | 1 | 30000 | 30000
|  | (i) Handling costs and profit in respect of item C20.1.2.2(a) | % | 30000 |  | 0
Sub-Total | [5 empty] | 30000
SCHEDULE A: TOTAL | [5 empty] | 2110500
SCHEDULE B: PART E, F and G
PART E |  | Expanded Public Works Programme |  |  |  | 2320000
PART F |  | Small Contract Development |  |  |  | 6284879.85
SUB-TOTAL 1 | [5 empty] | 10715379.85
PART G |  | Contract Skills Development Goal |  |  |  | 26788.4496
CALCULATION OF TENDER SUM
A | SUB-TOTAL 2 |  |  |  |  | 10742168.2996
B | CONTINGENCIES |  |  | 10% |  | 1074216.83
C | SUB-TOTAL 3 ( A + B) |  |  |  |  | 11816385.1296
D | CONTRACT PRICE ADJUSTMENT |  |  | 12% |  | 1417966.2156
E | VAT ON SUB TOTAL 3 |  |  | 15% |  | 1985152.7018
F | TENDER SUM (D + E) |  |  |  |  | 15219504.0469

## Road Assessment (hidden)
#REF!
ROAD ASSESSMENT FORM | [29 empty] | Type/ Catogery of Pothole
SUB-TOTAL (for filter) |  |  | C |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
|  |  | B |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
TOTALS |  |  | A |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 |  |  | 0 |  |  |  | 0 | 0
Chainage |  | Road | 0 - 10 m2 |  |  |  | > 10 m2 < 50 m2 |  |  |  | > 50 m2 < 100 m2 |  |  |  | > 100 m2 |  |  |  | Crack Seal | Edge Break | Rut/Depression |  |  | Overlay Sections |  |  |  | Finishing the Road | INSERT MORE ROWS IF THE CHAINAGE HAS MANY POTHOLES OF DIFFERENT SQUARE METRES. HIDE CHAINAGES THAT HAVE ZERO INPUTS | A | B | C
From | To |  | Length (m) | Width (m) | Catogery (A,B or C) | Area (m2) | Length (m) | Width (m) | Catogery (A,B or C) | Area (m2) | Length (m) | Width (m) | Catogery (A,B or C) | Area (m2) | Length (m) | Width (m) | Catogery (A,B or C) | Area (m2) | Length (m) | Length (m) | Length (m) | Width (m) | Area (m2) | Length (m) | Width (m) | H (m) | Area (m2) | km Measured on Site |  | Surface only | Surface+base | Surface+base+subbase
[30 empty] | 50mm | +150mm | +150mm
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
SUB-TOTAL (for filter) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTALS |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Saw Cutting | 0 | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| Subtotals from filtering for base and subbase----> |  |  | 0 | Asphalt | 0 | 40mm Th Asphalt A+B+C |  |  | 0 |  |  |  | 0 |  |  |  | 0 | FOR ITEM "C8.8.2.2" & "C8.8.2.3" FILTER FOR "B" FOR BASE AND "C" FOR SUBBASE ON CATERGORY COLUMNS. TAKE THE SUB-TOTAL AREA AFTER THE FILTER AND ENTER THE AREA MANUALLY ON CELL "G141 & G142", "K141 & K142", "O141 & O142" AND "S141 & S142"
|  |  |  | 0 | A | 0 | Ditto- Only A |  |  | 0 |  |  |  | 0 |  |  |  | 0
|  |  |  | 0 | B | 0 | Hole Dpth 150mm- G2 |  |  | 0 |  |  |  | 0 |  |  |  | 0
|  |  |  | 0 | C | 0 | Hole Dpth 300mm- G2 |  |  | 0 |  |  |  | 0 |  |  |  | 0
|  |  |  | 0 | Total | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| Type/ Catogery of Pothole | [8 empty] | 40-50mm Thick Asphalt - Cat A
|  | Cat A=40mm |  | Cat B=150mm |  | Cat C=300mm |  |  |  | 150mm Thich G2 Cat B Total Depth= 190-200mm
|  | Surface only |  | Surface+base |  | Surface+base+subbase | [9 empty] | IDMS J. Jaganath
|  | 40-50mm |  | +150mm |  | +150mm |  |  |  | 150mm Thich G2 Cat C Total Depth= 340-350mm | [5 empty] | DATE:
Total Depth |  | 40-50mm |  | 190-200mm |  | 340-350mm |  |  | C-Section
Note on F7: Thulani Ntombela: Specify Catergory A, B or C for the purpose of idenfiying the depth of pothole. A=Surface (30mm - 50mm deep) B=Base (150mm deep) C=Subbase (150mm depth) If pothole depth exceeds Subbase, increase the depth from 150mm to 300mm, etc.

## Part E
CONTRACT NO. ZNB01315/00000/00/POR/INF/22/T: PROVISION OF MAINTENANCE ON VARIOUS PROVINCIAL ROADS OVER A PERIOD OF 36 MONTHS WITHIN UMZUMBE NORTHERN ZONE 2 UNDER COST CENTRE PORT SHEPSTONE IN THE DURBAN REGION. CIDB GRADE 7CE OR HIGHER
ITEM | DESCRIPTION |  | QTY | RATE | AMT
PART E: EXPANDED PUBLIC WORK PROGRAMME
E | EXPANDED PUBLIC WORKS PROGRAMME
E6.01 | Provision of the training venue facility, including the cost of transporting the learners to and from this facility:
|  | Sum | 1 |  | 0
E6.02 | Training of learners employed by the contractor or Targeted Enterprise subcontractors:
(a) Generic skills:
| (i) Training costs | Prov sum | 1 | 400000 | 400000
| (ii) Handling costs and profit in respect of subitem E6.02(a)(i) | % | 400000 |  | 0
(b) Entrepreneurial skills:
| (i) Training costs | Prov sum | 1 | 500000 | 500000
| (ii) Handling costs and profit in respect of subitem E6.02(b)(i) | % | 500000 |  | 0
(c) Construction skills:
| (i) Training costs | Prov sum | 1 | 600000 | 600000
| (ii) Handling costs and profit in respect of subitem E6.02(c)(i) | % | 600000 |  | 0
(d) Transportation and accommodation costs of selected learners only, while receiving off-site training:
| (i) Transportation and accommodation costs | Prov sum | 1 | 250000 | 250000
| (ii) Handling costs and profit in respect of subitem E6.02(d)(i) | % | 250000 |  | 0
E6.03 | Payments associated with the NYS programme:
| (a) Employment of NYS workers | Prov sum | 1 | 440000 | 440000
| (b) Provision of tools and apparel for NYS workers | Prov sum | 1 | 30000 | 30000
| (c) Handling costs and profit in respect of subitems E6.03(a) and (b) | % | 470000 |  | 0
(d) Training of NYS workers:
| (i) Provision of training for NYS workers | Prov sum | 1 | 100000 | 100000
| (ii) Handling costs and profit in respect of subitem E6.03(d)(i) | % | 100000 |  | 0
(e) Liaison with the Employer’s project manager and the training service provider:
| (i) Liaison conducted by the Construction Manager | h | 30 |  | 0
| (ii) Liaison conducted by the senior site foreman | h | 60 |  | 0
TOTAL CARRIED FORWARD TO SUMMARY |  |  |  |  | 2320000

## Part F
CONTRACT NO. ZNB01315/00000/00/POR/INF/22/T: PROVISION OF MAINTENANCE ON VARIOUS PROVINCIAL ROADS OVER A PERIOD OF 36 MONTHS WITHIN UMZUMBE NORTHERN ZONE 2 UNDER COST CENTRE PORT SHEPSTONE IN THE DURBAN REGION. CIDB GRADE 7CE OR HIGHER
ITEM | DESCRIPTION |  | QTY | RATE | AMT
PART F: SMALL CONTRACTOR DEVELOPMENT
F | SMALL CONTRACTOR DEVELOPMENT
F10.01 | Procurement of Targeted Enterprises:
(a) Management and execution of Targeted Enterprise procurement process:
| (i) Procurement process for the appointment of CIDB contractor grading designation 1 Targeted Enterprise subcontractor (100 copies of the tender document required for each individual tender) | No | 3 |  | 0
| (ii) Procurement process for the appointment of CIDB contractor grading designation 2 Targeted Enterprise subcontractor (80 copies of the tender document required for each individual tender) | No | 2 |  | 0
| (iii) Procurement process for the appointment of CIDB contractor grading designation 3 Targeted Enterprise subcontractor (60 copies of the tender document required for each individual tender) | No | 1 |  | 0
| (iv) Procurement process for the appointment of CIDB contractor grading designation 4 Targeted Enterprise subcontractor (50 copies of the tender document required for each individual tender) | No |  | 60000 | 0
| (v) Procurement process for the appointment of CIDB contractor grading designation 5 Targeted Enterprise subcontractor (40 copies of the tender document required for each individual tender) | No | 0 | 60000 | 0
| (vi) Procurement process for the appointment of CIDB contractor grading designation 6 Targeted Enterprise subcontractor (40 copies of the tender document required for each individual tender) | No | 0 | 60000 | 0
F10.02 | Construction Works for Targeted Enterprise subcontractors:
| (a) Payments associated with the construction Works carried out by Targeted Enterprise subcontractors | Prov sum | 1 | 4327903.88 | 4327903.88
| (b) Handling costs and profit in respect of subitem F10.02(a) | % | 4327903.88 |  | 0
| (c) Supply of materials and small construction equipment to assist Targeted Enterprise subcontractors | Prov sum | 1 | 1081975.97 | 1081975.97
| (d) Handling costs and profit in respect of subitem F10.02(c) | % | 1081975.97 |  | 0
| (e) Management of Targeted Enterprise subcontractors | Sum | 1 |  | 0
F10.03 | Training of learners employed by Targeted Enterprise subcontractors:
(a) Generic skills:
| (i) Training costs | Prov sum | 1 | 200000 | 200000
| (ii) Handling costs and profit in respect of subitem F10.03(a)(i) | % | 200000 |  | 0
(b) Entrepreneurial skills:
| (i) Training costs | Prov sum | 1 | 250000 | 250000
| (ii) Handling costs and profit in respect of subitem F10.03(b)(i) | % | 250000 |  | 0
(c) Construction skills:
| (i) Training costs | Prov sum | 1 | 300000 | 300000
| (ii) Handling costs and profit in respect of subitem F10.03(c)(i) | % | 300000 |  | 0
(d) Transportation and accommodation costs of selected learners only, while receiving off-site training:
| (i) Transportation and accommodation costs | Prov sum | 1 | 125000 | 125000
| (ii) Handling costs and profit in respect of subitem G10.03(d)(i) | % | 125000 |  | 0
TOTAL CARRIED FORWARD TO SUMMARY |  |  |  |  | 6284879.85

## Part G (Not to be priced)
CONTRACT NO. ZNB01315/00000/00/POR/INF/22/T: PROVISION OF MAINTENANCE ON VARIOUS PROVINCIAL ROADS OVER A PERIOD OF 36 MONTHS WITHIN UMZUMBE NORTHERN ZONE 2 UNDER COST CENTRE PORT SHEPSTONE IN THE DURBAN REGION. CIDB GRADE 7CE OR HIGHER
ITEM |  | DESCRIPTION | UNIT | QTY | RATE | AMOUNT
PART G: CIDB CONTRACT SKILLS DEVELOPMENT GOAL
G7 |  | CIDB CONTRACT SKILLS DEVELOPMENT GOAL
G7.01 |  | Payments associated with the Contract Skills Development Goals:
(a) Employment of Leaners employed under Method 1
|  | (i) Povision for stipends | Prov Sum | 1 |  | 0
|  | (ii) Provision for additional Costs | Prov Sum | 1 |  | 0
(b) Employment of Leaners employed under Method 2
|  | (i) Povision for stipends | Prov Sum | 1 |  | 0
|  | (ii) Provision for additional Costs | Prov Sum | 1 |  | 0
(c) Employment of Leaners employed under Method 3
|  | (i) Povision for stipends | Prov Sum | 1 |  | 0
|  | (ii) Provision for mentorship | Prov Sum | 1 |  | 0
|  | (iii) Provision for additional Costs | Prov Sum | 1 |  | 0
(d) Employment of Candidates employed under Method 4
|  | (i) Povision for stipends | Prov Sum | 1 |  | 0
|  | (ii) Provision for mentorship | Prov Sum | 1 |  | 0
|  | (iii) Provision for additional Costs | Prov Sum | 1 |  | 0
(e) Liaison with the Employer’s project manager and the training service provider:
|  | (i) Liaison conducted by the Construction Manager | hr | 20 |  | 0
TOTAL CARRIED FORWARD TO SUMMARY | [5 empty] | 26788.4496
metre (m)
metre (m)
C2.3.27 |  |  | Extra over item C2.3.21 for encasing (wrapping) joints
| C2.3.27.1 |  | State for each water main the number of joints to be encased (wrapped)
State diameter
State diameter
C2.3.28 |  |  | Installation of hydrants and water meters
| C2.3.28.1 |  | Describe hydrant type
| C2.3.28.2 |  | Describe water meter type
| C2.3.28.3 |  | Etc., insert additional items as required
C2.3.29 |  |  | Bedding for water mains (Class B and C) and fill blanket compacted to 90 % of MDD (100 % for sand)
C2.3.29.1
C2.3.29.2